## PMR 1st sem 2019
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of 30 June 2019
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
| 1) Construction of 2-storey, 6-rooms Ynares School Building (Type III) at Libis Elem. School, Brgy. Libis, Binangonan, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 204 cd | SEF | 10024097.94 |  | 10024097.94 | 10003085.28 |  | 10003085.28 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 2) Construction of 4-storey, 12-rooms Ynares School Building at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 306 cd | SEF | 21687978.26 |  | 21687978.26 |  |  | Failure of bidding | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 3) Construction of 1-storey, 2-rooms Ynares School Building at Bangad Elem. School, Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 104 cd | SEF | 2724004.86 |  | 2724004.86 | 2717557.11 |  | 2717557.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 4) Construction of 2-storey, 4-rooms Ynares School Building (Type III) at Sapang Elem. School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 152 cd | SEF | 7396807.98 |  | 7396807.98 | 7377621.48 |  | 7377621.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 5) Construction of 4-storey, 24-rooms Ynares School Building at Cainta Elem. School, Brgy.San Roque, Cainta, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 408 cd | SEF | 53142128.65 |  | 53142128.65 | 53090999.15 |  | 53090999.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 6) Construction of 2-storey Ynares Multi-Purpose Building at Cainta Greenpark Village Zone 5, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 134 cd | GF | 3110793.74 |  | 3110793.74 | 3099076.81 |  | 3099076.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 7) Construction of 15x30m Ynares Multi-Purpose Covered Court at Adelina Homes Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 120 cd | GF | 3856859.32 |  | 3856859.32 | 3845528.61 |  | 3845528.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 8) Construction of 4-storey, 8-rooms Ynares School Building at Taytay National High School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 228 cd | SEF | 16591049.22 |  | 16591049.22 | 16558861.97 |  | 16558861.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 9) Construction of 2-storey, 4-rooms Ynares School Building (Type III) at Pinugay Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 168 cd | SEF | 7177861.43 |  | 7177861.43 | 7159707.46 |  | 7159707.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 10) Construction of 2-storey, 6-rooms Ynares School Building at Dalig Elem. School, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 204 cd | SEF | 9947467.45 |  | 9947467.45 | 9928340.48 |  | 9928340.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 11) Construction of 2-storey, 4-rooms Ynares School Building at Eusebio C. Ocampo Memorial Elem. School, Brgy. Lambac, Cardona, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 164 cd | SEF | 7854466.67 |  | 7854466.67 | 7835252.57 |  | 7835252.57 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 12) Construction of 1-storey, 2-rooms Ynares School Building at Subay Elem. School, Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 96 cd | SEF | 2388339.41 |  | 2388339.41 | 2377235.65 |  | 2377235.65 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 13) Construction of 3-storey, 6-rooms Ynares School Building at Bugarin Elem. School, Sitio Bugarin, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 220 cd | SEF | 12986648.24 |  | 12986648.24 | 12961679.16 |  | 12961679.16 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 14) Construction of 2-storey, 4-rooms Ynares School Building (Type III) at Malaya Elem. School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 168 cd | SEF | 7244397.38 |  | 7244397.38 | 7228260.84 |  | 7228260.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 15) Construction of 2-storey, 4-rooms Ynares School Building (Type III) at Niogan Elem. School, Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 168 cd | SEF | 7508767.88 |  | 7508767.88 | 7488937.54 |  | 7488937.54 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 16) Construction of 2-storey, 4-rooms Ynares School Building (Type III) at Pililla Elem. School Central, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 172 cd | SEF | 6886267.33 |  | 6886267.33 | 6869954.65 |  | 6869954.65 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 17) Construction of 1-storey, 2-rooms Ynares School Building at Balagbag Elem. School, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 100 cd | SEF | 2673060.15 |  | 2673060.15 | 2661574.13 |  | 2661574.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 18) Construction of 3-storey, 4-rooms Ynares School Building at San Isidro Labrador Elem. School, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 220 cd | SEF | 10367490.27 |  | 10367490.27 | 10346086.31 |  | 10346086.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 19) Construction of 2-storey Ynares Multi-Purpose Building at Southville 8C, Phase 1K2, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 139 cd | GF | 3120865.23 |  | 3120865.23 | 3108446.61 |  | 3108446.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 20) Construction of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Phase 8/8A Eastwood Subdivision., Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 128 cd | GF | 4008220.2 |  | 4008220.2 | 3996703.75 |  | 3996703.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 21) Construction of 1-storey Ynares Multi-Purpose Building at Tierra Monte Subd., Phase 2, Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 76 cd | GF | 1988566.69 |  | 1988566.69 | 1978353.5 |  | 1978353.5 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 22) Construction of 1-storey, 4-rooms Ynares School Building at Sta. Ines National High School, Brgy. Sta. Ines, Tanay, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 132cd | SEF | 4350912.37 |  | 4350912.37 | 4336459.45 |  | 4336459.45 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 23) Construction of 4-storey, 8-rooms Ynares School Building at Aldea National High School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding | 2018-12-14 | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 228 cd | SEF | 17068081.61 |  | 17068081.61 | 17030619.92 |  | 17030619.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 24) Construction of 1-storey, 3-rooms Ynares School Building at Cuyambay Elem. School, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 116 cd | SEF | 3572607.12 |  | 3572607.12 | 3559617.2 |  | 3559617.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 25) Construction of 2-storey, 2-rooms Ynares School Building at Abuyod Elem. School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 92 cd | SEF | 3455945 |  | 3455945 | 3443938.33 |  | 3443938.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 26) Construction of Drywall Partition at Ground Floor of Ynares Event Center, Ynares Center Compound, Brgy. San Roque, Antipolo City | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 58 cd | GF | 1499162.87 |  | 1499162.87 | 1490069.95 |  | 1490069.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 27) Various Repair at Rizal Provincial Hospital System-Morong Main, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 60 cd | GF | 1337940.07 |  | 1337940.07 | 1328931.78 |  | 1328931.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 28) Construction of 10x22m Ynares Multi-Purpose Covered Court (Rafter Type) at Manggahan Elem. School, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 - 24 Dec 2018 | 2018-12-26 |  | 2019-01-08 | 2019-01-14 | 2019-01-21 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 96 cd | SEF | 2345937.39 |  | 2345937.39 | 2334339.64 |  | 2334339.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-18 |  | 2018-12-18
| 1) Construction of Concrete Bleacher with Fence of Ynares Multi-Purpose Covered Court at Bagong Nayon IV Elem. School, Brgy. San Isidro, Antipolo City | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 60 cd | GF | 1291385.54 |  | 1291385.54 | 1282295.8 |  | 1282295.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 2) Repair / Repainting of Various School Bldg. at Rizal National Science High School, Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 88 cd | SEF | 3546094.7 |  | 3546094.7 | 3534094.41 |  | 3534094.41 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 3) Repair / Repainting of Ynares School Buildings at Sitio Mata Elem. School, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 60 cd | GF | 1415413.65 |  | 1415413.65 | 1406404.07 |  | 1406404.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 4) Construction of Concrete Bleacher and Ynares Stage and Improvement of Ynares Multi-Purpose Covered Court at Rotary Ville, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 100 cd | GF | 1885889.4 |  | 1885889.4 | 1875818.17 |  | 1875818.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 5) Rehabilitation of 1-storey, 3-rooms Ynares School Bldg. at Taytay National High School, Meralco Village, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 60 cd | GF | 1337934.11 |  | 1337934.11 | 1329097.02 |  | 1329097.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 6) Construction of 12x24m Ynares Multi-Purpose Covered Court and Stage at Dolores Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 120 cd | GF | 3157416.39 |  | 3157416.39 | 3142834.83 |  | 3142834.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 7) Asphalt Overlaying of Ben Llagas St. going to Sitio Don Lucas, Brgy. Concepcion, Baras, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 32 cd | GF | 2239490.02 |  | 2239490.02 | 2228111.61 |  | 2228111.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 8) Concreting of Road leading to San Roque Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 78 cd | GF | 1323813.54 |  | 1323813.54 | 1314786.24 |  | 1314786.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 9) Asphalt Overlaying of Roads at Brgy. Concepcion, Baras, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 32 cd | GF | 3494288.67 |  | 3494288.67 | 3482237.89 |  | 3482237.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 10) Asphalt Overlaying (portion) of H.F. Constantino Road, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2018-12-18 | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 44 cd | GF | 7306834.38 |  | 7306834.38 | 7287076.43 |  | 7287076.43 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 11) Asphalt Overlay of Road at Purok 1,2 & 3, Brgy. Palay-Palay, Jalajala, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 40 cd | GF | 3309271.71 |  | 3309271.71 | 3297325.8 |  | 3297325.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 12) Repair / Repainting of Ynares School Buildings at Palay-Palay Elem. School, Brgy. Palay-Palay, Jalajala, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 68 cd | SEF | 1935822.38 |  | 1935822.38 | 1925261.65 |  | 1925261.65 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 13) Improvement / Repainting of Fence and Construction of Covered Pathwalk at Malaya Elem. School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 56 cd | SEF | 1153650.46 |  | 1153650.46 | 1144726.86 |  | 1144726.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 14) Construction of Stone Masonry River Wall (portion) along Quisao River (near Quisao Bridge), Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 90 cd | GF | 3101633.7 |  | 3101633.7 | 3089632.01 |  | 3089632.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 15) Construction of 2-storey Ynares Multi-Purpose Bldg. at Kasiglahan Village Senior High School, Phase IK2, Kasiglahan Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 136 cd | GF | 3048902.09 |  | 3048902.09 | 3036346.07 |  | 3036346.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 16) Construction of Additional 2nd Floor of Existing Ynares Multi-Purpose Bldg. at Sitio Wawa, Brgy. San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 132 cd | GF | 3633450.59 |  | 3633450.59 | 3621681.03 |  | 3621681.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 17) Construction of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at Catmon Elementary School, Brgy. San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 100 cd | GF | 3003726.03 |  | 3003726.03 | 2991100.66 |  | 2991100.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 18) Improvement of 10x30m Ynares Multi-Purpose Covered Court at Burgos National High School, Sorrento Annex, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 82 cd | GF | 1496845.5 |  | 1496845.5 | 1488632.01 |  | 1488632.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 19) Improvement / Repair / Repainting of 25x36m Ynares Multi-Purpose Covered Court (Rafter Type)and Ynares Stage at Kasiglahan Village National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 85 cd | GF | 2029972.45 |  | 2029972.45 | 2018919.15 |  | 2018919.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 20) Improvement / Repair / Repainting of Ynares School Buildings, 15x24m Ynares Multi-Purpose Covered Court & Ynares Stage at Geronimo Elem. School, Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 80 cd | GF | 2158678.79 |  | 2158678.79 | 2147877.08 |  | 2147877.08 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 21) Construction of Fence & Improvement of 17x30m Ynares Multi-Purpose Covered Court (Arc Type) at Sub-Urban Village Phase 1A, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 68 cd | GF | 1493157.81 |  | 1493157.81 | 1484641.26 |  | 1484641.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 22) Repair / Repainting of 1-storey, 5-rooms Ynares School Bldg. at Puray National High School, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 72 cd | GF | 2711955.91 |  | 2711955.91 | 2700946.38 |  | 2700946.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 23) Construction of 10x24m Ynares Multi-Purpose Covered Court (Rafter Type) at San Mateo National High School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 96 cd | GF | 2395037.86 |  | 2395037.86 | 2385232.47 |  | 2385232.47 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 24) Construction of Drainage System at Pintong Bukawe National High School, Brgy. Pintong Bukawe, San Mateo, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 48 cd | SEF | 1011648.84 |  | 1011648.84 | 1003032.76 |  | 1003032.76 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 25) Repair / Improvement of 2-storey, 6-rooms Ynares School Bldg. at Sto. Nino Elementary School, Brgy. Sto. Nino, San Mateo, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 84 cd | SEF | 2262074.82 |  | 2262074.82 | 2251032.48 |  | 2251032.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 26) Construction of 1-storey Multi-Purpose Bldg. at Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 86 cd | GF | 1968806.99 |  | 1968806.99 | 1958936.59 |  | 1958936.59 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 27) Improvement of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Balikatan Village, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 64 cd | GF | 1095352.08 |  | 1095352.08 | 1086394.96 |  | 1086394.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 28) Improvement / Repair / Repainting of 17x30m Ynares Multi-Purpose Covered Court (Arc Type) & 2-storey Ynares Multi-Purose Bldg. (Barangay Hall), Brgy. San Gabriel, Teresa, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 64 cd | GF | 1828728.7 |  | 1828728.7 | 1818790.23 |  | 1818790.23 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 29) Repair / Repainting of 2-storey, 6-rooms Ynares School Bldg. at Bagumbayan Elem. School, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 40 cd | SEF | 1091636.06 |  | 1091636.06 | 1083646.21 |  | 1083646.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 30) Repair of Ynares School Building, Ynares Comfort Rooms & Rehabilitation of School Ground Concrete Flooring at Quiterio San Jose Elementary, School Brgy. May-Iba, Teresa, Rizal | PEO |  | Public Bidding |  | 21 -27 Dec 2018 | 2018-12-28 |  | 2019-01-11 | 2019-01-17 | 2019-01-22 |  | 2019-01-25 | 2019-02-01 | 2019-02-12 | 74 cd | SEF | 2318611.29 |  | 2318611.29 | 2307556.24 |  | 2307556.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2018-12-21 |  | 2018-12-21
| 1) Construction of Ynares Stage and Improvement of 17x30m Ynares Multi-Purpose Covered Court at Grandvalley Subd., Phase 3, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 86 cd | GF | 1236348.52 |  | 1236348.52 | 1229051.43 |  | 1229051.43 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 2) Improvement/Concreting of Villaluz St., Dulo, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 120 cd | GF | 2490470.58 |  | 2490470.58 | 2480945.79 |  | 2480945.79 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 3) Rehabilitation of Road at Saturn St. and Jupiter St. at Constellation Homes Phase I, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 96 cd | GF | 3334340.78 |  | 3334340.78 | 3321946.39 |  | 3321946.39 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 4) Construction of 2-storey Ynares Multi-Purpose Bldg. at Tagpos Public Market, Brgy. Tagpos, Binangonan, Rizal | PEO |  | Public Bidding | 2019-01-07 | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 215 cd | GF | 19075069.35 |  | 19075069.35 | 19039850.93 |  | 19039850.93 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 5) Improvement/Rehabilitation of Wharf, Brgy. Kalinawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 60 cd | GF | 907970.26 |  | 907970.26 | 899765.44 |  | 899765.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 6) Construction of Covered Pathwalk, Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 52 cd | GF | 1027650.92 |  | 1027650.92 | 1018900.73 |  | 1018900.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 7) Improvement of Pathwalk and Repair of Gutter of School Building at Don Jose Ynares Memorial High School, Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 56 cd | SEF | 828795.74 |  | 828795.74 | 820727.64 |  | 820727.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 8) Improvement/Concreting of Road at Sapang Malalim, Brgy. Tatala, Binangonan, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 96 cd | GF | 2329295.49 |  | 2329295.49 | 2317895.02 |  | 2317895.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 9) Improvement of Ynares Multi-Purpose Covered Court at Vista Verde Executive Village, Phase 3, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 52 cd | GF | 966484.84 |  | 966484.84 | 956307.01 |  | 956307.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 10) Repair/Repainting of 2-units, 2-storey, 4-rooms Ynares School Bldg. at San Francisco Elementary School, Brgy. Muzon, Taytay, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 32 cd | SEF | 775562.84 |  | 775562.84 | 767988.11 |  | 767988.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 11) Construction of Perimeter Fence of 1-storey Ynares Multi-Purpose Bldg. at Sitio Habitat, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 64 cd | GF | 769226.88 |  | 769226.88 | 761209.33 |  | 761209.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 12) Construction of 3-storey, 6-rooms Ynares School Building at Antonio C. Esguerra Memorial National High School, Taytay, Rizal | PEO |  | Public Bidding | 2019-01-07 | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 220 cd | SEF | 12577394.1 |  | 12577394.1 | 0 |  |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 13) Improvement/Construction of Stone Masonry Slope Protection of Creek & Concreting of Creekbed, Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 80 cd | GF | 2732429.2 |  | 2732429.2 | 2721725.97 |  | 2721725.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 14) Construction of 2-storey, 6-rooms Ynares School Building at Bayugo Elementary School, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding | 2019-01-07 | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 204 cd | SEF | 9574673.77 |  | 9574673.77 | 9555494.32 |  | 9555494.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 15) Installation of Solar Streetlights at Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 80 cd | GF | 4360293.05 |  | 4360293.05 | 4346339.41 |  | 4346339.41 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 16) Rehabilitation of Stone Masonry Wall (portion) of Morong River, Sitio Tupas, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 80 cd | PDRRMF | 1908415.94 |  | 1908415.94 | 1898261.78 |  | 1898261.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 17) Construction of Drainage Canal (portion) at Turentigue St., Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 80 cd | GF | 1368101.47 |  | 1368101.47 | 1359046.91 |  | 1359046.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 18) Construction of 1-storey, 2-rooms Ynares School Building at Hulo National High School, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 102 cd | SEF | 2735337.01 |  | 2735337.01 | 2724383.76 |  | 2724383.76 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 19) Construction of Fence & Covered Pathwalk at Brgy. San Isidro & Brgy. San Jose, Rodriguez, Rizal; a) Construction of Fence (portion) at Southville 8C Elem. School, Brgy. San Isidro, b) Construction of Covered Pathwalk at Kasiglahan Village National High School, Brgy. San Jose | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 61 cd | GF | 2485598.95 |  | 2485598.95 | 2473881.25 |  | 2473881.25 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 20) Construction of 2-units Ynares Stage at Brgy. San Isidro, Rodriguez, Rizal; a) Construction of Ynares Stage at Eastwood Residences Subd. Phase 4, Brgy. San Isidro, b) Construction of Ynares Stage at Eastwood Residences, Terra Verde, Phase 3, Brgy. San Isidro | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 70 cd | GF | 1802346.43 |  | 1802346.43 | 1791853.36 |  | 1791853.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 21) Repair/Repainting of Ynares School Buildings, 17x30m Ynares Multi-Purpose Covered Court and Stage at Brgy. Macabud, Rodriguez, Rizal; a) Repair/Repainting of Ynares School Buildings, 17x30m Ynares Multi-Purpose Covered Court and Stage at Macabud National High School, Brgy. Macabud, b) Repair/Repainting of Ynares School Buildings at Macabud Elem. School, Brgy. Macabud | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 64 cd | GF | 1909206.45 |  | 1909206.45 | 1899133.8 |  | 1899133.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 22) Repair/Repainting of Ynares School Buildings & Construction of Covered Pathwalk at Brgy. Burgos, Rodriguez, Rizal; a) Repair/Repainting of Ynares School Buildings at Burgos National High School (Sorento Extension & Main Campus), Brgy. Burgos , b) Construction of Covered Pathwalk at Burgos Elem. School Unit I, Brgy. Burgos | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 80 cd | GF | 1641823.57 |  | 1641823.57 | 1632692.43 |  | 1632692.43 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 23) Repair/Repainting of Ynares School Bldg. and Construction of Welcome Arc at San Mateo and Rodriguez, Rizal; a) Repair/Repainting of 2-storey, 8-rooms Ynares School Bldg. at San Mateo Elem. School, Brgy. Sta. Ana, San Mateo, b) Construction of 3-units Welcome Arc at Southville 8B, Phase 5, Brgy. San Isidro, Rodriguez | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 60 cd | SEF | 1387354.42 |  | 1387354.42 | 1378129.49 |  | 1378129.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 24) Improvement/Rehabilitation/Repair/Repainting of 19x27m Diaz Multi-Purpose Covered Court (Rafter Type), Stage and Concrete Bleacher at Modesta Village, Brgy. Sto Niňo, San Mateo, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 97 cd | GF | 4517958.69 |  | 4517958.69 | 4503654.12 |  | 4503654.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 25) Rehabilitation/Concreting of Yellow Bell St. and Rose St., Modesta Village, Brgy. Sto. Niňo, San Mateo, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 82 cd | GF | 3829792.31 |  | 3829792.31 | 3818305.79 |  | 3818305.79 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 26) Concreting of Waling-Waling St., Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 88 cd | GF | 3250436.7 |  | 3250436.7 | 3238831.25 |  | 3238831.25 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 27) Construction of Covered Pathwalk at Sto. Niňo Integrated School, Brgy. Sto. Niňo, Tanay, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 48 cd | GF | 951985.26 |  | 951985.26 | 942317.43 |  | 942317.43 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 28) Improvement of 15x24m Ynares Multi-Purpose Covered Court at Tablon Elem. School, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 48 cd | SEF | 939758.57 |  | 939758.57 | 931667.75 |  | 931667.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 29) Construction of Ynares Stage & Improvement of 15x24m Ynares Multi-Purpose Covered court at Tanay East National High School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 80 cd | SEF | 1629348.94 |  | 1629348.94 | 1619387.01 |  | 1619387.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 30) Concreting of Road Going to Bahay Pag-Asa St., Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 60 cd | GF | 1293644.88 |  | 1293644.88 | 1284787.48 |  | 1284787.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 31) Improvement/Concreting (portion) of Tuoy Road, Sitio Tuoy, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding | 2019-01-07 | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 120 cd | GF | 5109257.98 |  | 5109257.98 | 5091571.58 |  | 5091571.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 32) Concreting of Road at Teresa Learning Resource Center (TLRC) in Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 96 cd | GF | 2877670.01 |  | 2877670.01 | 2866284.05 |  | 2866284.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 33) Construction of Stone Masonry for Slope Protection at F. Gonzales St., Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding |  | 10 -16 Jan 2019 | 2019-01-17 |  | 2019-01-29 | 2019-02-06 | 2019-02-12 |  | 2019-02-15 | 2019-02-22 | 2019-03-01 | 60 cd | PDRRMF | 1030539.61 |  | 1030539.61 | 1021118.61 |  | 1021118.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-10 |  | 2019-01-10
| 1) Improvement/Concreting (portion) of Palmera St., Sitio Baliksaka (Phase I), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 72 cd | GF | 1499750.57 |  | 1499750.57 | 1490295.71 |  | 1490295.71 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 2) Improvement/Concreting (portion) of Mahogany Road., Sitio Baliksaka , Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 998667.05 |  | 998667.05 | 989635.32 |  | 989635.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 3) Rehabilitation / Concreting of Roads at Brgy. San Juan & Brgy. Pinugay, Baras, Rizal; a) Rehabilitation / Concreting (portion) of Ilaya St., Brgy. San Juan, b) Concreting (remaining portion) of Orchids St., Sitio Baliksaka, (Phase 8), Brgy. Pinugay | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 875069.75 |  | 875069.75 | 866949.17 |  | 866949.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 4) Concrete Overlay of Dulong Bayan St., Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 986418.26 |  | 986418.26 | 978385.12 |  | 978385.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 5) Concrete Overlay of A. Ferrera St., Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1213681.77 |  | 1213681.77 | 1204669.64 |  | 1204669.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 6) Construction of Dressing Room and Fence of Ynares Multi-Purpose Covered Court & Rehabilitation of Slope Protection of River at Brgy. Pinugay & Brgy. Mabini, Baras, Rizal; a) Construction of Dressing Room and Fence of Ynares Multi-Purpose Covered Court at Habitat Ynares Village, Brgy. Pinugay, b) Rehabilitation of Slope Protection along Baras River at M. Golla St., Brgy. Mabini | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | PDRRMF | 823344.38 |  | 823344.38 | 815312.14 |  | 815312.14 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 7) Concreting (portion) of Road at Daang Rumagit, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 827151.63 |  | 827151.63 | 818966.95 |  | 818966.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 8) Construction of Drainage Canal at Nagpatong St., Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 80 cd | GF | 1504115.01 |  | 1504115.01 | 1495378.52 |  | 1495378.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 9) Concreting of School Ground at Bernardo F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 132 cd | SEF | 2334548.36 |  | 2334548.36 | 2324538.26 |  | 2324538.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 10) Improvement/Concrete Overlaying of R. Capili St., and Rehabilitation of Stone Masonry Slope Protection of Creek, Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 80 cd | GF | 1469479.1 |  | 1469479.1 | 1461724.24 |  | 1461724.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 11) Construction of Covered Pathwalk & Repair / Repainting of Ynares Stage and Dressing Room at Brgy. Bayugo & Brgy. Bagumbong, Jalajala, Rizal; a) Construction of Covered Pathwalk at Bayugo Elementary School, Brgy. Bayugo, b) Repair / Repainting of Ynares Stage and Dressing Room at Bagumbong National High School, Brgy. Bagumbong | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1222667.2 |  | 1222667.2 | 1213935.03 |  | 1213935.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 12) Construction / Concreting of Drainage Canal, Pathways and Road at Jalajala & Tanay, Rizal; a) Construction / Concreting of Drainage Canal and Pathways at Bagumbong Elementary School, Brgy. Bagumbong, Jalajala, b) Concreting (portion) of M.H. Del Pilar St., Brgy. Kaybuto, Tanay | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 68 cd | GF | 2104318.42 |  | 2104318.42 | 2093330.42 |  | 2093330.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 13) Construction of Stone Masonry for Slope Protection of Creek at Sitio Pulong Ligaya and Sitio Lumang Nayon, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2019-01-11 | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 140 cd | GF | 8281456 |  | 8281456 | 8262329.46 |  | 8262329.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 14) Construction/Rehabilitation/Improvement of Drainage Canal & Construction of Hand Washing Facility at Morong & Pililla, Rizal; a) Construction of Drainage Canal with Cover at J. Alegre St. Upper Balante, Brgy. San Jose, Morong, b) Rehabilitation / Improvement of Drainage Canal at Zamora St., Brgy. San Jose, Morong, c) Construction of Hand Washing Facility at Malaya National High School, Brgy. Malaya, Pililla | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 68 cd | SEF | 951332.5 |  | 951332.5 | 944229.94 |  | 944229.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 15) Const. of 2-Storey Ynares Multi-Purpose Building (Morong Gad Activity and Resource Center) at Morong Municipal Hall Compound, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 132 cd | GF | 2091845.13 |  | 2091845.13 | 2080818.84 |  | 2080818.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 16) Construction of 2-storey Ynares Multi-Purpose Building, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 178 cd | GF | 4686329.91 |  | 4686329.91 | 4671318.35 |  | 4671318.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 17) Improvement of Ynares Multi-Purpose Covered Court & Stage at Halayhayin Elementary School, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | SEF | 1069412.78 |  | 1069412.78 | 1060412.72 |  | 1060412.72 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 18) Asphalt Overlaying of Various Roads, Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding | 2019-01-11 | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 5396092.54 |  | 5396092.54 | 5380067.61 |  | 5380067.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 19) Improvement of Creek and Construction of Covered Pathwalk at Malaya National High School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 64 cd | GF | 1505649.56 |  | 1505649.56 | 1496323.91 |  | 1496323.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 20) Rehabilitation/Improvement of Concrete Bleacher / Repair / Repainting of Ynares School Building, Ynares Multi-Purpose Covered Court , Canopy, School Signage and Construction of Covered Pathwalk at Brgy. Hulo, Brgy. Niogan & Brgy. Malaya, Pililla, Rizal; a) Rehabilitation / Improvement of Concrete Bleacher & Repainting of 17x30m Ynares Multi-Purpose Covered Court, Brgy. Hulo, b) Repair of 2-Storey 6-Rooms Ynares School Building & Repair of Ynares Multi-Purpose Covered Court at Niogan Elementary School, Brgy. Niogan, c) Construction of Covered Pathwalk, Gate and Repair of Canopy and School Signage at Malaya Elementary School, Brgy. Malaya | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 80 cd | GF | 3153310.9 |  | 3153310.9 | 3141030.27 |  | 3141030.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 21) Improvement/Repair of Health Center, Day Care Center & 2-storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1421820.8 |  | 1421820.8 | 1412822.58 |  | 1412822.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 22) Asphalt Overlaying of Various Roads at King David Subd., Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 32 cd | GF | 2897263.42 |  | 2897263.42 | 2887629.34 |  | 2887629.34 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 23) Construction of 1-storey Ynares Multi-Purpose Building at Southville 8c Phase 1N, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 100 cd | GF | 2051888.02 |  | 2051888.02 | 2040901.79 |  | 2040901.79 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 24) Repair/Repainting of 17x30m Ynares Multi-Purpose Covered Court (Rigid) at URS-Rodriguez, Rodriguez, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 82 cd | GF | 1289835.08 |  | 1289835.08 | 1281524.03 |  | 1281524.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 25) Construction of Drainage Canal with Cover at La Solidaridad St., Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 100 cd | GF | 2275938.24 |  | 2275938.24 | 2263939 |  | 2263939 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 26) Rehabilitation/Improvement/Concreting of Pathway/Pathwalk & Construction of Drainage System at Brgy. San Isidro & Brgy. Plaza Aldea, Tanay, Rizal; a) Rehabilitation / Concreting of Pathway at Patricio Jarin Elementary School, Brgy. San Isidro, b) Improvement/ Concreting of Pathwalk and Construction of Drainage System at Aldea National High School, Brgy. Plaza Aldea | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1635570.86 |  | 1635570.86 | 1625281.26 |  | 1625281.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 27) Construction of Ynares Stage & Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Tandang Kutyo & Brgy. Plaza Aldea, Tanay, Rizal; a) Construction of Ynares Stage at Tanay North National High School, Brgy. Tandang Kutyo, b) Installation of Electrical Lighting System of 15x24m Ynares Multi-Purpose Covered Court at Tanay East National High School, Brgy. Plaza Aldea | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 68 cd | GF | 1122138.12 |  | 1122138.12 | 1113279.18 |  | 1113279.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 28) Improvement/Repainting of 17x30m Ynares Multi-Purpose Covered Court and Ynares Stage at Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1787857.04 |  | 1787857.04 | 1778610.51 |  | 1778610.51 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 29) Installation of Solar Streetlights & Construction of Playground Fecilities at Brgy. Cayabu, Tanay, Rizal; a) Installation of Solar Streetlights at Brgy. Cayabu, b) Construction of Playground Facilities at Brgy. Cayabu | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 40 cd | GF | 1203323.36 |  | 1203323.36 | 1194134.02 |  | 1194134.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 30) Construction of Drainage Canal of Roads at Brgy. Kaybuto, Tanay, Rizal; a) Construction of Drainage Canal at Lorenzo Ramos St., Brgy. Kaybuto, b) Construction of Drainage Canal with Cover (portion) at J.M. Catolos Ext., Brgy. Kaybuto | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1043673.36 |  | 1043673.36 | 1033977.52 |  | 1033977.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 31) Improvement/ Concreting/ Construction of Drainage Canal at A. Natividad St. (Boulevard), Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 120 cd | GF | 3198900 |  | 3198900 | 3187510.48 |  | 3187510.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 32) Rehabilitation/Improvement of Drainage Canal of Roads at Brgy. May-Iba & Brgy. San Roque, Teresa, Rizal; a) Rehabilitation of Drainage Canal along Roxas Road, Brgy. May-Iba, b) Improvement of Drainage System at F.C. Francisco St., Brgy. San Roque | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 50 cd | GF | 898515.35 |  | 898515.35 | 890209.17 |  | 890209.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 33) Construction of Covered Pathwalk, at Pantay Elementary School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 17 - 23 Jan 2019 | 2019-01-24 |  | 2019-02-06 | 2019-02-13 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 52 cd | SEF | 899874.5 |  | 899874.5 | 891788.04 |  | 891788.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-17 |  | 2019-01-17
| 1) Improvement/Rehabilitation of J. Sumulong St. (Saudi Village) and P. Burgos St. (portion), Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 80 cd | GF | 2337841.76 |  | 2337841.76 | 2327813.92 |  | 2327813.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 2) Improvement/Concreting/Construction of Drainage Canal at Road Lot 6 (Mangosteen St.) at Vocalan Compound, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 70 cd | GF | 1836983.37 |  | 1836983.37 | 1827884.3 |  | 1827884.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 3) Improvement/Concreting/Construction of Drainage Canal at Road Lot 8 (Sampaloc St.) at Vocalan Compound, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 94 cd | GF | 3944797.51 |  | 3944797.51 | 3932706.6 |  | 3932706.6 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 4) Construction of Stone Masonry for Slope Protection at Gupiing Creek, Jacinto Street, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 140 cd | GF | 3363434.93 |  | 3363434.93 | 3350570.5 |  | 3350570.5 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 5) Improvement/Repair of Ynares Multi-Purpose Covered Court & Damaged Riprap along Creek at Cainta & Binangonan, Rizal; a) Improvement/Repair of Ynares Multi-Purpose Covered Court at Blk 10 Road 19 Floodway Planters, Brgy. San Andres, Cainta, b) Repair of Damaged Riprap along Creek near Aralar St. at Brgy. Pilapila, Binangonan | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 48 cd | GF | 1294823.89 |  | 1294823.89 | 1286025.55 |  | 1286025.55 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 6) Upgrading of Electrical System of Rizal Police Provincial Office Compound, Camp Gen. Licerio I. Geronimo, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 67 cd | GF | 3595136.89 |  | 3595136.89 | 3582078.39 |  | 3582078.39 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 7) Construction of Drainage Canal at Blk 38 at Sitio Lumang Ilog, Floodway B, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1087617.69 |  | 1087617.69 | 1076922.18 |  | 1076922.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 8) Rehabilitation of Flood Control Protection (Stone Masonry) along Baras River at Magtanggol St., Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | PDRRMF | 1444476.99 |  | 1444476.99 | 1435199.46 |  | 1435199.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 9) Construction of Stone Masonry for Slope Protection & Improvement of Drainage Canal at Brgy. Concepcion & Brgy. San Jose, Baras, Rizal; a) Construction of Stone Masonry for Slope Protection, Hillside Subd., Brgy. Concepcion, b) Improvement of Drainage Canal at Trabajo St., Brgy. San Jose | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | PDRRMF | 1599303.35 |  | 1599303.35 | 1588989.47 |  | 1588989.47 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 10) Rehabilitation of Road at O. Matignas St., Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 999856.02 |  | 999856.02 |  |  | CANCELLED | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 11) Improvement / Asphalt Overlay at Upper-San Carlos St. (portion), Brgy. Del Remedio, Cardona, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 64 cd | GF | 1754935.55 |  | 1754935.55 | 1745732.46 |  | 1745732.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 12) Concreting of School Ground and Construction of Fence (portion) at Tadlak Elementary School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 64 cd | GF | 1499536.15 |  | 1499536.15 | 1489516.95 |  | 1489516.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 13) Improvement/Concreting of School Ground and Rehabilitation of Stone Masonry Protection at Ticulio Elem. School, Brgy. Ticulio, Cardona, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 94 cd | SEF | 2117919.81 |  | 2117919.81 | 1489516.95 |  | 1489516.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 14) Rehabilitation of Road at Zapanta St. and Asphalt Overlaying of Campo St., Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 40 cd | GF | 1199662.3 |  | 1199662.3 | 2107264.72 |  | 2107264.72 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 15) Construction of 10x18m Ynares Multi-Purpose Covered Court at Navotas Elementary School, Brgy. Navotas, Cardona, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 88 cd | SEF | 2571187.07 |  | 2571187.07 | 2560464.84 |  | 2560464.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 16) Improvement of Ynares Multi-Purpose Covered Courts & Repair of Stage at Cardona & Morong, Rizal; a) Improvement for 17x30m Ynares Multi-Purpose Covered Court (Rigid) at Brgy. Boor, Cardona, b) Repair of Stage at Brgy. Looc, Cardona, c) Improvement/Provision of Louver, Fence and Movable Bleacher of Ynares Multi-Purpose Covered Court (Rafter Type) at Sitio Itaas, Brgy. Bombongan, Morong | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1517021.94 |  | 1517021.94 | 1507524.06 |  | 1507524.06 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 17) Repair/Improvement of Ynares Multi-Purpose Covered Court, Brgy. Maybangcal, Morong, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 64 cd | GF | 1718294.51 |  | 1718294.51 | 1704326.72 |  | 1704326.72 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 18) Construction of Stone Masonry River Wall along Quisao River near Yago Compound going to Quisao Elem. School, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2019-01-14 | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 92 cd | PDRRMF | 6723439.38 |  | 6723439.38 | 6707239.09 |  | 6707239.09 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 19) Construction of Stone Masonry Dike Barrier along Quisao River at Sitio Wawa, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | PDRRMF | 1403386.52 |  | 1403386.52 | 1394198.33 |  | 1394198.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 20) Construction of Drainage Canal with cover at M. Casas St., Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 733503.4 |  | 733503.4 | 727856.4 |  | 727856.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 21) Concreting of School Ground and Construction of Canal at Niogan Elementary School, Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 72 cd | SEF | 1399516.58 |  | 1399516.58 | 1390505.24 |  | 1390505.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 22) Repainting / Rehabilitation of Ynares Multi-Purpose Covered Court at Carlton Village, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 79 cd | GF | 975722.41 |  | 975722.41 | 967336.98 |  | 967336.98 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 23) Improvement/Repair of 15x24m Ynares Multi-Purpose Covered Court at Montalban Heights National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1438096 |  | 1438096 | 1429168.07 |  | 1429168.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 24) Repair of Ynares Stage & Improvement of Ynares Multi-Purpose Covered Court at Brgy. Mascap & Brgy. Puray, Rodriguez, Rizal; a) Repair of Ynares Stage at Mascap National High School, Brgy. Mascap, b) Improvement of 17x30m Ynares Multi-Purpose Covered Court at Brgy. Puray | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | GF | 1231129.37 |  | 1231129.37 |  |  | CANCELLED | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 25) Repair/Repainting/Improvement of 1-storey, 2-rooms Ynares School Bldg. & Completion of Kitchen Counter at Tagumpay National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 75 cd | GF | 892014.45 |  | 892014.45 | 884283.86 |  | 884283.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 26) Construction of Perimeter Fence at Eastwood Greenview Subdivision Phase 2, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 46 cd | GF | 835983.2 |  | 835983.2 | 827611.94 |  | 827611.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 27) Rehabilitation / Concreting portion of School Ground, Installation of Steel Gate & Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Guitnang Bayan I & Brgy. Ampid I, San Mateo, Rizal; a) Rehabilitation / Concreting portion of School Ground and Installation of Steel Gate at Guitnang Bayan Elementary School, Brgy. Guitnang Bayan I, b) Installation of Electrical Lighting System of 17x30m Ynares Multi-Purpose Covered Court at Moncarlo Village, Brgy. Ampid I | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 60 cd | SEF | 884315.69 |  | 884315.69 | 876292.26 |  | 876292.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 28) Improvement/Repair/ Repainting of Ynares Multi-Purpose Covered Court & Construction of Comfort Room, Fence and Concrete Bleacher at Brgy. Sto. Niňo, Brgy. Banaba & Brgy. Ampid I, San Mateo, Rizal; a) Improvement and Repainting of 17x30m Ynares Multi-Purpose Covered Court (Tennis Court) at Modesta Village, Brgy. Sto. Niňo, b) Construction of 2-Seater Comfort Room, Fence and Concrete Bleacher at Ynares Multi-Purpose Covered Court, Armel III Subdivision, Brgy. Banaba, c) Repair of 17x30m Ynares Multi-Purpose Covered Court at Moncarlo Village, Brgy. Ampid I | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 70 cd | GF | 1991915.86 |  | 1991915.86 | 1983893.59 |  | 1983893.59 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 29) Concreting of Road at Purok 2, Brgy. Pintong Bukawe, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 50 cd | GF | 720561.25 |  | 720561.25 | 712738.73 |  | 712738.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 30) Improvement/Repair of Ynares Multi-Purpose Covered Court at New San Mateo Subd., Phase 7, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 64 cd | GF | 1528296.96 |  | 1528296.96 | 1518210.99 |  | 1518210.99 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 31) Construction of Drainage Canal at F. Sandal St. to Vedallo St., Brgy. Daraitan, Tanay, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 100 cd | GF | 2999231.5 |  | 2999231.5 | 2988145.4 |  | 2988145.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 32) Improvement/Concreting (portion) of Dayapa Road, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 18 -24 Jan 2019 | 2019-01-25 |  | 2019-02-08 | 2019-02-14 | 2019-02-19 |  | 2019-02-22 | 2019-02-28 | 2019-03-07 | 120 cd | GF | 4997877.1 |  | 4997877.1 | 4983358.7 |  | 4983358.7 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-18 |  | 2019-01-18
| 1) Improvement / Concreting of Sugar Palm St., Sampaguita St. Extension, Brgy. Dela Paz, Antipolo City | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 68 | GF | 1120768.83 |  | 1120768.83 | 1111767.52 |  | 1111767.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 2) Rehabilitation / Concreting of Road and Construction of Drainage Canal at Ivory Palm St., Brgy. Dela Paz, Antipolo City | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 95 | GF | 2770961.87 |  | 2770961.87 | 2759518.06 |  | 2759518.06 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 3) Improvement of Various Pathwalk & Concreting of School Ground at Brgy. San Isidro, Antipolo City; a) Improvement of Various Pathwalk at Bagong Nayon II, Brgy. San Isidro, b) Concreting of School Ground at Daycare Center, Sitio Phase 2, Bagong Nayon II, Brgy. San Isidro | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 80 | GF | 1324911.95 |  | 1324911.95 | 1315522.35 |  | 1315522.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 4) Improvement of 17x30m Ynares Multi-Purpose Covered Court at Grandvalley Subd. Phase 3, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 88 | GF | 2495418.78 |  | 2495418.78 | 2484503.96 |  | 2484503.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 5) Impr./Concreting of Del Rosario St. (Dulo), Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 100 | GF | 3671364.49 |  | 3671364.49 | 3659706.62 |  | 3659706.62 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 6) Improvement of Ynares School & Multi-Purpose Building, Const. of Comfort Room and Repair/ Impr. Of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Brgy. San Vicente & Brgy. Mahabang Parang, Angono, Rizal; a) Improvement of 2-units 2-storey Ynares School Building at Regional Lead School for the Arts, Brgy. San Isidro, b) Improvement of 2-Storey Ynares Multi-Purpose Building at San Vicente Elem. School, Brgy. San Vicente, c) Const. of 2-Seater Comfort Room and Repair/ Impr. Of Ynares Multi-Purpose Covered Court at Meralco Village, Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 80 | GF | 1635032.26 |  | 1635032.26 | 1625723.36 |  | 1625723.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 7) Construction of Water System Level III, Brgy. Kaytome, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 148 | GF | 4856966.59 |  | 4856966.59 | 4844864.17 |  | 4844864.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 8) Improvement / Concreting / Construction of Drainage Canal / System at Brgy. San Isidro & Brgy. San Juan, Cainta, Rizal; a) Improvement / Concreting / Construction of Drainage Canal at Cainta Greenpark Village, Zone 3, Brgy. San Isidro, b) Improvement of Drainage System for Ynares Multi-Purpose Covered Court at Youngstown, Brgy. San Juan | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 60 | GF | 859383.59 |  | 859383.59 | 851384.64 |  | 851384.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 9) Improvement / Concreting / Construction of Drainage Canal at Golden Mile Subdivision, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2019-01-21 | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 190 | GF | 9638113.09 |  | 9638113.09 | 9614040.97 |  | 9614040.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 10) Rehabilitation of Electrical Lighting System of Various Ynares Ynares Multi-Purpose Covered Courts at Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 60 | GF | 943180.54 |  | 943180.54 | 934081.43 |  | 934081.43 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 11) Concreting/Improvement of Callejon II, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 60 | GF | 799381.14 |  | 799381.14 | 791331.15 |  | 791331.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 12) Construction of 2-storey Ynares Multi-Purpose Building at Bagong Pag-Asa Elementary School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 134 | GF | 3119193.75 |  | 3119193.75 | 3108643.2 |  | 3108643.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 13) Improvement / Concreting (portion) of Baras-Pinugay Road, Brgy. San Jose, Baras, Rizal | PEO |  | Public Bidding | 2019-01-21 | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 180 | GF | 15538140.86 |  | 15538140.86 | 15503109.99 |  | 15503109.99 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 14) Concreting of Ground and Impr. of Drainage Canal at Evangelista Elementary School, Brgy. Evangelista, Baras, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 60 | GF | 636766.99 |  | 636766.99 | 628703.32 |  | 628703.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 15) Asphalt Overlaying and Concrete Reblocking of road at Purok 7, Sitio Tanauan, Brgy. Palaypalay, Jalajala, Rizal | PEO |  | Public Bidding | 2019-01-21 | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 120 | GF | 11387763.94 |  | 11387763.94 | 11363610.19 |  | 11363610.19 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 16) Construction of 17x30m Ynares Multi-Purpose Covered Court (Rafter) at URS-Jaljala, Brgy. Special District, Jalajala, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 128 | GF | 4091035 |  | 4091035 | 4078011.54 |  | 4078011.54 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 17) Improvement of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Sitio Itaas, Brgy. Bombongan, Morong, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 64 | GF | 1550486.66 |  | 1550486.66 | 1540508.8 |  | 1540508.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 18) Construction of 15x24m Ynares Multi-Purpose Covered Court at Sitio Taghangin, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 112 | GF | 3700803.48 |  | 3700803.48 | 3688756.58 |  | 3688756.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 19) Repair / Improvement of 2-storey Ynares Multi-Purpose Building (Brgy Hall) at Sitio Calero, Brgy. CCL, Morong, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 40 | GF | 654288.01 |  | 654288.01 | 646250.21 |  | 646250.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 20) Repair of Ynares School Building, Ynares Multi-Purpose Covered Court and Construction of Gardenhouse at Malaya Elementary School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 64 | SEF | 911736.44 |  | 911736.44 | 903177.82 |  | 903177.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 21) Concreting of Open Space and Parking Area at Metro Montana Village, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 180 | GF | 3829805.8 |  | 3829805.8 | 3817249.91 |  | 3817249.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 22) Construction of 2-storey Ynares Multi-Purpose Building (School Canteen) at Balagbag Elem. School, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 100 | GF | 2081942.65 |  | 2081942.65 | 2070614.09 |  | 2070614.09 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 23) Rehabilitation / Concreting portion of School Ground at Dulongbayan Elementary School, Brgy. Dulong Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 50 | SEF | 844120.52 |  | 844120.52 | 835845.08 |  | 835845.08 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 24) Construction of Stone Masonry for Slope Protection of Children's Park at Sitio Waray, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 90 | GF | 2721582.84 |  | 2721582.84 | 2709853.92 |  | 2709853.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 25) Construction of Ynares Stage w/ Dressing Room at Tanay Senior High School, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 76 | GF | 1381907.21 |  | 1381907.21 | 1372635.14 |  | 1372635.14 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 26) Installation of Solar Streetlights at Sitio Tablon, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 40 | GF | 649653.98 |  | 649653.98 | 641600.42 |  | 641600.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 27) Improvement / Concreting of Road from Brgy. Proper to Sitio Tablon, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding | 2019-01-21 | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 224 | GF | 14720020.13 |  | 14720020.13 | 14694337.2 |  | 14694337.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 28) Improvement / Extension of Gateway, Provision of Pedestrian Entry & Improvement of School Arc at Quiterio San Jose Elem. School, Brgy. May-Iba, Teresa, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 60 | GF | 758527.07 |  | 758527.07 | 750516.93 |  | 750516.93 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 29) Improvement of Ynares Multi-Purpose Covered Court and Expansion and Repainting of Ynares Stage at Bagumbayan Elem. School, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 40 | GF | 854848.43 |  | 854848.43 | 846816.42 |  | 846816.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 30) Construction of Stone Masonry for Slope Protection of Teresa River at Bridge No. 1, Brgy. May-Iba, Teresa, Rizal | PEO |  | Public Bidding | 2019-01-21 | 23 - 29 Jan 2019 | 2019-01-30 |  | 2019-02-12 | 2019-02-15 | 2019-02-22 |  | 2019-02-27 | 2019-03-08 | 2019-03-14 | 252 | PDRRMF | 18151784.44 |  | 18151784.44 | 18116543.68 |  | 18116543.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-23 |  | 2019-01-23
| 1) Construction of Welcome Arc, Concrete Wall, Improvement of Drainage System & Repair of Multi-Purpose Building at Brgy. Calawis and Brgy. Dela Paz, Antipolo City; a) Construction of 1-unit Welcome Arc, Brgy. Calawis, b) Construction of Concrete Wall and Improvement of Drainage System at YMPCC, Sitio Logcom, Brgy. Dela Paz, c) Repair of Multi-Purpose Building (Muslim Cultural Center) at Phase IV-B, Bagong Nayon II, Brgy. Dela Paz | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 653946.57 |  | 653946.57 | 645681.7 |  | 645681.7 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 2) Improvement/Concreting of Aguinaldo St. (Dulo), Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 80 | GF | 1584612.24 |  | 1584612.24 | 1575324.76 |  | 1575324.76 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 3) Improvement/Concreting with Drainage Canal of Roads at St. Anthony Ville (DOMSA) Phase I, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 150 | GF | 3350704.19 |  | 3350704.19 | 3338692.61 |  | 3338692.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 4) Rehabilitation/Improvement of Various Streets at Graceville Subd., Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 75 | GF | 4899993.84 |  | 4899993.84 | 4885798.38 |  | 4885798.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 5) Improvement/Extension, Repair of Ynares Multi-Purpose Covered Court & Ynares Multi-Purpose Building and Rehabilitation of Open Spaces at Binangonan & Taytay, Rizal; a) Improvement of 10x24m Ynares Multi-Purpose Covered Court at Guronasyon Foundation Inc. National High School, Brgy. Bilibiran, Binangonan, b) Extension and Repair of 1-storey Ynares Multi-Purpose Building (Day Care Center), Brgy. Tayuman, Binangonan, c) Rehabilitation of Open Spaces at Rizal Chamber of Commerce Bldg., Brgy. Dolores, Taytay | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 68 | SEF | 2071741.14 |  | 2071741.14 | 2062403.92 |  | 2062403.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 6) Rehabilitation/Concreting (portion) of Oja Road at Sitio Bagbagin, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1197768.06 |  | 1197768.06 | 1189452.29 |  | 1189452.29 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 7) Improvement/Concreting/Construction of Drainage Canal of Road Lot 7 (Mansanas St.) at Vocalan Compound, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 52 | GF | 999825.92 |  | 999825.92 | 991957.3 |  | 991957.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 8) Improvement/Concreting/Construction of Drainage Canal of Road Lot 8 (Bayabas St.) at Vocalan Compound, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 52 | GF | 999825.92 |  | 999825.92 | 991957.3 |  | 991957.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 9) Construction of 4-storey, 12-rooms Ynares School Building at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding | 2019-01-25 | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 396 | SEF | 21687978.26 |  | 21687978.26 |  |  | FAILURE OF BIDDING | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 10) Improvement of Ynares Multi-Purpose Covered Court at Brookside Hills Subdivision, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 47 | GF | 1188382.2 |  | 1188382.2 | 1179118.84 |  | 1179118.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 11) Improvement / Concrete Reblocking / Construction of Drainage Canal of Various Road, Marick Subdivision, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding | 2019-01-25 | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 118 | GF | 9452825.07 |  | 9452825.07 | 9428297.61 |  | 9428297.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 12) Improvement / Repair / Repainting of Ynares Multi-Purpose Covered Court, Office and Comfort Room at Brgy. San Isidro, Cainta, Rizal; a) Improvement/Repair of Ynares Multi-Purpose Covered Court, Office and Comfort Room at U.E. Village, Brgy. San Isidro, b) Impr/ Repair of Ynares Multi-Purpose Covered Court at Vista Verde Exec. Village, Phase 9, Brgy. San Isidro, c) Repainting/Improvement of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) and Repainting of Comfort Room at Greenpark Village, Zone 5, Brgy. San Isidro | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1297432.45 |  | 1297432.45 | 1288636.9 |  | 1288636.9 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 13) Upgrading of Concrete Roads at Villarica Subd., Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 80 | GF | 1793555.55 |  | 1793555.55 | 1783425.83 |  | 1783425.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 14) Upgrading/Concreting and Construction of Drainage Canal of Road Blk. 68, Sitio Panghulo, Floodway A, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 84 | GF | 953075.34 |  | 953075.34 | 945031.59 |  | 945031.59 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 15) Construction of Drainage Canal at Blk 36, Sitio Lumang Ilog, Floodway B, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1051124.39 |  | 1051124.39 | 1043012.47 |  | 1043012.47 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 16) Repair/Repainting of Ynares School Building and Repainting / Installation of Insulation of Ynares Multi-Purpose Covered Courts at Taytay & Cainta, Rizal; a) Repair/Repainting of 2-units, 2-storey, 4-rooms and 2-storey, 6-rooms Ynares School Building at Taytay Elementary School, Brgy. Dolores, Taytay, b) Repainting of Ynares Multi-Purpose Covered Court at Gruar Subd., Brgy. Domingo, Cainta, c) Installation of Insulation for Ynares Multi-Purpose Covered Court at Marick Subdivision, Brgy. Sto. Domingo, Cainta | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 64 | GF | 1818632.96 |  | 1818632.96 | 1807979.46 |  | 1807979.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 17) Improvement/Asphalt Overlaying & Concrete Reblocking (portion) of Baras-Pinugay Road, Sitio Tampoy, Sitio Santolan, Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 64 | GF | 3298758.65 |  | 3298758.65 |  |  | CANCELLED | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 18) Construction of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 136 | GF | 3367702.29 |  | 3367702.29 | 3355542.52 |  | 3355542.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 19) Construction of 2-storey, 10-rooms Ynares School Building at Cardona Senior High School, Cardona Government Center, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding | 2019-01-25 | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 258 | SEF | 16651922.18 |  | 16651922.18 | 16622124.07 |  | 16622124.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 20) Repair/ Repainting of 17x30 m Ynares Multi-Purpose Covred Court at Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 62 | GF | 921183.68 |  | 921183.68 | 913168.42 |  | 913168.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 21) Repainting/Repair of 2-storey Casimiro A. Ynares Sr. Memorial Hospital, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 114 | GF | 3134152.64 |  | 3134152.64 | 3121727.85 |  | 3121727.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 22) Construction of Stone Masonry for Slope Protection at Sitio Laan Creek 1, Brgy. Macabud, Rodriguez, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 118 | GF | 4013497.89 |  | 4013497.89 | 3999259.44 |  | 3999259.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 23) Construction of Stone Masonry for Slope Protection at Sitio Laan Creek 2, Brgy. Macabud, Rodriguez, Rizal | PEO |  | Public Bidding | 2019-01-25 | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 120 | GF | 5931616.23 |  | 5931616.23 | 5915459.74 |  | 5915459.74 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 24) Repair of Ynares Stage & Improvement of Ynares Multi-Purpose Covered Court at Brgy. Mascap & Brgy. Puray, Rodriguez, Rizal; a) Repair of Ynares Stage at Mascap National High School, Brgy. Mascap, b) Improvement of 17x30m Ynares Multi-Purpose Covered Court at Brgy. Puray | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1231129.37 |  | 1231129.37 | 1222048.36 |  | 1222048.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 25) Rehabilitation/Improvement of Various Roads at Brgy. Calumpang-Sto. Cristo, Teresa, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 50 | GF | 3433288.7 |  | 3433288.7 | 3421390.17 |  | 3421390.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 26) Construction of Drainage Canal at F. Gonzales St., Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding |  | 29 Jan - 4 Feb 2019 | 2019-02-06 |  | 2019-02-19 | 2019-02-25 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 72 | GF | 1462989.8 |  | 1462989.8 | 1453988.27 |  | 1453988.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-01-29 |  | 2019-01-29
| 1) Repair/Repainting of Ynares School Bldg., Ynares Multi-Purpose Covered Court, Stage, Basketball Goal & Installation of Electronic Scoreboard at Brgy. San Isidro, Brgy. San Luis & Brgy. Mayamot, Antipolo City; a) Repair/Repainting of 2-storey, 6-rooms Ynares School Bldg., 10x24m Ynares Multi-Purpose Covered Court & Stage at Bagong Nayon II National High School, Brgy. San Isidro, b) Repair of Basketball Goal of Ynares Multi-Purpose Covered Court at Peace Village Phase 2, Brgy. San Luis, c) Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Vermont Royale Executive Village, Brgy. Mayamot | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 72 | GF | 791495.98 |  | 791495.98 | 783693.38 |  | 783693.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 2) Construction of 1-storey Ynares Multi-Purpose Building at Rainbow Village, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 88 | GF | 1939282.72 |  | 1939282.72 | 1929453.63 |  | 1929453.63 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 3) Construction of 3-seater Comfort Room and Repainting of Covered Pathwalk at Janosa National High School, Brgy. Janosa, Binangonan, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 40 | GF | 718382.39 |  | 718382.39 | 710339.05 |  | 710339.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 4) Concrete Overlay / Concreting of Roads at Angono & Binangonan, Rizal; a) Concrete Overlay (portion) of Ipil St. Brgy. San Roque, Angono, b) Concreting of Road at F. Cervantes St., Brgy. Tatala, Binangonan | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 835975.08 |  | 835975.08 | 827541.67 |  | 827541.67 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 5) Improvement/Repair of Multi-Purpose Covered Court at West Embankment Anak Pawis II, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 46 | GF | 874763.91 |  | 874763.91 | 866627.44 |  | 866627.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 6) Construction of Comfort Room and Repair/Repainting of Ynares Multi-Purpose Building at Brgy. San Andres & Brgy. Sto. Domingo, Cainta, Rizal; a) Construction of 2-seater Comfort Room at Area 8, Greenwoods Executive Village, Brgy. San Andres, b) Repair/Repainting of 2-storey Ynares Multi-Purpose Building at Marick Subdivision, Brgy. Sto. Domingo | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 513504.31 |  | 513504.31 | 507478.61 |  | 507478.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 7) Improvement/Concreting / Construction of Drainage Canal of Roads at Cresdaville Subd., Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 160 | GF | 5181150.16 |  | 5181150.16 | 5165968.75 |  | 5165968.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 8) Concreting of Blk 18, Ynares Ave. Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1199962.57 |  | 1199962.57 | 1190927.78 |  | 1190927.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 9) Concreting of Road at Sitio Rumagit to PPC Road, Brgy. Concepcion, Baras, Rizal | PEO |  | Public Bidding | 2019-01-28 | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 140 | GF | 10344911.31 |  | 10344911.31 | 10320526.16 |  | 10320526.16 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 10) Construction of Drainage Canal (portion) at San Juan St., Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1407912.39 |  | 1407912.39 | 1398881.87 |  | 1398881.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 11) Construction of Drainage Canal at F. Nido St., Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 80 | GF | 1751329.73 |  | 1751329.73 | 1741329.38 |  | 1741329.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 12) Improvement/Construction of Stone Masonry Slope Protection at Purok 5 and 6, Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 100 | GF | 2872469 |  | 2872469 | 2862579.07 |  | 2862579.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 13) Construction of Fence at Mariano C. San Juan Elementary School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 511138.07 |  | 511138.07 | 502084.06 |  | 502084.06 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 14) Construction of 7x20m Ynares Multi-Purpose Covered Court at Ticulio Elementary School, Brgy. Ticulio, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 72 | GF | 1851323.8 |  | 1851323.8 | 1841221.28 |  | 1841221.28 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 15) Construction of 1-storey, 2-rooms Ynares School Building at Boor Barrio School, Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 104 | GF | 2807420.92 |  | 2807420.92 | 2796362.13 |  | 2796362.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 16) Construction of Ynares Stage with Basement at Sitio Itaas, Brgy. Bombongan, Morong, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 80 | GF | 1579969.28 |  | 1579969.28 | 1567933.48 |  | 1567933.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 17) Asphalt Overlaying/ Concrete Reblocking of G. Dikit St., Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2019-01-28 | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 76 | GF | 5893995.06 |  | 5893995.06 | 5877778.45 |  | 5877778.45 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 18) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 64 | GF | 1975606.454 |  | 1975606.454 | 1965644.81 |  | 1965644.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 19) Construction of Concrete Bleacher and Fence of Ynares Multi-Purpose Covered Court at Southville 8C Phase 1K, Kasiglahan Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 70 | GF | 1088282.56 |  | 1088282.56 | 1080248.88 |  | 1080248.88 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 20) Improvement of Ynares Multi-Purpose Covered Court and Construction of 2-seater Comfort Room at Greenrose 1, Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 68 | GF | 1531982.48 |  | 1531982.48 | 1522421.2 |  | 1522421.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 21) Improvement/Repair of Ynares Multi-Purpose Covered Court at King David Subd., Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 61 | GF | 1732049.93 |  | 1732049.93 | 1722056.13 |  | 1722056.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 22) Construction of Stone Masonry for Slope Protection at Maislap Creek 2, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1446709.09 |  | 1446709.09 | 1438523.04 |  | 1438523.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 23) Construction of Stone Masonry for Slope Protection at Mango River (Hinayon Portion), Brgy. Manggahan , Rodriguez, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 112 | GF | 4496107.97 |  | 4496107.97 | 4481502.78 |  | 4481502.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 24) Construction of Covered Pathwalk at Cuyambay Elementary School, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 52 | GF | 669946.79 |  | 669946.79 | 661752.98 |  | 661752.98 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 25) Construction of 2-storey Ynares Multi-Purpose Building at National Commission on Indigenous People (NCIP), Brgy. Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 120 | GF | 2595885.41 |  | 2595885.41 | 2584763.96 |  | 2584763.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 26) Improvement of Ynares Multi-Purpose Covered Court and Construction of Concrete Bleacher at Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1831745.98 |  | 1831745.98 | 1821548.03 |  | 1821548.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 27) Repair of 2-storey Bahay Pag-Asa Building at Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 60 | GF | 1320542.05 |  | 1320542.05 | 1311158.49 |  | 1311158.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 28) Installation of Canopy at 17x30m Ynares Multi-Purpose Covered Court, Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 30 | GF | 796751.92 |  | 796751.92 | 788764.4 |  | 788764.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 29) Repair / Improvement / Repainting of Ynares Multi-Purpose Buildings and Construction of Fence at Binangonan & Angono, Rizal; a) Repair / Improvement of 1-storey Ynares Multi-Purpose Building (Senior Citizen Office), Brgy. San Carlos, Binangonan, b) Repainting of 3-storey Ynares Multi-Purpose Building (Barangay Hall) at Brgy. Mahabang Parang, Angono, c) Construction of Fence at Purok 3, Brgy. Malakaban, Binangonan 392,817.43 | PEO |  | Public Bidding |  | 1 - 7 Feb 2019 | 2019-02-08 |  | 2019-02-22 | 2019-02-26 | 2019-03-05 |  | 2019-03-08 | 2019-03-18 | 2019-03-21 | 50 | GF | 1104199.7 |  | 1104199.7 | 1094779.42 |  | 1094779.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-01 |  | 2019-02-01
| 1) Construction of 10.75(ave.) x 21m Ynares Multi-Purpose Covered Court at Singcalan, Brgy. San Roque, Antipolo City | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 124 | GF | 3505537.11 |  | 3505537.11 | 3493249.94 |  | 3493249.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 2) Construction of 4-storey Multi-Purpose Bldg. (Administrative Bldg.) at URS-Cainta, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2019-02-04 | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 272 | GF | 14190024.35 |  | 14190024.35 | 14163228.67 |  | 14163228.67 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 3) Improvement of Ynares Multi-Purpose Bldg. / Ynares Multi-Purpose Covered Court & Construction of CHB Fence at Brgy. Sta. Ana, Brgy. San Isidro & Brgy. San Juan, Taytay, Rizal; a) Improvement of Ynares Multi-Purpose Bldg. (Senior Citizens's Office) at Exodus Floodway, Brgy. Sta. Ana, b) Improvement / Enclosure of 10x30m Ynares Multi-Purpose Covered Court at San Isidro Elem. School, c) Construction of CHB Fence (portion) at Bagong Pag-Asa Elementary School (main), Brgy. San Juan | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 60 | GF | 1260791.37 |  | 1260791.37 | 1251760.15 |  | 1251760.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 4) Widening of Road and Construction of Drainage Canal at Sitio Mambog, Brgy. San Jose & Brgy. Evangelista, Baras, Rizal; a) Widening of Road and Construction of Drainage Canal at Sitio Mambog, Brgy. San Jose, b) Construction of Canal at Purok 2, Sitio Iloco, Brgy. Evangelista | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 76 | GF | 2367285.75 |  | 2367285.75 | 2357287.1 |  | 2357287.1 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 5) Repair and Improvement of 2-storey Ynares Multi-Purpose Building at Magsaysay Blvd., Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 52 | GF | 1147913.91 |  | 1147913.91 | 1138748.42 |  | 1138748.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 6) Construction of GAD Center, Baras, Rizal | PEO |  | Public Bidding | 2019-02-04 | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 212 | GF | 10416409.21 |  | 10416409.21 | 10393213.69 |  | 10393213.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 7) Construction of DRRM Center, Baras, Rizal | PEO |  | Public Bidding | 2019-02-04 | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 250 | PDRRMF | 13144053.94 |  | 13144053.94 | 13119077.96 |  | 13119077.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 8) Construction of Drainage Canal along Sitio Pawpawan Road, Brgy. San Salvador, Baras, Rizal | PEO |  | Public Bidding | 2019-02-04 | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 120 | GF | 6741457.75 |  | 6741457.75 | 6725440.3 |  | 6725440.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 9) Construction of GAD Building at Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 178 | GF | 4872834.81 |  | 4872834.81 | 4856747.18 |  | 4856747.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 10) Construction of Drainage Canal at Blk 40, Sitio Lumang Ilog, Floodway B, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 82 | GF | 2027692.75 |  | 2027692.75 | 2018419.86 |  | 2018419.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 11) Repair of Ynares School Buildings & Concreting of School Playground at Brgy. Bombongan & Brgy. San Guillermo, Morong, Rizal; a) Repair of Ynares School Buildings at Bombongan Elementary School, Brgy. Bombongan, b) Concreting of School Playground at San Guillermo Elementary School, Brgy. San Guillermo | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 50 | GF | 1290105.36 |  | 1290105.36 | 1281197.15 |  | 1281197.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 12) Repair of Ynares Multi-Purpose Covered Court at Brgy. CCL, Morong, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 64 | GF | 1407901.32 |  | 1407901.32 | 1398877.85 |  | 1398877.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 13) Construction of 17x28m Ynares Multi-Purpose Covered Court at Sitio Agas-As, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 128 | GF | 4038115.36 |  | 4038115.36 | 4025049.97 |  | 4025049.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 14) Construction of Concrete Bleacher and Improvement / Installation of Commemorative Stone at Brgy. Bagumbayan & Brgy. Niogan, Pililla, Rizal; a) Construction of Concrete Bleacher of Ynares Multi-Purpose Covered Court at Brgy. Bagumbayan, b) Improvement/Installation of Commemorative Stone at Niogan Elem. School, Brgy. Niogan | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 60 | GF | 966288.89 |  | 966288.89 | 958295.05 |  | 958295.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 15) Construction of Concrete Bleacher of Ynares Multi-Purpose Covered Court at Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 60 | GF | 871982.84 |  | 871982.84 | 863374.31 |  | 863374.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 16) Construction of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Greenbreeze Subd., Phase 2A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 128 | GF | 3968161.38 |  | 3968161.38 | 3956090.02 |  | 3956090.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 17) Improvement/Repair of Ynares Multi-Purpose Covered Court & Stage at Kasiglahan Village I, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 60 | GF | 1297022.73 |  | 1297022.73 | 1288408.04 |  | 1288408.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 18) Construction of Stone Masonry & Single Barrel Box Culvert, Demountable Stage & Improvement of Laboratory Facility at Rodriguez & Jalajala, Rizal; a) Construction of Stone Masonry and Single Barrel Box Culvert at Homes of Hope Compound, Brgy. Burgos, Rodriguez, b) Construction of Demountable Stage at San Isidro National High School, Brgy. San Isidro, Rodriguez, c) Improvement of Laboratory Facility at Ynares Municipal Hospital, Jalajala | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 60 | GF | 605526.86 |  | 605526.86 | 597673.69 |  | 597673.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 19) Improvement/Installation/Rehabilitation of Electrical Lighting System and Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Brgy. Pintong Bukawe, Brgy. Dulong Bayan 1 & Brgy. Ampid I, San Mateo, Rizal; a) Improvement of 17x30m Ynares Multi-Purpose Covered Court at Brgy. Pintong Bukawe, b) Installation of Electrical Lighting System of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at Dulong Bayan Elementary School, Brgy. Dulong Bayan | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 52 | GF | 1170914.22 |  | 1170914.22 | 1161562.68 |  | 1161562.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 20) Construction of 2-storey Multi-Purpose Bldg., Perimeter Fence & Repair/Repainting of Ynares Multi-Purpose Covered Court at Sunnyville 5 Subd., Brgy. Ampid I, San Mateo, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 120 | GF | 2646797.09 |  | 2646797.09 | 2636368.29 |  | 2636368.29 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 21) Construction of 17x30m Ynares Multi-Purpose Covered Court at Sitio Abuyod, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 145 | GF | 4241735.11 |  | 4241735.11 | 4227740.65 |  | 4227740.65 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 22) Construction of 17x30m Ynares Multi-Purpose Covered Court at Carissa Homes East II, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 131 | GF | 3923656.64 |  | 3923656.64 | 3911630.83 |  | 3911630.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
| 23) Improvement of Ynares Multi-Purpose Covered Court at Quiterio San Jose Elementary School, Brgy. May-Iba, Teresa, Rizal | PEO |  | Public Bidding |  | 7 - 13 Feb 2019 | 2019-02-14 |  | 2019-02-26 | 2019-03-01 | 2019-03-08 |  | 2019-03-13 | 2019-03-22 | 2019-03-28 | 40 | GF | 772801.29 |  | 772801.29 | 764464.18 |  | 764464.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-02-07 |  | 2019-02-07
Total Alloted Budget of Procurement Activities | [17 empty] | 902065254.984
Total Contract Price of Procurement Activities Conducted | [17 empty] | 837832303.02
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 64232951.964
ON-GOING PROCUREMENT ACTIVITIES
Total Alloted Budget of On-going Procurement Activities | [21 empty] | 0
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | MA. TERESA E. LASQUETY | [12 empty] | Engr. LUISITO G. MUNSOD | [8 empty] | Dr. REYNALDO H. SAN JUAN, Jr., M.D.
|  | Head - BAC Secretariat | [12 empty] | BAC Chairperson | [8 empty] | Acting Governor

## PMR 2nd sem 2019
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of 31 December 2019
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
| 1) Rehabilitation/ Asphalt Overlaying of Road Lot 4 at Peace Village 2, Brgy. San Luis, Antipolo City | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 30 C.D. | GF | 2047972.14 |  | 2047972.14 | 2026738.32 |  | 2026738.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 2) Asphalt Overlaying of Road Lot 3 & 9 at Peace Village Phase 3, Brgy. San Luis, Antipolo City; a) Asphalt Overlaying of Road Lot 3 at Peace Village Phase 3, Brgy. San Luis, b) Asphalt Overlaying of Road Lot 9 at Peace Village Phase 3, Brgy. San Luis | PEO |  | Public Bidding | 2019-07-17 | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 40 | GF | 6550452.54 |  | 6550452.54 | 6479154.01 |  | 6479154.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 3) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the City of Antipolo | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 64 | GF | 1601687.04 |  | 1601687.04 | 1585456.12 |  | 1585456.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 4) Extension of Existing 2-Storey Ynares Multi-Pupose Building (Brgy. Hall), Brgy. San Roque, Angono, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 108 | GF | 2409024.57 |  | 2409024.57 | 2383794.68 |  | 2383794.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 5) Repair/Repainting of School Buildings at Mahabang Parang National High School, Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 116 | GF | 2906286.81 |  | 2906286.81 | 2874335.31 |  | 2874335.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 6) Construction of Comfort Room & Repair/Improvement of Ynares Multi-Purpose Building at Brgy. Darangan & Brgy. Mambog, Binangonan, Rizal; a) Construction of Comfort Room at Ynares Multi-Purpose Covered Court, Brgy. Darangan, b) Repair/Improvement of 2-Storey Ynares Multi-Purpose Building at Brgy. Mambog | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 64 | GF | 1384907.6 |  | 1384907.6 | 1370746.61 |  | 1370746.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 7) Rehabilitation/Installation of Water Distribution Lines at Brgy. Bombong & Brgy. Kalinawan, Binangonan, Rizal; a) Rehabilitation/Installation of Water Distribution Lines at Brgy. Bombong, b) Rehabilitation/Installation of Water Distribution Lines at Brgy. Kalinawan | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 48 | GF | 1484760.67 |  | 1484760.67 | 1469736.84 |  | 1469736.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 8) Repair / Improvement / Repainting of Multi-Purpose Building at Brgy. Kasile, Brgy. Bombong & Brgy. Janosa, Binangonan, Rizal; a) Repair / Improvement of 1-Storey Multi-Purpose Building (Day Care Center) at Brgy. Kasile, b) Repair / Improvement of 2-Units 2-Storey Multi-Purpose Building at Brgy. Bombong, c) Improvement / Repainting of 1-Storey Ynares Multi-Purpose Building (Day Care Center) at Brgy. Janosa | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 60 | GF | 1450843.93 |  | 1450843.93 | 1435277.91 |  | 1435277.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 9) Construction of Comfort Room & Installation of Electronic Scoreboard at Brgy. San Roque & Brgy. San Isidro, Cainta, Rizal; a) Construction of Comfort Room at Ynares Multi-Purpose Covered Court, Brgy. San Roque, b) Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Park Place Executive Village, Brgy. San Isidro | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 64 | GF | 936182.79 |  | 936182.79 | 925859.58 |  | 925859.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 10) Improvement of Ynares Multi-Purpose Covered Court & Ynares Multi-Purpose Building at Brgy. San Isidro, Cainta, Rizal; a) Improvement of Ynares Multi-Purpose Covered Court at Vista Verde Exec. Village, Phase 5, Brgy. San Isidro, b) Improvemennt of 2-Storey Ynares Multi-Purpose Building at Zone 6 Greenpark Village, Brgy. San Isidro | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 80 | GF | 1668613.82 |  | 1668613.82 | 1650677.94 |  | 1650677.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 11) Improvement and Repainting of Ynares Multi-Purpose Covered Court, Repair of Ynares School Building at Brgy. San Andres, Cainta, Rizal; a) Improvement and Repainting of Ynares Multi-Purpose Covered Court at Mercedes Exec. Village, Brgy. San Andres, b) Repair of 2-Storey 6-Rooms Ynares School Building at Francisco P. Felix Elem. School Unit-I, Brgy. San Andres | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 60 | GF | 2042689.34 |  | 2042689.34 | 2020731.66 |  | 2020731.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 12) Construction of Comfort Room at Ynares Multi-Purpose Covered Court, Barangay Hall Compound, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 64 | GF | 806836.71 |  | 806836.71 | 796496.5 |  | 796496.5 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 13) Construction of Comfort Rooms & Improvement of Ynares Multi-Purpose Building (Brgy.Hall) at Cardona, Rizal; a) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the Municipality of Cardona, b) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy.Hall) at Brgy. San Roque | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 90 | GF | 2793560.97 |  | 2793560.97 | 2762283.81 |  | 2762283.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 14) Extension & Improvement of Ynares Multi-Purpose Building & Ynares Multi-Purpose Covered Court at Brgy. Second District & Brgy. Palaypalay, Jalajala, Rizal; a) Extension & Improvement of 1-Storey Ynares Multi-Purpose Building (Day Care Center), Brgy. Second District, b) Improvement of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Palaypalay | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 76 | GF | 1370145.08 |  | 1370145.08 | 1355741.86 |  | 1355741.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 15) Repair of Ynares School Building & Repair/Improvement of Ynares Multi-Purpose Buildings at Morong & Baras, Rizal; a) Repair of 2-Storey, 6-Rooms Ynares School Building at Roman Tantiongco Mem. School, Brgy. San Juan, Morong, b) Repair/Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy.Hall), Brgy. Maybangcal, Morong, c) Repair/Improvement of 2-Storey Ynares Multi-Purpose Building, Brgy. Mabini, Baras | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 60 | SEF | 1391463.68 |  | 1391463.68 | 1377428.21 |  | 1377428.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 16) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the Municipality of Morong, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 90 | GF | 2450040.96 |  | 2450040.96 | 2425413.53 |  | 2425413.53 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 17) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court & Improvement of Rizal Prov'l. Hospital System - Pililla (RPHS Pililla) Annex, Pililla, Rizal; a) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the Municipality of Pililla, b) Improvement of Rizal Prov'l. Hospital System - Pililla (RPHS Pililla) Annex, Brgy. Takungan | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 64 | GF | 2119831.36 |  | 2119831.36 | 2096144.56 |  | 2096144.56 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 18) Repair/Improvement of Ynares Multi-Purpose Building and Ynares School Building at Brgy. Takungan & Brgy. Halayhayin, Pililla, Rizal; a) Repair/Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy.Hall), Brgy. Takungan, b) Repair of 2-Storey 4-Rooms Ynares School Building at Bugarin Elem.School, Sitio Bugarin, Brgy. Halayhayin | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 50 | GF | 787440.9 |  | 787440.9 | 781534.67 |  | 781534.67 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 19) Construction of Playground Facilities, Fence and Concrete Bleacher, Improvement/Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Halayhayin, Brgy. Bagumbayan & Brgy. Quisao, Pililla, Rizal; a) Construction of Playground Facilities, Fence and Concrete Bleacher at Bugarin Elem. School, Brgy. Halayhayin, b) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Bagumbayan, c) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Sitio Libis, Brgy. Quisao | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 60 | GF | 1699006.17 |  | 1699006.17 | 1681952.94 |  | 1681952.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 20) Construction of Additional Second Floor of Existing 1-Storey Multi-Purpose Building at Dona Pepeng Subd., Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 107 | GF | 2483103.85 |  | 2483103.85 | 2457799.61 |  | 2457799.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 21) Construction of 2-Storey Ynares Multi-Purpose Building at East Bellevue Residences Phase 1A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 137 | GF | 3152939.6 |  | 3152939.6 | 3120624.14 |  | 3120624.14 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 22) Construction of 2-Storey Ynares Multi-Purpose Building at Montalban Heights, LGU Phase 1, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 71 | GF | 2726956.45 |  | 2726956.45 | 2698683.85 |  | 2698683.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 23) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the Municipality of Rodriguez, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 128 | GF | 4824575.93 |  | 4824575.93 | 4774985.82 |  | 4774985.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 24) Repair of Ynares Multi-Purpose Covered Court and Ynares Stage at Metro Manila Hills, Phase 2B, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 80 | GF | 2050610.45 |  | 2050610.45 | 2032425.45 |  | 2032425.45 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 25) Installation of Solar Streetlights at Sitio Balagbag, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 54 | GF | 1348239.74 |  | 1348239.74 | 1335304.89 |  | 1335304.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 26) Repair/Improvement/Rehabilitation of Electrical Lighting System and Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court and Fence at Brgy. Banaba & Brgy. Ampid, San Mateo, Rizal; a) Repair / Improvement of Ynares Multi-Purpose Covered Court and Fence at Doňa Pepeng Subd., Brgy. Banaba; b) Rehabilitation of Electrical Lighting System and Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Duraville Homes Phase II, Brgy. Ampid | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 60 | GF | 1383155.84 |  | 1383155.84 | 1368605.39 |  | 1368605.39 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 27) Construction of Comfort Rooms & Repair of Ynares Multi-Purpose Covered Court at San Mateo, Rizal; a) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the Municipality of San Mateo, b) Repair of Ynares Multi-Purpose Covered Court at Graceland Subd., Brgy. Ampid II | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 90 | GF | 3250695.48 |  | 3250695.48 | 3217868.84 |  | 3217868.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 28) Repair / Repainting of Ynares School Building / Improvement of Ynares Multi-Purpose Covered Court & Construction of School Gate at Brgy. Plaza Aldea, Tanay, Rizal; a) Repair / Repainting of Ynares School Building at Tanay East National High School, Brgy. Plaza Aldea, b) Improvement of Ynares Multi-Purpose Covered Court at Tanay East National High School, Brgy. Plaza Aldea, c) Construction of School Gate at Don Domingo Capistrano Elem.School, Brgy. Plaza Aldea | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 60 | SEF | 1926308.52 |  | 1926308.52 | 1903600.88 |  | 1903600.88 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 29) Construction of Comfort Rooms at Various Ynares Multi-Purpose Covered Court in the Municipality of Teresa, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 128 | GF | 3208111.51 |  | 3208111.51 | 3173929.74 |  | 3173929.74 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 30) Repair/Repainting of 1-storey, 5-rooms Ynares School Building at Pantay National High School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 18-24 July 2019 | 2019-07-25 |  | 2019-08-07 | 2019-08-12 | 2019-08-19 |  | 2019-08-27 | 2019-09-02 | 2019-09-10 | 42 | GF | 1421595.5 |  | 1421595.5 | 1407135.05 |  | 1407135.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-07-18 |  | 2019-07-18
| 1) Concrete Reblocking of Jordan Street, Victoriaville Subd, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | GF | 1015326.62 |  | 1015326.62 | 1005309.19 |  | 1005309.19 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 2) Construction of 13x24m Ynares Multi-Purpose Covered Court at Victoriaville Subd. Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 100 | GF | 2997656.85 |  | 2997656.85 | 2967919.3 |  | 2967919.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 3) Construction of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Carolina Village, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 128 | GF | 4000680.68 |  | 4000680.68 | 3961211.08 |  | 3961211.08 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 4) Concrete Reblocking and Asphalt Overlaying of Rome Street & Babylon Street, Victoriaville Subd, Brgy. Sta. Cruz, Antipolo City; a) Concrete Reblocking and Asphalt Overlaying of Rome Street, Victoriaville Subd, Brgy. Sta. Cruz; b) Concrete Reblocking and Asphalt Overlaying of Babylon Street, Victoriaville Subd, Brgy. Sta. Cruz | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 50 | GF | 3237397.85 |  | 3237397.85 | 3205438.82 |  | 3205438.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 5) Construction of 2-Storey Ynares Multi-Purpose Building at Antipolo Hills Subd. Brgy. San Luis, Antipolo City | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 120 | GF | 3074115.91 |  | 3074115.91 | 3043166.98 |  | 3043166.98 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 6) Repair/Improvement of 3-Units Multi-Purpose Covered Court at Sitio Upper Sto.Nino, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | GF | 1099721.91 |  | 1099721.91 | 1088762.69 |  | 1088762.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 7) Improvement/Construction of Drainage Canal at C. Bolado Avenue (portion), Brgy. Tatala, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 80 | GF | 4205423.8 |  | 4205423.8 | 4163541.75 |  | 4163541.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 8) Repair / Repainting of 2-storey-6-rooms Deped School Building & 2-storey-4-rooms Ynares School Building at Dr. Vivencio B. Villamayor National High School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | SEF | 750145.98 |  | 750145.98 | 741968.18 |  | 741968.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 9) Asphalt Overlaying of Dugay St., Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 40 | GF | 4090641.44 |  | 4090641.44 | 4050177.3 |  | 4050177.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 10) Asphalt Overlaying of Aralar St. & Paralejas St. (portion), Brgy. Pilapila, Binangonan, Rizal; a) Asphalt Overlaying of Aralar St., Brgy. Pilapila, b) Asphalt Overlaying of Paralejas St. (portion), Brgy. Pilapila | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 40 | GF | 4846687.66 |  | 4846687.66 | 4798695.31 |  | 4798695.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 11) Improvement/ Concreting of Roads at Sitio Mata, Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 85 | GF | 1769507.61 |  | 1769507.61 | 1752244.97 |  | 1752244.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 12)Construction of 2-Storey Ynares Multi-Purpose Building at Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 126 | GF | 2255503.23 |  | 2255503.23 | 2232641.31 |  | 2232641.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 13)Repair / Repainting of DENR-PENRO Building and Replacement of Concrete Pavement (Parking) at Cabrera Road, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 86 | GF | 1495247.21 |  | 1495247.21 | 1480144.82 |  | 1480144.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 14)Construction of Fence, Extension of Conc.Pavement, Repair & Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Courts at Brgy. San Juan, Cainta, Rizal; a) Construction of Fence & Extension of Conc.Pavement of Ynares Multi-Purpose Covered Court, Phase 5 at Greenland Exec.Village, Brgy. San Juan, b) Repair of Ynares Multi-Purpose Covered Court at Palmera Heights Subd., Phase III, Brgy. San Juan, c) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Cainta Greenland Subd., Brgy. San Juan | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | GF | 1345759.13 |  | 1345759.13 | 1332469.92 |  | 1332469.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 15) Improvement/Repair/Rehabilitation of Electrical Lighting System & Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Courts at Brgy. San Isidro, Taytay, Rizal; a) Improvement / Repair Ynares Multi-Purpose Covered Court at St. Anthony Subd., Brgy. San Isidro, b) Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Simona Subdivision, Brgy. San Isidro, c) Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Simona Subdivision, Brgy. San Isidro | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 40 | GF | 1003303.44 |  | 1003303.44 | 993153.15 |  | 993153.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 16)Construction of Drainage Canal (Portion) at Purok 5, Sitio May Anii, Brgy. Evangelista, Baras, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | GF | 1264939.5 |  | 1264939.5 | 1251671.08 |  | 1251671.08 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 17) Improvement/Repair of 2-Storey Ynares Multi-Purpose Building (Brgy.Hall), Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | GF | 963775.55 |  | 963775.55 | 953621.89 |  | 953621.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 18)Improvement / Rehabilitation of Electrical Lighting System, Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Courts & Construction of 2 seater Comfort Room at Brgy. San Juan, Brgy. San Jose & Brgy. San Guillermo, Morong, Rizal; a) Improvement/ Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. San Juan, b) Installation of Electronic Scoreboard at Ynares Multi-Purpose Covered Court, Sitio Balante, Brgy. San Jose, c) Construction of 2 seater Comfort Room at San Guillermo Elem. School, Brgy. San Guillermo | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 40 | GF | 854139.2 |  | 854139.2 | 0 |  | 0 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 19)Improvement//Repainting/Repair of Ynares Multi-Purpose Covered Court & Ynares Stage at Talaga Elem. School, Brgy. Maybangcal, Morong, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 52 | GF | 992373.16 |  | 992373.16 | 982322.1 |  | 982322.1 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 20)Rehabilitation / Concrete Reblocking of Angel Paz St., Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 60 | GF | 971327.67 |  | 971327.67 | 961327.78 |  | 961327.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 21) Repair/Repainting of Ynares Multi-Purpose Building, Ynares School Building & Construction of Hand Washing Facility at Brgy. San Jose & Brgy. Geronimo, Rodriguez, Rizal; a) Repair/Repainting of 1-Storey Ynares Multi-Purpose Building at San Jose Oval, Brgy. San Jose, b) Repair of 2 storey 6 rooms Ynares School Building at Amityville Elem. School, Brgy. San Jose, c) Construction of Hand Washing Facility at Geronimo Elem. School, Brgy. Geronimo | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 46 | GF | 936729.1 |  | 936729.1 | 927337.89 |  | 927337.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 22) Construction of Ynares Stage at San Jose-Litex Senior High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 70 | GF | 917105.68 |  | 917105.68 | 907828.44 |  | 907828.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 23)Construction of 2-Storey Ynares Multi-Purpose Building at Congressville Subd., Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 137 | GF | 3159704.75 |  | 3159704.75 | 3127153.75 |  | 3127153.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 24)Const.of 10x30m Ynares Multi-Purpose Covered Court (Rafter Type) at San Jose-Litex Senior High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 100 | GF | 2892808.61 |  | 2892808.61 | 0 |  | 0 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 25)Construction of 10x20m Ynares Multi-Purpose Covered Court (Rafter Type) at Kasiglahan Village Senior High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 100 | GF | 2310275.19 |  | 2310275.19 | 2287009.17 |  | 2287009.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 26)Construction of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at Phase 1C Kasiglahan Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 110 | GF | 3225068.27 |  | 3225068.27 | 3192055.77 |  | 3192055.77 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 27) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Courts at Brgy. San Isidro, Rodriguez, Rizal; a) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Terra Verde Phase 3 & 3a Eastwood Residence, Brgy. San Isidro, b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Bautista Creekside Ph 1, Brgy. San Isidro, c) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Eastwood Residences Subdivision Phase IV, Brgy. San Isidro | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 40 | GF | 1021961.91 |  | 1021961.91 | 1011853.15 |  | 1011853.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 28) Construction of Children's Playground Facilities & Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Tanay, Rizal; a) Construction of Children's Playground Facilities at Patricio Jarin Mem. Elem. School, Brgy. San Isidro, b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Isidro | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 48 | GF | 1221916.92 |  | 1221916.92 | 1207917.01 |  | 1207917.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 29) Construction of 1-Storey Ynares Multi-Purpose Building at Balikatan Village, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 86 | GF | 1414174.48 |  | 1414174.48 | 1399155.04 |  | 1399155.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 30)Construction of Ynares Stage at Pantay National High School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 2 - 8 Aug 2019 | 2019-08-08 |  | 2019-08-20 | 2019-08-27 | 2019-09-02 |  | 2019-09-06 | 2019-09-13 | 2019-09-20 | 86 | GF | 969456.43 |  | 969456.43 | 959439.67 |  | 959439.67 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-02 |  | 2019-08-02
| 1) Asphalt Overlaying of Bethlehem Street, Nile Street & Eden Street, Victoriaville Subd, Brgy. Sta. Cruz, Antipolo City; a) Asphalt Overlaying of Bethlehem Street, Victoriaville Subd, Brgy. Sta. Cruz, b) Asphalt Overlaying of Nile Street, Victoriaville Subd, Brgy. Sta. Cruz, c) Asphalt Overlaying of Eden Street, Victoriaville Subd, Brgy. Sta. Cruz | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 4521240.89 |  | 4521240.89 | 4466123.26 |  | 4466123.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 2) Asphalt Overlaying of Jerusalem Street, Samaria Street, Arimathea Street, & Corith Street, Victoriaville Subd, Brgy. Sta. Cruz, Antipolo City; a) Asphalt Overlaying of Jerusalem Street, Victoriaville Subd, Brgy. Sta. Cruz, b) Asphalt Overlaying of Samaria Street, Victoriaville Subd, Brgy. Sta. Cruz, c) Asphalt Overlaying of Arimathea Street, Victoriaville Subd, Brgy. Sta. Cruz, d) Asphalt Overlaying of Corith Street, Victoriaville Subd, Brgy. Sta. Cruz | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 4526690.74 |  | 4526690.74 | 4470835.45 |  | 4470835.45 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 3) Asphalt Overlaying of Jericho Street, Bethel Street & Bethsaida Street, Victoriaville Subd, Brgy. Sta. Cruz, Antipolo City; a) Asphalt Overlaying of Jericho Street, Victoriaville Subd, Brgy. Sta. Cruz, b) Asphalt Overlaying of Bethel Street, Victoriaville Subd, Brgy. Sta. Cruz, c) Asphalt Overlaying of Bethsaida Street, Victoriaville Subd, Brgy. Sta. Cruz | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 4650244.93 |  | 4650244.93 | 4593032.64 |  | 4593032.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 4) Improvement of Multi-Purpose Covered Court, Construction of Demountable Stage & Repainting/Repair of Welcome Arc at Brgy. Dalig & Brgy. Dela Paz, Antipolo City; a) Improvement of Gatlabayan Multi-Purpose Covered Court at Lores Country Executive Homes, Brgy. Dalig, b) Construction of Demountable Stage at Sitio Kabute, Brgy. Dela Paz, c) Repainting/Repair of Welcome Arc at Sitio Dalig II, Brgy. Dalig | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 64 | GF | 813667.7 |  | 813667.7 | 805328.36 |  | 805328.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 5) Repair/Repainting of Multi-Purpose Building & Renovation of Multi-Purpose Hall at Brgy. Dela Paz, Antipolo City; a) Repair/Repainting of 2-Storey Multi-Purpose Building at Antonio Zuzuarregui Subd. Phase 4-B, Purok Silangan, Brgy. Dela Paz, b) Renovation of Multi-Purpose Hall at Purok V, Lower Lucban, Brgy. Dela Paz | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 826586.23 |  | 826586.23 | 818549.95 |  | 818549.95 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 6) Concreting of Various Alleys with Stair at Sitio Lupangge, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 100 | GF | 1026868.76 |  | 1026868.76 | 1016579.11 |  | 1016579.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 7) Concrete Reblocking of Athens Street, Victoriaville Subd, Brgy. Sta. Cruz, Antipolo City | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 1453095.77 |  | 1453095.77 | 1432517.94 |  | 1432517.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 8) Repair/Improvement of Ynares Multi-Purpose Building at Brgy. Sta. Cruz & Construction of Roof/Shed for Chiller and Chilled Water System & Repair of Roofing, Ceiling (Portion) and Flooring of Fitness Room at Ynares Center, Brgy. San Roque, Antipolo City; a) Repair/Improvement of 2-Storey w/ Roof Deck Ynares Multi-Purpose Building at Upper Sto.Niño, Brgy. Sta. Cruz, b) Construction of Roof/Shed for Chiller 1 & 2 and Chilled Water System at Ynares Center, Brgy. San Roque, c) Repair of Roofing,Ceiling (Portion) and Flooring of Fitness Room at Ynares Center , Brgy. San Roque | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 1041746.89 |  | 1041746.89 | 1031620.89 |  | 1031620.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 9) Repair/Improvement of Ynares Multi-Purpose Building, Ynares & Gatlabayan Multi-Purpose Covered Courts & Construction of Covered Pathwalk at Brgy. San Luis, Brgy. Mayamot & Brgy. Cupang, Antipolo City; a) Repair/Improvement of Ynares Multi-Purpose Building at Peace Village Phase 2, Brgy. San Luis, b) Improvement of Ynares Multi-Purpose Covered Court & Gatlabayan Multi-Purpose Covered Court at Town & Country Exec. Village, Brgy. Mayamot, c) Construction of Covered Pathwalk at Taguete Elementary School, Brgy. Cupang | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 810447.46 |  | 810447.46 | 802363.09 |  | 802363.09 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 10)Improvement of Ynares Multi-Purpose Covered Court at Angono Elem. School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 44 | GF | 891043.17 |  | 891043.17 | 882087.26 |  | 882087.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 11)Improvement of Ynares Multi-Purpose Covered Court at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 52 | GF | 762809.57 |  | 762809.57 | 754511.81 |  | 754511.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 12)Construction of Volleyball Court, Movable Bleacher, Fence & Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Mahabang Parang & Brgy. San Vicente, Angono, Rizal; a) Construction of 15x24m Volleyball Court, Movable Bleacher & Fence at Grand Valley Subd. Phase 1, Brgy. Mahabang Parang, b) Repair/Repainting of Ynares Multi-Purpose Covered Court, Brgy. San Vicente | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 86 | GF | 1147694.38 |  | 1147694.38 | 1136578.78 |  | 1136578.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 13)Repair / Improvement of Duavit Multi-Purpose Covered Court and Stage at Sitio Sto. Niño, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 64 | GF | 1514260.45 |  | 1514260.45 | 1499324.99 |  | 1499324.99 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 14)Repair/Improvement of Ynares School Buildings, Stage & Ynares Multi-Purpose Covered Court at Brgy. Tabon & Brgy. Bangad, Binangonan, Rizal; a) Repair/Improvement of Ynares School Buildings & Stage at Tabon Elem.School, Brgy. Tabon, b) Improvement of Ynares Multi-Purpose Covered Court at Bangad Elem. School, Brgy. Bangad | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 76 | SEF | 1329225.58 |  | 1329225.58 | 1315145.05 |  | 1315145.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 15)Repair/Improvement of Multi-Purpose Buildings, Construction of Demountable Stage at Binangonan & Construction of Movable Bleacher & Concreting of Ground of Ynares Multi-Purpose Covered Court at Angono, Rizal; a) Repair/Improvement of 2-Storey Multi-Purpose Building (Health Center) and 2-Storey Ynares Multi-Purpose Building (Day Care Center) at Sitio Sto. Niño, Brgy. Bilibiran, Binangonan, b) Construction of Demountable Stage at Sitio Mata Elem. School, Brgy. Palangoy, Binangonan, c) Construction of Movable Bleacher & Concreting of Ground of Ynares Multi-Purpose Covered Court at Exodusville, Brgy. San Vicente , Angono | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 990847.84 |  | 990847.84 | 980846.33 |  | 980846.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 16)Concreting of Creek Bed (Portion) of Pinagsalaan Creek, Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 80 | GF | 1347239.18 |  | 1347239.18 | 1337796.18 |  | 1337796.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 17)Repair/Repainting of Ynares School Buildings, Ynares Multi-Purpose Covered Court & Construction of Fence for 2-Storey Ynares Multi-Purpose Building at Brgy. San Isidro, Cainta, Rizal; a) Repair/Repainting of Ynares School Buildings & Ynares Multi-Purpose Covered Court at Saint Gregory Elem.School, Brgy. San Isidro, b) Construction of Fence for 2-Storey Ynares Multi-Purpose Building at Brookside Hills Subd. , Brgy. San Isidro | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 52 | SEF | 1079225.17 |  | 1079225.17 | 1068025.05 |  | 1068025.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 18)Improvement of Ynares Multi-Purpose Covered Court, Ynares Stage, Ynares Multi-Purpose Building, Welded Wire Fence & Repair of Storage Room at Brgy. Sto. Domingo & Brgy. San Juan, Cainta, Rizal; a) Improvement of Ynares Multi-Purpose Covered Court & Ynares Stage at St. Joseph Elem. School, Brgy. Sto. Domingo, b) Improvement of 2-Storey Ynares Multi-Purpose Building at Palmera Heights Subd., Brgy. San Juan, c) Improvement (portion) of Welded Wire Fence at Marick Elem. School, Brgy. Sto. Domingo, d) Repair of Storage Room at Marick Elem. School, Brgy. Sto. Domingo | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 1268132.02 |  | 1268132.02 | 1252168.07 |  | 1252168.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 19)Repair/Repainting of Ynares School Buildings & Construction of Waiting Shed at Brgy. Pinugay, Baras, Rizal; a) Repair/Repainting of 1-storey,6-rooms Ynares School Building at Baras-Pinugay National High School, Sitio Habitat Southville 9, Brgy. Pinugay, Baras, Rizal, b) Repair/Repainting of Ynares School Building at Painaan Elem.School, Sitio Paenaan, Brgy. Pinugay, c) Construction of Waiting Shed at Baras Pinugay Elem. School Annex Ynares Village Phase 2, Brgy. Pinugay | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 64 | SEF | 1818972.07 |  | 1818972.07 | 1800646.15 |  | 1800646.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 20)Improvement / Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court & Construction of Comfort Room at Brgy. San Juan & Brgy. San Guillermo, Morong, Rizal; a) Improvement/ Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. San Juan, Morong, b) Construction of 2 seater Comfort Room at San Guillermo Elem. School, Brgy. San Guillermo, Morong | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 712980.62 |  | 712980.62 | 704934.19 |  | 704934.19 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 21)Repair of Ynares School Buildings at San Guillermo National.High School, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 62 | SEF | 2056014.45 |  | 2056014.45 | 2031336.36 |  | 2031336.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 22)Construction of Ynares Stage, Impr. / Provision of Movable Bleacher of Ynares Multi-Purpose Covered Court at Brgy. San Isidro & Brgy. Burgos, Rodriguez, Rizal; a) Construction of Ynares Stage and Impr.of Ynares Multi-Purpose Covered Court at Southville 8B, Phase 2, Brgy. San Isidro, b) Provision of Movable Bleacher at Ynares Multi-Purpose Covered Court, Doña Pepeng Subd. II, Brgy. Burgos | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 78 | GF | 2074659.92 |  | 2074659.92 | 2054481.05 |  | 2054481.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 23)Construction of Comfort Room at Ynares Multi-Purpose Covered Court, Metro Manila Hills, Phase 2B, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 64 | GF | 809995.92 |  | 809995.92 | 800864.93 |  | 800864.93 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 24)Construction of Covered Pathwalk at Sto Niño Elem.School, Brgy. Sto. Niňo, San Mateo, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 1299463.83 |  | 1299463.83 | 1286524.85 |  | 1286524.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 25)Asphalt Overlaying (portion) of B. Mariano St., Brgy. Sta. Ana, San Mateo, Rizal | PEO |  | Public Bidding | 2019-08-26 | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 7156853.68 |  | 7156853.68 | 7085408.82 |  | 7085408.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 26)Improvement/Repainting of Ynares Multi-Purpose Covered Court at Cayabu Elem.School, Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 782535.74 |  | 782535.74 | 774101.38 |  | 774101.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 27)Repair/Repainting of Ynares School Buildings at Cayabu Elem. School, Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | SEF | 1679588.9 |  | 1679588.9 | 1662233.81 |  | 1662233.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 28)Construction of Comfort Room, Demountable Stage, Improvement of Stage & Repainting of Perimeter Fence & Gate at Brgy. Plaza Aldea & Brgy. Tandang Kutyo, Tanay, Rizal; a) Construction of Comfort Room at Ynares Multi-Purpose Covered Court, De Castro Subd., Brgy. Plaza Aldea, b) Construction of Demountable Stage at Lorenzo A. Ramos Elem.School, Brgy. Tandang Kutyo, c) Improvement of Stage at Ilaya Elem. School, Brgy. Tandang Kutyo, d) Repainting of Perimeter Fence & Gate at Doña Paz Sumulong Tanjuatco Elem.School, Brgy. Tandang Kutyo | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 70 | GF | 1106896.37 |  | 1106896.37 | 1094326.8 |  | 1094326.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 29)Construction of 3-Seater Comfort Rooms & Installation of Solar Streetlights at Brgy. Cayabu & Brgy. Cuyambay, Tanay, Rizal; a) Construction of 3-Seater Comfort Rooms at Cayabu Elem. School, Brgy. Cayabu, b) Installation of Solar Streetlights at Sitio Maysawa, Brgy. Cuyambay | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 60 | GF | 1297324.12 |  | 1297324.12 | 1284103.41 |  | 1284103.41 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 30)Construction of Stock Room & Improvement of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. May-Iba & Brgy. Prinza, Teresa, Rizal; a) Construction of Stock Room at Quiterio San Jose Elem. School, Brgy. May-Iba, b) Improvement of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Prinza | PEO |  | Public Bidding |  | 28 Aug-3 Sept 2019 | 2019-09-04 |  | 2019-09-17 | 2019-09-23 | 2019-09-30 |  | 2019-10-04 | 2019-10-11 | 2019-10-18 | 50 | GF | 760304.78 |  | 760304.78 | 752585.36 |  | 752585.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-08-28 |  | 2019-08-28
| 1) Construction of Stone Masonry Wall at Creek near Block 15 PCUP-RPG Ville, Brgy. San Jose, Antipolo City | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 2094828.73 |  | 2094828.73 | 2071777.51 |  | 2071777.51 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 2) Construction of 4-storey, 16-rooms Ynares School Building at Angono Elementary School, Angono, Rizal | PEO |  | Public Bidding | 2019-09-20 | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 360 | SEF | 39193310.6 |  | 39193310.6 | 39073065.47 |  | 39073065.47 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 3) Rehabilitation/ Concreting (portion) of Botong Francisco Avenue, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 960201.5 |  | 960201.5 | 950090.58 |  | 950090.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 4) Construction of Comfort Room & Rehabilitation of Road at Angono & Cainta, Rizal; a) Construction of 3-Seater Comfort Room at San Vicente Elementary School, Brgy. San Vicente, Angono, b) Rehabilitation of K-6 St., Karangalan Village, Brgy. San Isidro, Cainta | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 797226.7 |  | 797226.7 | 788929.14 |  | 788929.14 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 5) Repair/Improvement of Ynares Multi-Purpose Covered Court at Doňa Susana Madrigal Elementary School, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 54 | GF | 1198754.72 |  | 1198754.72 | 1186793.13 |  | 1186793.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 6) Repair/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 48 | GF | 1285968.81 |  | 1285968.81 | 1272975.92 |  | 1272975.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 7) Repair/Improvement of Ynares School Buildings at Sapang Elementary School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 52 | SEF | 1358751.96 |  | 1358751.96 | 1344535.81 |  | 1344535.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 8) Improvement/Repair of Ynares Multi-Purpose Covered Court at Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 867262.46 |  | 867262.46 | 858254.99 |  | 858254.99 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 9) Construction of 2-storey, 6-rooms Ynares School Building at Macamot Elementary School, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2019-09-20 | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 204 | TF | 10491652.64 |  | 10491652.64 | 10386620.44 |  | 10386620.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 10)Improvement/Concreting of Creek Bed at Purok I, Brgy. Kalinawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 70 | GF | 1306931.52 |  | 1306931.52 | 1293877.16 |  | 1293877.16 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 11)Construction of 1-storey Ynares Multi-Purpose Building (Daycare Center) at Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 72 | GF | 1461800.66 |  | 1461800.66 | 1446936.27 |  | 1446936.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 12)Repair/Repainting of Ynares School Buildings at San Francisco Elementary School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 95 | SEF | 1512173.3 |  | 1512173.3 | 1495942.33 |  | 1495942.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 13) Improvement/Repainting of Ynares Multi-Purpose Covered Court, Ynares Multi-Purpose Building & Installation of Electronic Scoreboard at Brgy. San Andres, Cainta, Rizal; a) Improvement / Repainting of Ynares Multi-Purpose Covered Court & 1-Storey Ynares Multi-Purpose Building at Venice Homes, Brgy. San Andres, b) Improvement of Ynares Multi-Purpose Covered Court & Tennis Court at Midtown Village, Brgy. San Andres, c) Installation of Electronic Scoreboard at Ynares Multi-Purpose Covered Court at DM Homes Phase I Subd., Brgy. San Andres | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 1495191.16 |  | 1495191.16 | 1478301.17 |  | 1478301.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 14)Construction of 4-storey, 12-rooms Ynares School Building at Gov. Isidro Rodriguez Memorial National High School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding | 2019-09-20 | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 300 | TF | 30123008.74 |  | 30123008.74 | 30012920.62 |  | 30012920.62 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 15)Concreting of Road at Blk. 14, ABTHOA, Purok 3, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 1233398.46 |  | 1233398.46 | 1220815.02 |  | 1220815.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 16)Repair/Repainting of Ynares Multi-Purpose Covered Court & Repair/Replacement of Ceiling Eaves of School Building at Brgy. Dolores, Taytay, Rizal; a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Tower Hills Subd., Brgy. Dolores, b) Repair/Replacement of Ceiling Eaves of 2-Storey, 4-Rooms Ynares School Building at Taytay Elementary School, Brgy. Dolores | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 729891.73 |  | 729891.73 | 721099.1 |  | 721099.1 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 17)Construction of 4-storey, 16-rooms Ynares School Building at Rosario Ocampo Elementary School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding | 2019-09-20 | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 344 | SEF | 38251578.69 |  | 38251578.69 | 38130695.22 |  | 38130695.22 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 18)Construction of 1-storey, 4-rooms Ynares School Building at Tuna Barrio School, Brgy. Tuna, Cardona, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 160 | TF | 5329549.86 |  | 5329549.86 | 5275424.36 |  | 5275424.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 19)Construction of Artesian Wells, Dismantling of Elevated Steel Water Tank/Pump & Motor & Improvement/Re-Piping of Water Lines at Brgy. Bagumbong, Brgy. Lubo & Brgy. First District, Jalajala, Rizal; a) Construction of three (3)-units Artesian Well at Brgy. Bagumbong, b) Dismantling of 10,000gals capacity of Elevated Steel Water Tank/Pump & Motor at Brgy. Lubo, c) Improvement/Re-Piping of Water Lines of Ynares Municipal Hospital (old Bldg.), Brgy. First District | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 1141154.51 |  | 1141154.51 | 1129739.65 |  | 1129739.65 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 20)Extension/Improvement/Repair/Repainting of 2-storey Ynares Multi-Purpose Bldg. (Barangay Hall) at Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 114 | GF | 2798429.16 |  | 2798429.16 | 2770335.23 |  | 2770335.23 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 21)Rehabilitation of Stone Masonry Wall (portion) of Morong River, Tupas St, Sitio Ibaba, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 1651722.24 |  | 1651722.24 | 1634760.27 |  | 1634760.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 22)Repair/Improvement of Ynares Multi-Purpose Covered Court at Balajadia St., Sitio Ibaba, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 60 | GF | 1039999.68 |  | 1039999.68 | 1028104.07 |  | 1028104.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 23)Construction of 2-storey, 2-rooms Ynares School Building at Wawa National High School, Brgy. San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 92 | SEF | 3098677.71 |  | 3098677.71 | 3065564.7 |  | 3065564.7 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 24)Construction of Covered Pathwalk & Rehabilitation / Improvement of Ynares Waiting Shed at Brgy. San Rafael & Brgy. San Jose, Rodriguez, Rizal; a) Construction of Covered Pathwalk at Wawa Nat'l.High School, Brgy. San Rafael, b) Rehabilitation/Improvement of Ynares Waiting Shed at Villa Ana Maria Subd., Brgy. San Jose | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 50 | GF | 850732.2 |  | 850732.2 | 841605.82 |  | 841605.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 25)Construction of 2-storey Ynares Multi-Purpose Bldg. at Lotus Ville, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 140 | GF | 3540029.56 |  | 3540029.56 | 3502327.85 |  | 3502327.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 26)Construction of 1-storey, 3-rooms Ynares School Building at Cayabu National High School, Brgy. Cayabu, Tanay, Rizal | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 120 | TF | 3483795.19 |  | 3483795.19 | 3447980.08 |  | 3447980.08 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 27)Asphalt Overlaying of Roads at Teresa & Jalajala, Rizal; a) Asphalt Overlaying of OT Cruz St, Brgy. Dulumbayan, Teresa, b) Asphalt Overlaying of JICA Road (portion) and Turnina Bridge at Sitio Pulong Monico, Brgy. Bagumbong, Jalajala | PEO |  | Public Bidding |  | 23 - 29 Sept 2019 | 2019-09-01 |  | 2019-10-15 | 2019-10-21 | 2019-10-28 |  | 2019-11-04 | 2019-11-08 | 2019-11-14 | 52 | GF | 2728035.1 |  | 2728035.1 | 2701652.63 |  | 2701652.63 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-09-23 |  | 2019-09-23
| 1) Construction of 1-storey Ynares Multi-Purpose Bldg. & Repair & Improvement of Ynares Multi-Purpose Covered Court, Stage & Fence at Brgy. Dela Paz, Antipolo City; a) Construction of 1-storey Ynares Multi-Purpose Bldg. at Phase V, Lower Lucban, Brgy. Dela Paz, b) Repair & Improvement of Ynares Multi-Purpose Covered Court, Stage & Fence at Purok Silangan, Brgy. Dela Paz | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 80 | GF | 1670968.21 |  | 1670968.21 | 1655002.59 |  | 1655002.59 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 2) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center & Repair of 2-storey Ynares Multi-Purpose Bldg. at Antipolo City & Cainta, Rizal; a) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Francisville Subd., Brgy. Mambugan, Antipolo City, b) Repair of 2-storey Ynares Multi-Purpose Bldg. at Villarica Subd., Brgy. Sto. Domingo, Cainta | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 80 | GF | 1098119.98 |  | 1098119.98 | 1085866.78 |  | 1085866.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Nayon Silangan Subd., Brgy. Dalig, Antipolo City | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 70 | GF | 800405.96 |  | 800405.96 | 792470.68 |  | 792470.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 4) Improvement/Repainting of Ynares Multi-Purpose Covered Court at Rosario Village, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 92 | GF | 1741039.16 |  | 1741039.16 | 1723594.73 |  | 1723594.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 5) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Richmond Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 70 | GF | 822917.72 |  | 822917.72 | 813785.37 |  | 813785.37 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 6) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Grandvalley Subd., Phase 3, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 70 | GF | 841557.85 |  | 841557.85 | 833557.3 |  | 833557.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 7) Construction of 15x28m Ynares Multi-Purpose Covered Court (Rafter Type) at Grandview Homes I, Sitio San Jose, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 108 | GF | 2730230.69 |  | 2730230.69 |  |  | CANCELLED | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 8) Improvement / Repainting, Repair of Electrical Lighting System of Ynares Multi-Purpose Covered Court & Ynares Stage at Brgy. Macamot & Brgy. Tayuman, Binangonan, Rizal; a) Improvement/Repainting of Ynares Multi-Purpose Covered Court & Ynares Stage at Macamot Elem. School, Brgy. Macamot, b) Repair of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Tayuman | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 72 | GF | 1181663.6 |  | 1181663.6 | 1169348.26 |  | 1169348.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 9) Improvement/Installation of Road Safety Signages at Darangan, Binangonan-Angono-Antipolo Road (Eastridge), Rizal | PEO |  | Public Bidding | 2019-09-30 | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 160 | TF | 10497725.2 |  | 10497725.2 | 10407701.85 |  | 10407701.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 10)Repair of Main & Annex Building at University of Rizal System-Binangonan Campus, Brgy. Calumpang, Binangonan, Rizal | PEO |  | Public Bidding | 2019-09-30 | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 224 | GF | 12509257.66 |  | 12509257.66 | 12418614.13 |  | 12418614.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 11)Concreting (portion) of Road at Block 18, Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 60 | TF | 1165580.58 |  | 1165580.58 | 1154565.07 |  | 1154565.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 12)Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Brgy. San Juan, Taytay, Rizal; a) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) at Fishport, Floodway A, Brgy. San Juan, b) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Batasin II, Floodway A, Brgy. San Juan | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 120 | GF | 1605929.67 |  | 1605929.67 | 1589257.1 |  | 1589257.1 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 13)Concreting of M. Borja St. (Interior), Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 76 | TF | 1431361.72 |  | 1431361.72 | 1417703.54 |  | 1417703.54 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 14)Construction of Stone Masonry Wall for Slope Protection around Wet & Dry Market at Blk 73 Southville 9 (Ynares Village), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 72 | GF | 2049661.66 |  | 2049661.66 | 2028491.31 |  | 2028491.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 15)Improvement of 2-storey Ynares Multi-Purpose Bldg. (Barangay Hall) at Brgy. San Jose, Baras, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 60 | GF | 766985.4 |  | 766985.4 | 758931.29 |  | 758931.29 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 16)Asphalt Overlaying (portion) of H.F. (formerly Magsaysay Blvd.), Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2019-09-30 | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 60 | GF | 6168631.13 |  | 6168631.13 | 6106096.23 |  | 6106096.23 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 17)Construction of 10x24m Ynares Multi-Purpose Covered Court (Rafter Type) at Baras-Pinugay National High School, Phase 1 (Senior High School), Sitio Habitat, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 108 | GF | 2819406.14 |  | 2819406.14 | 2791429.69 |  | 2791429.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 18)Improvement/Concreting (portion) of Mahogany St. & Palmera St., Sitio Baliksaka, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 80 | TF | 2380735.22 |  | 2380735.22 | 2357708.06 |  | 2357708.06 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 19)Improvement/Repair of Ynares Multi-Purpose Covered Court and Stage at Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 72 | GF | 1435792.98 |  | 1435792.98 | 1425777.48 |  | 1425777.48 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 20)Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Sampad, Cardona, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 60 | GF | 1364605.1 |  | 1364605.1 | 1350721.87 |  | 1350721.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 21)Construction of Additional 2nd Floor of Ynares Multi-Purpose Bldg. (Baragay Hall) at Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 160 | GF | 4576044.07 |  | 4576044.07 | 4530859.31 |  | 4530859.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 22)Construction of 2-storey Ynares Multi-Purpose Bldg. (Barangay Hall) at Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 148 | GF | 3599074.72 |  | 3599074.72 | 3569009.45 |  | 3569009.45 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 23)Construction of Stone Masonry for Slope Protection of Maunahan Creek, Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 120 | GF | 4447796.65 |  | 4447796.65 | 4402712.57 |  | 4402712.57 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 24)Repair of 1-storey, 4-rooms Ynares School Building at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 60 | GF | 941082.01 |  | 941082.01 | 930846.11 |  | 930846.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 25)Construction of 12x12m Ynares Multi-Purpose Covered Court (Rafter Type) & Perimeter Fence at Southville 8B Phase 3, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 76 | GF | 2258096.05 |  | 2258096.05 | 2235658.49 |  | 2235658.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 26)Renovation of 1-storey Multi-Purpose Building at Amityville Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 92 | GF | 3306945.36 |  | 3306945.36 | 3272996.35 |  | 3272996.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 27)Construction of 2-Storey Ynares Multi-Purpose Building at Villa Ana Maria Subd., Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 150 | GF | 3162259.86 |  | 3162259.86 | 3129480.41 |  | 3129480.41 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 28)Repair/Repainting of Ynares School Buildings, Stage & Multi-Purpose Covered Court at Burgos Elem. School, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 93 | GF | 2663659.11 |  | 2663659.11 | 2639139.12 |  | 2639139.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 29)Construction of 2-storey Ynares Multi-Purpose Bldg. at Graceland Executive Village, Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 92 | GF | 1550471 |  | 1550471 | 1534247.32 |  | 1534247.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 30)Rehabilitation (portion) of Riprap for Side Protection of Road at Brgy. Laiban, Tanay, Rizal | PEO |  | Public Bidding |  | 01 - 07 Oct 2019 | 2019-10-07 |  | 2019-10-18 | 2019-10-22 | 2019-10-28 |  | 2019-11-08 | 2019-11-08 | 2019-11-14 | 72 | GF | 1822893.32 |  | 1822893.32 | 1804885.66 |  | 1804885.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-01 |  | 2019-10-01
| 1) Repair/Repainting of Multi-Purpose Covered Court, Perimeter Fence & Replacement of Basketball Goal at Brgy. Inarawan, Antipolo City; a) Repair/Repainting of Gatlabayan Multi-Purpose Covered Court & Perimeter Fence at St. Anthony II, Brgy. Inarawan, b) Replacement of Basketball Goal at Sitio Maagay II, Brgy. Inarawan | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 68 | GF | 1369200.51 |  | 1369200.51 | 1355788.89 |  | 1355788.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 2) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Teremil Subd., Brgy. Mambugan, Antipolo City | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 70 | PDRRMF | 798491.35 |  | 798491.35 | 789322.96 |  | 789322.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Kingsville Subd., Brgy. Inarawan, Antipolo City | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 70 | PDRRMF | 796467.96 |  | 796467.96 | 788460.97 |  | 788460.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 4) Improvement/Concreting of Magnolia St. at Nieves Hills Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 68 | TF | 1044363.22 |  | 1044363.22 | 1034323.72 |  | 1034323.72 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 5) Improvement/Concreting of Jasmine St. at Nieves Hills Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 68 | TF | 1028824.86 |  | 1028824.86 | 1018762.24 |  | 1018762.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 6) Repair/Repainting/Improvement of Ynares School Buildings at Brgy. Buhangin & Brgy. Kinagatan, Binangonan, Rizal; a) Repair/Repainting of Ynares School Buildings at Buhangin Elem. School, Brgy. Buhangin, b) Improvement/Repair/Repainting of Ynares School Building at Kinagatan Elem. School, Brgy. Kinagatan | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 70 | GF | 1760957.9 |  | 1760957.9 | 1742716.02 |  | 1742716.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 7) Improvement of Ynares Multi-Purpose Covered Court & Construction of 2-seater Comfort Room at St. Clement Village I, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 72 | GF | 1756565.08 |  | 1756565.08 | 1738942.3 |  | 1738942.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 8) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Binangonan Elem. School, Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 72 | GF | 1483412.06 |  | 1483412.06 | 1468639.22 |  | 1468639.22 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 9) Repair/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Libid, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 100 | GF | 2889807.58 |  | 2889807.58 | 2859796.87 |  | 2859796.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 10) Construction of Bleacher and Mesh Welded Wire Fence & Repair/Repainting of Stage at Binangonan Elem. School, Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 68 | GF | 813296.86 |  | 813296.86 | 804708.69 |  | 804708.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 11) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center & Construction of Fence (Portion) of Parks / Playground at Brgy. San Isidro, Cainta, Rizal; a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Greenpark Village , Phase 8A, Zone 4, Brgy. San Isidro, b) Construction of Fence (Portion) of Parks / Playground at Greenpark Village, Zone 6, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 76 | PDRRMF | 1325670.92 |  | 1325670.92 | 1310103.68 |  | 1310103.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 12) Improvement/Additional 2nd Floor (Mezzanine) of Ynares Multi-Purpose Bldg. at Blk. 30, Purok 8, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 148 | GF | 2704301.94 |  | 2704301.94 | 2676635.53 |  | 2676635.53 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 13) Repair of School Buildings at Bagong Pag-Asa Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 60 | GF | 832884.78 |  | 832884.78 | 823947.75 |  | 823947.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 14) Rehabilitation/Concrete Reblocking of T.R. Llagas St., Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 68 | TF | 982307.15 |  | 982307.15 | 972236.88 |  | 972236.88 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 15) Construction of Covered Pathwalk and Improvement of Various Rooms at Baras Elem. School, Brgy. Concepcion, Baras, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 84 | GF | 2181678.75 |  | 2181678.75 | 2159768.24 |  | 2159768.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 16) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage at Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 72 | GF | 870615.12 |  | 870615.12 | 860080.98 |  | 860080.98 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 17) Construction of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at Sitio Pulong Ligaya, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 100 | GF | 3254371.91 |  | 3254371.91 | 3221173.86 |  | 3221173.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 18) Construction of 4,000 gals. Elevated Steel Water Tank at San Guillermo National High School, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 60 | GF | 816655.05 |  | 816655.05 | 808482.74 |  | 808482.74 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 19) Repair/Improvement of Ynares Multi-Purpose Covered Court at Capt. Titoy St., Sitio Ibaba, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 68 | GF | 726807.42 |  | 726807.42 | 719759.01 |  | 719759.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 20) Asphalt Overlaying of Various Roads at Sitio Namay, Brgy. San Juan, Morong, Rizal; a) Asphalt Overlaying of Rodriguez St., Sitio Namay, Brgy. San Juan, b) Asphalt Overlaying of Mateo St.., Sitio Namay, Brgy. San Juan, c) Asphalt Overlaying of Gutierrez St.., Sitio Namay, Brgy. San Juan | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 60 | GF | 3209036.72 |  | 3209036.72 | 3177815.79 |  | 3177815.79 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 21) Asphalt Overlaying of Various Roads at Sitio Caingin, Turentigue St., Sitio Wawa & Road at Cruz Compound, Sitio Taghangin, Brgy. San Juan, Morong, Rizal; a) Asphalt Overlaying of Various Roads at Sitio Caingin, Brgy. San Juan, b) Asphalt Overlaying of Turentigue St., Sitio Wawa, Brgy. San Juan, c) Asphalt Overlaying of Road at Cruz Compound, Sitio Taghangin, Brgy. San Juan | PEO |  | Public Bidding | 2019-10-08 | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 80 | GF | 7145429.05 |  | 7145429.05 | 7074450.46 |  | 7074450.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 22) Improvement of Ynares Multi-Purpose Covered Court & Fence at Brgy. Imatong & Brgy. Takungan, Pililla, Rizal; a) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Imatong, b) Improvement of Fence of Ynares Multi-Purpose Covered Court at Brgy. Takungan | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 60 | GF | 824236.14 |  | 824236.14 | 815822.66 |  | 815822.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 23) Construction of 1-Storey Ynares Multi-Purpose Building at Southville 8C, Phase 1K, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 96 | GF | 1907251.79 |  | 1907251.79 | 1887562.17 |  | 1887562.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 24) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Charmizons Subd., Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 70 | PDRRMF | 794499.21 |  | 794499.21 | 786579.78 |  | 786579.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 25) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Marigold Subd. & Doňa Maria Subd., Brgy. Burgos, Rodriguez, Rizal; a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Marigold Subd., Brgy. Burgos, b) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Doňa Maria Subd., Brgy. Burgos | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 90 | PDRRMF | 1604663.18 |  | 1604663.18 | 1587951.44 |  | 1587951.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 26) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Victoria Hills Eastwood Greenview, Phase 5, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 70 | PDRRMF | 794499.21 |  | 794499.21 | 786579.78 |  | 786579.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 27) Construction of 17x30m Ynares Multi-Purpose Covered Court (Rafter Type) at East Meridian (Phase 1A Bianca), Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 140 | GF | 4021344.25 |  | 4021344.25 | 3980221.02 |  | 3980221.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 28) Asphalt Overlaying of Eastwood Roads, Rodriguez, Rizal | PEO |  | Public Bidding | 2019-10-08 | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 200 | GF | 48999455.53 |  | 48999455.53 | 48868796.88 |  | 48868796.88 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 29) Rehabilitation/Concreting of Various Roads at Modesta Village, Brgy. Sto. Niňo, San Mateo, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 80 | TF | 2530104.87 |  | 2530104.87 | 2503584.06 |  | 2503584.06 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 30) Construction of Drainage Canal (portion) at Damaso Reyes St., Brgy. San Isidro, Tanay, Rizal | PEO |  | Public Bidding |  | 11 - 17 Oct 2019 | 2019-10-18 |  | 2019-10-30 | 2019-11-04 | 2019-11-11 |  | 2019-11-15 | 2019-11-22 | 2019-11-29 | 64 | GF | 1120944.6 |  | 1120944.6 | 1109942.99 |  | 1109942.99 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-11 |  | 2019-10-11
| 1) Repair/Improvement of Various School Buildings at University of Rizal System-Antipolo Campus, Brgy. San Roque, Antipolo City | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 140 | GF | 6103065.55 |  | 6103065.55 | 6052319.76 |  | 6052319.76 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 2) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Villa Grande Subd., Brgy. Cupang, Antipolo City | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | PDRRMF | 800405.46 |  | 800405.46 | 792446.26 |  | 792446.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 3) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Village East Executive Homes, Brgy. Muntindilaw, Antipolo City | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | PDRRMF | 794499.21 |  | 794499.21 | 786398.61 |  | 786398.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 4) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Senora dela Paz Subd. (ABA Homes), Brgy. Dalig, Antipolo City | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | PDRRMF | 796467.96 |  | 796467.96 | 788508.71 |  | 788508.71 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 5) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Brgy. Sta. Cruz & Brgy. San Roque, Antipolo City; a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Bankers Village, Brgy. Sta. Cruz, b) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at URS-Antipolo, Brgy. San Roque | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 120 | PDRRMF | 1596873.42 |  | 1596873.42 | 1580954.97 |  | 1580954.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 6) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Sitio Fuentes, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 60 | GF | 897308.32 |  | 897308.32 | 888641.25 |  | 888641.25 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 7) Improvement/Construction of Drainage Canal at Purok I & II, Brgy. Gulod, Binangonan, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 90 | GF | 2684802.08 |  | 2684802.08 | 2657431.03 |  | 2657431.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Vista Verde Executive Homes, Phase I, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | PDRRMF | 794499.21 |  | 794499.21 | 786448.53 |  | 786448.53 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 9) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Rotaryville , Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | PDRRMF | 807321.58 |  | 807321.58 | 799019.98 |  | 799019.98 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 10) Rehabilitation/Concreting (portion) of Bonifacio St., Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 84 | TF | 2426606 |  | 2426606 | 2402151.74 |  | 2402151.74 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 11) Repair/Repainting of Ynares School Buildings at Exodus Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 68 | GF | 1179023.3 |  | 1179023.3 | 1165431.03 |  | 1165431.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 12) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Brgy. San Andres & Brgy. San Isidro, Cainta, Rizal; a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Greenwoods Executive Village Area 2, Brgy. San Andres, b) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Adelina Homes II, Brgy. San Isidro | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 120 | PDRRMF | 1590967.17 |  | 1590967.17 | 1574765.97 |  | 1574765.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 13) Improvement of Ynares School Buildings at Rosario Ocampo Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 60 | GF | 1011303.74 |  | 1011303.74 | 999844.43 |  | 999844.43 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at URS-Taytay, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | GF | 811097.08 |  | 811097.08 | 802865.28 |  | 802865.28 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 15) Construction of 2-storey, 4-rooms Ynares School Building at Taytay Elem. School (Central), Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 168 | SEF | 7637174.94 |  | 7637174.94 | 7559420.51 |  | 7559420.51 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 16) Construction of Water System Level II at Baras Senior High School, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 140 | GF | 2235089.4 |  | 2235089.4 | 2212749.9 |  | 2212749.9 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 17) Construction of Drainage Canal & Fence at Brgy. Dalig & Brgy. San Roque, Cardona, Rizal; a) Construction of Drainage Canal at Concepcion St., Purok 3, Brgy. Dalig, b) Construction of Fence (portion) at B.F. San Juan National High School, Brgy. San Roque | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 72 | GF | 1111618.38 |  | 1111618.38 | 1100044.15 |  | 1100044.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 18) Construction of 1-storey, 2-rooms Ynares School Building at Looc Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 102 | SEF | 2603798.97 |  | 2603798.97 | 2587518.03 |  | 2587518.03 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 19) Repair of Ynares Multi-Purpose Covered Court (Morong Gym) at Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 64 | GF | 1075745.92 |  | 1075745.92 | 1063614.98 |  | 1063614.98 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 20) Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 60 | GF | 1010321.48 |  | 1010321.48 | 1000313.02 |  | 1000313.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 21) Construction of 15x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Morong National High School-Talaga Annex, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 120 | GF | 3606339.04 |  | 3606339.04 | 3570194.38 |  | 3570194.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 22) Rehabilitation/Improvement/Repair of Ynares Multi-Purpose Bldg. & Construction of Children's Playground at Metro Manila Hills, Phase 2B, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 60 | GF | 972686.78 |  | 972686.78 | 962180.12 |  | 962180.12 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 23) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Metro Montana Village, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | PDRRMF | 794499.21 |  | 794499.21 | 786579.78 |  | 786579.78 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 24) Construction of Stage, Fence & Improvement of Ynares Multi-Purpose Covered Court at Pamahay Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 80 | GF | 1283413.65 |  | 1283413.65 | 1271411.96 |  | 1271411.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 25) Construction of 13x15m Ynares Multi-Purpose Covered Court (Rafter Type) at Eastwood Residences, Phase 6, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 100 | GF | 2431162.09 |  | 2431162.09 | 2407994.22 |  | 2407994.22 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 26) Improvement / Repair of Ynares Multi-Purpose Covered Court & Repair/Repainting of Barangay Outpost, Day Care Center, Health Center and Barangay. Hall at Brgy. Laiban, Tanay, Rizal; a) Improvement / Repair of Ynares Multi-Purpose Covered Court at Brgy. Laiban, b) Repair/Repainting of Barangay Outpost, Day Care Center, Health Center and Barangay. Hall at Brgy. Laiban | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 80 | GF | 1478639.58 |  | 1478639.58 | 1462226.55 |  | 1462226.55 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 27) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) & Covered Pathwalk at Brgy. Sampaloc & Brgy. Wawa, Tanay, Rizal; a) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) at Brgy. Sampaloc, b) Construction of Covered Pathwalk at Tanay West National High School, Brgy. Wawa | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 90 | GF | 982833.59 |  | 982833.59 | 972745.72 |  | 972745.72 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 28) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Brgy. Laiban, Tanay, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 70 | GF | 815698.97 |  | 815698.97 | 807458.11 |  | 807458.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 29) Construction of Perimeter Fence of Bureau of Jail Management & Penology (Teresa District Jail) at Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 160 | GF | 4279603.58 |  | 4279603.58 | 4234608.41 |  | 4234608.41 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
| 30) Asphalt Overlaying of Roads at Teresa & Pililla, Rizal; a) Asphalt Overlaying of Sgt. Espiritu Santo St., Brgy. Calumpang-Sto. Cristo, Teresa, b) Asphalt Overlaying of M. Garrovillas St., Brgy. Calumpang-Sto. Cristo, Teresa, c) Asphalt Overlaying of A.V. Masarap St., Brgy. Takungan, Pililla | PEO |  | Public Bidding |  | 31 Oct - 6 Nov 2019 | 2019-11-05 |  | 2019-11-18 | 2019-11-22 | 2019-11-28 |  | 2019-12-04 | 2019-12-13 | 2019-12-20 | 60 | GF | 2839380.98 |  | 2839380.98 | 2810660.34 |  | 2810660.34 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-10-31 |  | 2019-10-31
Total Alloted Budget of Procurement Activities | [17 empty] | 578812919.8
Total Contract Price of Procurement Activities Conducted | [17 empty] | 567652475.52
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 11160444.28
ON-GOING PROCUREMENT ACTIVITIES
| 1) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Mayamot National High School, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 70 | PDRRMF | 809366.55 |  | 809366.55 | 801237.75 |  | 801237.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 2) Improvement/Concreting (portion) of Road at Sitio Igiban, Zone 7-A, Brgy. Cupang, Antipolo City | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 150 | GF | 7951914 |  | 7951914 | 7871887.61 |  | 7871887.61 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 3) Improvement/Installation of Canopy of Ynares Multi-Purpose Covered Court at Angono Elem. School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 68 | GF | 701782.06 |  | 701782.06 | 694550.25 |  | 694550.25 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 4) Construction of Drainage Canal and Rehabilitation of Stone Masonry Wall at Ulang St., Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 96 | GF | 1375567.47 |  | 1375567.47 | 1362427.66 |  | 1362427.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 5) Construction of 15x18m Ynares Multi-Purpose Covered Court (Rafter Type) at Grandview Homes I, Sitio San Jose, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 108 | GF | 2730230.69 |  | 2730230.69 | 2702384.68 |  | 2702384.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 6) Installation of Solar Streetlights at Darangan, Binangonan - Angono - Antipolo Road (Eastridge), Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 90 | GF | 6516972.11 |  | 6516972.11 | 6461733.37 |  | 6461733.37 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 7) Construction of 3-storey, 6-rooms Ynares School Building at St. Joseph Elem. School, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 220 | SEF | 12435647.3 |  | 12435647.3 | 12311269.47 |  | 12311269.47 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 8) Improvement/Rehabilitation of Concrete Pavement and Drainage Canal at Irish St., Esla Subd., Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 80 | GF | 2669067.94 |  | 2669067.94 | 2642660.35 |  | 2642660.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 9) Improvement/Construction of Drainage Canal at Zinia St., Esla Subd., Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 60 | GF | 535709.63 |  | 535709.63 | 529885.93 |  | 529885.93 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 10) Improvement/ Concreting of Pasadena St. (Area 4 & 5), Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 60 | GF | 1586242.5 |  | 1586242.5 | 1575441.73 |  | 1575441.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 11) Improvement/Repair of Ynares Multi-Purpose Covered Court at Exodus Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 60 | GF | 1151907.5 |  | 1151907.5 | 1139079.15 |  | 1139079.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 12) Improvement of Covered Pathwalk & Installation of Steel Grills of School Bldg. at Brgy. Dolores, Taytay, Rizal; a) Improvement of Covered Pathwalk at Taytay Elem. School, Brgy. Dolores, b) Installation of Steel Grills of 4-Storey 16-Rooms DepEd School Bldg. at Dolores Elem. School, Brgy. Dolores | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 52 | GF | 781318.27 |  | 781318.27 | 772924.16 |  | 772924.16 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 13) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at San Juan Resettlement, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 70 | GF | 817241.55 |  | 817241.55 | 809087.18 |  | 809087.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 14) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Golden City, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 70 | GF | 810679.05 |  | 810679.05 | 802524.68 |  | 802524.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 15) Repair/Repainting of 4-Storey Ynares School Building at University of Rizal System Taytay Campus, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 68 | GF | 1499671.45 |  | 1499671.45 | 1484716.31 |  | 1484716.31 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 16) Repair/Improvement of Ynares Multi-Purpose Covered Court & Installation of Steel Grills at 2nd Floor Area of School Buildings at Brgy. Muzon & Brgy. Sta. Ana, Taytay, Rizal; a) Repair/Improvement of Ynares Multi-Purpose Covered Court at Muzon National High School, Brgy. Muzon, b) Installation of Steel Grills at 2nd Floor Area of School Buildings at Sta. Ana Elem. School, Brgy. Sta. Ana | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 60 | SEF | 730393.04 |  | 730393.04 | 723168.73 |  | 723168.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 17) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at St. Anthony Subd., Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 70 | GF | 809366.67 |  | 809366.67 | 801345.42 |  | 801345.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 18) Construction of Drainage Canal at Concepcion St., Purok 4 & 5, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 100 | GF | 2029012.21 |  | 2029012.21 | 2008976.05 |  | 2008976.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 19) Concreting of School Ground at Subay Elem. School, Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 60 | SEF | 989980.09 |  | 989980.09 | 979907.38 |  | 979907.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 20) Construction of Covered Pathwalk & Waiting Shed at B.F. San Juan National High School, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 92 | SEF | 1873470.52 |  | 1873470.52 | 1854009.27 |  | 1854009.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 21) Improvement of Ynares Multi-Purpose Covered Court at Palma St., Sitio Ibaba, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 68 | GF | 1050176.57 |  | 1050176.57 | 1040258.13 |  | 1040258.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 22) Installation/Improvement/Rehabilitation/Repair of Electrical Lighting System of Ynares Multi-Purpose Covered Court & Installation of Solar Streetlights at Brgy. San Pedro & Brgy. Maybancal, Morong, Rizal; a) Installation/ of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Sitio Ibaba, Brgy. San Pedro, b) Improvement / Rehabilitation / Repair of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. San Pedro, c) Installation of Solar Streetlights at Brgy. Maybangcal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 60 | GF | 1424972.1 |  | 1424972.1 | 1409710.69 |  | 1409710.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 23) Asphalt Overlaying (portion) of Garrovillas St. & Zamora St., Brgy. San Jose, Morong, Rizal; a) Asphalt Overlaying (portion) of Garrovillas St., Brgy. San Jose, b) Asphalt Overlaying of Zamora St., Brgy. San Jose | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 40 | GF | 1819550.82 |  | 1819550.82 | 1800639.97 |  | 1800639.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 24) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Brgy. San Jose & Brgy. San Isidro, Rodriguez, Rizal; a) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Sub-Urban Village, Phase 1-A, Brgy. San Jose, b) Construction/Provision of Wash Facilities (Water Sanitation & Hygiene) at Eastwood Residences, Phase 8/8A, Brgy. San Isidro | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 90 | PDRRMF | 1621513.14 |  | 1621513.14 | 1605163.91 |  | 1605163.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 25) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Courts & Repair of Fence & Rehabilitation/Concreting (portion) of School Ground at Brgy. Geronimo & Brgy. San Isidro, Rodriguez, Rizal; a) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Greenrose 1 Subd., Brgy. Geronimo, b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Phase 7-7A Eastwood Residences, Brgy. San Isidro, c) Repair of Fence & Rehabilitation/Concreting (portion) of School Ground at San Isidro National High School, Brgy. San Isidro | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 72 | GF | 771220.06 |  | 771220.06 | 763206.15 |  | 763206.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 26) Construction of Stone Masonry for Slope Protection at Sitio Laan Creek 3, Brgy. Macabud, Rodriguez, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 120 | GF | 5088153.24 |  | 5088153.24 | 5035178.66 |  | 5035178.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 27) Concreting of Road at Purok 4, Brgy. Pintong Bukawe, San Mateo, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 72 | TF | 2677922.85 |  | 2677922.85 | 2649712.97 |  | 2649712.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 28) Improvement/Repair of Ynares Multi-Purpose Covered Court & Ynares Multi-Purpose Building at Brgy. Malanday & Brgy. Guitnang Bayan II, San Mateo, Rizal; a) Improvement Repair of Ynares Multi-Purpose Covered Court at Brgy. Malanday, b) Improvement of Ynares Multi-Purpose Covered Court & Ynares Multi-Purpose Building at La Mar Village, Brgy. Guitnang Bayan II | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 84 | GF | 3369061.4 |  | 3369061.4 | 3335305.19 |  | 3335305.19 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 29) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Tablon, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 70 | GF | 842311.29 |  | 842311.29 | 832005.18 |  | 832005.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 30) Construction of 2-storey Ynares Multi-Purpose Building at Sitio Harangan, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 12 - 18 Nov 2019 | 2019-11-18 |  | 2019-12-03 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 26 de 19 | 2020-01-09 | 136 | GF | 3265075.09 |  | 3265075.09 | 3232225.15 |  | 3232225.15 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-12 |  | 2019-11-12
| 1) Concreting & Improvement of Drainage Canal at M.L. Quezon Ave. (portion), San Martin Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 1927857.82 |  | 1927857.82 | 1907954.26 |  | 1907954.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 2) Improvement/Concreting of Villaluz St. (Dulo), Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 50 | GF | 523762.5 |  | 523762.5 | 517964.92 |  | 517964.92 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 3) Rehabilitation/Concreting (portion) of Road at Sitio Hulo, Brgy. Pilapila, Binangonan, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 76 | GF | 3022381.86 |  | 3022381.86 | 2992387.71 |  | 2992387.71 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 4) Construction of Drainage Canal (portion) of Bonifacio St., Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 706533.75 |  | 706533.75 | 697790.51 |  | 697790.51 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 5) Construction of 2-storey Ynares Multi-Purpose Building at Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 100 | GF | 3085242.67 |  | 3085242.67 | 3053732.86 |  | 3053732.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 6) Improvement/ Concreting of Boston St. (Area 7), Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 2023181.22 |  | 2023181.22 | 2002255.21 |  | 2002255.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 7) Improvement/ Concreting of Herrera St. (Area 4 & 5), Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 1344685.43 |  | 1344685.43 | 1330456.86 |  | 1330456.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 8) Improvement/ Concreting of Crisfield Ave. (Area 1), Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 1259414.54 |  | 1259414.54 | 1246624.32 |  | 1246624.32 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 9) Improvement/ Concreting of Bellevue St. (Area 9), Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 1152140.88 |  | 1152140.88 | 1140216.73 |  | 1140216.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 10) Improvement/ Concreting of Colby Ave. (Area 14), Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 1124290.24 |  | 1124290.24 | 1112051.8 |  | 1112051.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 11) Construction of 8x12m Ynares Multi-Purpose Covered Court (Rafter Type) at Francisco P. Felix Elem. School, Unit 1, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 82 | SEF | 1495129.94 |  | 1495129.94 | 1480201.24 |  | 1480201.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 12) Construction of 2-storey Ynares Multi-Purpose Building at Anak Pawis, Floodway, Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 134 | GF | 2257429.42 |  | 2257429.42 | 2235395.11 |  | 2235395.11 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 13) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) & Improvement/Repair of Ynares Multi-Purpose Covered Court at Taytay & Cainta, Rizal; a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Cresdaville II Subd., Brgy. San Juan, Taytay, b) Improvement/Repair of Ynares Multi-Purpose Covered Court at Apple Village I Subd., Valley Golf Road, Brgy. San Juan, Cainta | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 1030939.79 |  | 1030939.79 | 1020999.49 |  | 1020999.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 14) Installation of Solar Streetlights at Southville 9, Ynares Village, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 5086498.9 |  | 5086498.9 | 5036175.75 |  | 5036175.75 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 15) Rehabilitation of Drainage Canal of Roads at Brgy. San Miguel, Baras, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 140 | GF | 3258905.85 |  | 3258905.85 | 3226934.67 |  | 3226934.67 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 16) Construction of Drainage Canal (portion) of Sitio Haligionan Road, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 3210219.03 |  | 3210219.03 | 3178201.55 |  | 3178201.55 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 17) Improvement of Drainage Canal of Road at Sitio Tampoy and Sitio Santolan, Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 1325667.29 |  | 1325667.29 | 1312359.42 |  | 1312359.42 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 18) Asphalt Overlaying/Improvement of Drainage Canal at Alejo St., Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 2091534.47 |  | 2091534.47 | 2070399.4 |  | 2070399.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 19) Asphalt Overlaying/Improvement of Drainage Canal at Alvarez St., Brgy. Rizal, Baras, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 2481579.69 |  | 2481579.69 | 2456570.21 |  | 2456570.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 20) Construction of Artesian Wells & Dismantling of Elevated Steel Water Tanks & Removal of Pump Cage at Cardona & Antipolo City, Rizal; a) Construction of 2-units Artesian Well at Catalino Salazar National High School (Senior High School), Brgy. Subay, Cardona, b) Dismantling of 2,000gals Capacity Elevated Steel Water Tank & Removal of Pump Cage at Sambaville, Brgy. San Luis, Antipolo City, c) Dismantling of 2,000gals Capacity Elevated Steel Water Tank at Purok Silangan, Brgy. Dela Paz, Antipolo City | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 76 | GF | 743775.26 |  | 743775.26 | 735784.66 |  | 735784.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 21) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Purok 6, Brgy. Palaypalay, Jalajala, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 76 | GF | 2803009.73 |  | 2803009.73 | 2774966.38 |  | 2774966.38 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 22) Construction of Double Barrel Box Culvert at Luna St., Sitio Ik-Ik, Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 70 | GF | 997578.29 |  | 997578.29 | 987376.39 |  | 987376.39 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 23) Construction of Stone Masonry for Slope Protection of Creek at Purok 5, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 100 | GF | 2783855.18 |  | 2783855.18 | 2755674.96 |  | 2755674.96 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 24) Construction of Drainage Canal at M. Bellin St., Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 90 | GF | 2148012.8 |  | 2148012.8 | 2128591.33 |  | 2128591.33 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 25) Concrete Reblocking (portion) of Pag-Asa St., Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 100 | GF | 2163349.69 |  | 2163349.69 | 2143585.58 |  | 2143585.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 26) Improvement/Construction of Drainage Canal at Sitio Matagbak Feeder Road going to Sagbat Pililla Diversion Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 869951.37 |  | 869951.37 | 860861.81 |  | 860861.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 27) Concreting of Road at RJL, Sitio Bolo-Bolo, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 70 | GF | 2192083.22 |  | 2192083.22 | 2172110.08 |  | 2172110.08 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 28) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Dela Costa Homes V., Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 70 | PDRRMF | 807397.8 |  | 807397.8 | 799356.87 |  | 799356.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 29) Improvement / Construction of Drainage Canal (portion) of Balagbag Road, Sitio Balagbag, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 162 | GF | 5935538.4 |  | 5935538.4 | 5875610.01 |  | 5875610.01 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 30) Improvement of Ynares Multi-Purpose Covered Court and Construction of Fence at Celina Homes 4 Subd., Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 70 | GF | 1409618.25 |  | 1409618.25 | 1395865.85 |  | 1395865.85 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 31) Rehabilitation/Concreting of Fleur de Liz St., Modesta Village, Brgy. Sto. Niňo, San Mateo, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 100 | TF | 1739658.84 |  | 1739658.84 | 1721029.86 |  | 1721029.86 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 32) Concreting (portion) of Old Tuluan Road, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 72 | GF | 1155143.21 |  | 1155143.21 | 1143638.5 |  | 1143638.5 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 33) Construction of Drainage Canal (portion) of Balayong St., Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 60 | GF | 966053.65 |  | 966053.65 | 955568.53 |  | 955568.53 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 34) Improvement/Construction of Drainage Canal (portion) of M.L. Quezon St., Brgy. Kaybuto, Tanay, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 2048199.81 |  | 2048199.81 | 2027152.54 |  | 2027152.54 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 35) Improvement of Road and Drainage Canal at Nangka St., Brgy. Pinagkamaligan, Tanay, Rizal | PEO |  | Public Bidding |  | 15 - 21 Nov 2019 | 2019-11-21 |  | 2019-12-05 | 2019-12-09 | 2019-12-16 |  | 2019-12-20 | 2019-12-26 | 2020-01-09 | 80 | GF | 2134497.94 |  | 2134497.94 | 2113491.2 |  | 2113491.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-15 |  | 2019-11-15
| 1) Construction of Drainage Canal & Improvement of Concrete Cross Canal of Various Road at Brgy. San Luis, Antipolo City; a) Construction of Drainage Canal along Alley 3,4 and 5 at Peace Village 2, Brgy. San Luis, b) Improvement of Concrete Cross Canal at Various Road Intersection at Peace Village 2, Brgy. San Luis | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 68 | GF | 914907.19 |  | 914907.19 | 905424.71 |  | 905424.71 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 2) Construction of Fence & Concreting of Ground of Ynares Multi-Purpose Building & Repair / Improvement of Flooring of Ynares Multi-Purpose Covered Court at Brgy. Kalayaan & Brgy. Mahabang Parang, Angono, Rizal; a) Construction of Fence & Concreting of Ground of 1-storey Ynares Multi-Purpose Building (Daycare Center) at Rainbow Village 1, Brgy. Kalayaan, b) Repair / Improvement of Flooring of Ynares Multi-Purpose Covered Court at Grandvalley Subd., Phase III, Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 68 | GF | 1017380.28 |  | 1017380.28 | 1007203.13 |  | 1007203.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 3) Repair/Improvement of 1-storey Ynares Multi-Purpose Building (Barangay Hall) at Brgy. Tabon, Binangonan, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 657527.67 |  | 657527.67 | 650548.04 |  | 650548.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 4) Construction of Covered Pathwalk at at Sapang Elem. School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 68 | SEF | 1448870.45 |  | 1448870.45 | 1433610.82 |  | 1433610.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 5) Construction of Covered Pathwalk at Binangonan Elem. School, Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 68 | SEF | 2897743.99 |  | 2897743.99 | 2868741.39 |  | 2868741.39 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 6) Repair/Repainting of Various School Building at Libis Elem. School, Brgy. Libis, Binangonan, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 1310976.58 |  | 1310976.58 | 1297958.62 |  | 1297958.62 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 7) Concreting of Road leading to Municipal Jail, Sitio Bunot, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | GF | 1409012.07 |  | 1409012.07 |  |  | cancelled | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Karangalan Village, Phase 1C, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | PDRRMF | 796992.96 |  | 796992.96 | 788367.36 |  | 788367.36 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 9) Improvement/Construction of Drainage Canal & Concrete Overlaying (portion) of A. Ferrera St., Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 1348177.75 |  | 1348177.75 | 1334996.04 |  | 1334996.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 10) Concrete Reblocking (portion) of J. Luna St., Sitio Ik-Ik, Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 3150161.88 |  | 3150161.88 | 3119456.34 |  | 3119456.34 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 11) Concreting of Jacinto St. Ext. (Escarmosa Compound), Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 72 | GF | 895329.52 |  | 895329.52 | 886321.09 |  | 886321.09 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 12) Improvement/Repair of Ynares Multi-Purpose Covered Courts at Brgy. CCL, Morong, Rizal; a) Improvement / Repair of Ynares Multi-Purpose Covered Court at Sitio Calero, Brgy. CCL, b) Repair of Ynares Multi-Purpose Covered Court at Sitio Lanang, Brgy. CCL | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 1502160.71 |  | 1502160.71 | 1485870.84 |  | 1485870.84 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 13) Repair/Repainting of Ynares Multi-Purpose Covered Court and Improvement of Stage at Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 68 | GF | 706873.78 |  | 706873.78 | 699657.24 |  | 699657.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 14) Construction of Perimeter Fence at Virgilio B. Melendres Mem. Elem. School, Brgy. Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 96 | SEF | 3100190.65 |  | 3100190.65 | 3070301.55 |  | 3070301.55 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 15) Construction of Double Box Culvert at T. Daria St. (Batlag Creek), Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 72 | GF | 1194740.31 |  | 1194740.31 | 1182670.6 |  | 1182670.6 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 16) Concrete Reblocking of Bagumbayan Feeder Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | GF | 1109257.13 |  | 1109257.13 | 1098249.52 |  | 1098249.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 17) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Kasiglahan Village, Phase 1K, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | PDRRMF | 813435.38 |  | 813435.38 | 805278.41 |  | 805278.41 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 18) Construction of Stone Masonry for Slope Protection & Concreting of Road at Spillway 1,2,3 & 4, Mascap River, Brgy. Mascap, Rodriguez, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 180 | GF | 3771539.8 |  | 3771539.8 | 3734038.64 |  | 3734038.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 19) Construction of Spillway at Puray River Sitio Mabolo to Sitio Bagong Silang, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 92 | GF | 2831989.78 |  | 2831989.78 | 2803925.52 |  | 2803925.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 20) Repair/Improvement of Ynares School Building, Ynares Stage & Perimeter Fence at Catmon Elem. School, Brgy. San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 973021.24 |  | 973021.24 | 963012.73 |  | 963012.73 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 21) Rehabilitation/Concreting of Road Lot 2 at Graceland Subd., Brgy. Ampid 2, San Mateo, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 1360750.49 |  | 1360750.49 | 1346242.87 |  | 1346242.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 22) Rehabilitation/Concreting of Road Lot 6 at Graceland Subd., Brgy. Ampid 2, San Mateo, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 682506.14 |  | 682506.14 | 674980.83 |  | 674980.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 23) Improvement/Repair of Ynares Multi-Purpose Covered Court at Brgy. Dulong Bayan II, San Mateo, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 140 | GF | 4379470.36 |  | 4379470.36 | 4334914.81 |  | 4334914.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 24) Repair of Fence at Sampaloc Elem. School, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 731043.93 |  | 731043.93 | 724675.79 |  | 724675.79 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 25) Installation of Solar Streetlights at Ipil-Ipil, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 2139795.68 |  | 2139795.68 | 1925822.35 |  | 1925822.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 26) Construction of Drainage Canal (portion) of Yujuico St., Brgy. Tabing Ilog, Tanay, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 72 | GF | 891485.74 |  | 891485.74 | 882574.57 |  | 882574.57 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 27) Concreting of School Ground and Construction of Drainage Canal at Pantay National High School, Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | SEF | 1139559.8 |  | 1139559.8 | 1127594.8 |  | 1127594.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 28) Concreting /Upgrading & Construction of Drainage Canal (portion) of Jose M. Cruz St., Brgy. San Roque, Teresa, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 928509.34 |  | 928509.34 | 917914.49 |  | 917914.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 29) Construction of Perimeter Fence at Pantay National High School, Sitio Pantay, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | SEF | 1437818.58 |  | 1437818.58 | 1422830.55 |  | 1422830.55 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 30) Construction of Water System Level II at Abuyod Senior High School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 19 - 25 Nov 2019 | 2019-11-26 |  | 2019-12-10 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 130 | GF | 2299750.88 |  | 2299750.88 | 2276805.47 |  | 2276805.47 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-19 |  | 2019-11-19
| 1) Repair/Repainting of Ynares Multi-Purpose Covered Court & 1-storey Ynares Multi-Purpose Building at Valley View Executive Village, Phase 1, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 687219.75 |  | 687219.75 | 680276.74 |  | 680276.74 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 2) Repair/Repainting of Ynares School Buildings at Angono Elem. School, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 90 | GF | 1784333.81 |  | 1784333.81 | 1766078.4 |  | 1766078.4 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 3) Construction of Fence (Road Barrier) at Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 52 | GF | 647054.43 |  | 647054.43 | 640673.62 |  | 640673.62 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 4) Improvement of Ynares Multi-Purpose Covered Court at Pinagdilawan Elem. School, Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 40 | GF | 455418.22 |  | 455418.22 | 450318.64 |  | 450318.64 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 5) Repair/Repainting of Ynares Multi-Purpose Covered Court & Ynares Multi-Purpose Building at Brgy. Calumpang & Brgy. Pantok, Binangonan, Rizal; a) Repair / Repainting of Ynares Multi-Purpose Covered Court at Brgy. Calumpang, b) Repair / Repainting of 2-units, 1-storey Ynares Multi-Purpose Building at Ynares Village, Brgy. Pantok | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 957867.51 |  | 957867.51 | 947788.58 |  | 947788.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 6) Improvement/Repair/Repainting of Ynares Multi-Purpose Buildings & Construction of Fence at Brgy. San Andres, Brgy. Sto. Domingo & Brgy. San Isidro, Cainta, Rizal; a) Improvement/Repair/Repainting of 2-storey Multi-Purpose Bldg. at Summergreen Executive Village, Brgy. San Andres, Cainta, Rizal, b) Improvement of 2-storey Ynares Multi-Purpose Building (Senior Citizens's Office) at Zone 5, Greenpark Village, Brgy. Sto. Domingo, c) Construction of Fence at Senior Citizen's Office and Mini-Park, Park Place Executive Village, Brgy. San Isidro | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 717103.08 |  | 717103.08 | 709089.17 |  | 709089.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 7) Improvement of 2-storey Ynares Multi-Purpose Building at Palmera Hills VI, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 40 | GF | 560430.99 |  | 560430.99 | 553410.49 |  | 553410.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 8) Repair/Repainting of Multi-Purpose Building & Construction of Artesian Well at Baras & Pililla, Rizal; a) Repair/Repainting of 1-storey Multi-Purpose Building (Daycare Center) at Brgy. Santiago, Baras, b) Construction of one (1)-unit Artesian Well at Sitio Malindig, Brgy. Bagumbayan, Pililla | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 48 | GF | 518812.64 |  | 518812.64 | 513716.94 |  | 513716.94 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 9) Repair/Repainting of Ynares Multi-Purpose Covered Court, Stage & Fence at Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 1073692.98 |  | 1073692.98 | 1063083.69 |  | 1063083.69 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 10) Repair/Repainting of 2-storey, 6-rooms Ynares School Building at Subay Elem. School, Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 64 | SEF | 500297.56 |  | 500297.56 | 494637.26 |  | 494637.26 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 11) Improvement / Repair / Repainting of Ynares Multi-Purpose Bldg. & Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Baras & Morong, Rizal; a) Improvement / Repair of 2-storey Ynares Multi-Purpose Bldg. (Barangay Hall) at Brgy. Concepcion, Baras, b) Repair / Improvement of 1-storey Ynares Multi-Purpose Bldg. (Barangay Hall) at Brgy. Santiago, c) Installation of Electronic Scoreboard at Ynares Multi-Purpose Covered Court, Sitio Lagim, Brgy. San Jose, Morong | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 64 | GF | 846494.48 |  | 846494.48 | 838221.13 |  | 838221.13 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 12) Construction of Drainage Canal at Rodriguez St., Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 82 | GF | 894543.42 |  | 894543.42 | 886252.16 |  | 886252.16 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 13) Construction of Fence at Palaypalay Elem. School, Brgy. Palaypalay, Jalajala, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | SEF | 1399707.1 |  | 1399707.1 | 1385688.88 |  | 1385688.88 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 14) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 82 | GF | 1545293.41 |  | 1545293.41 | 1529243.35 |  | 1529243.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 15) Construction of Deepwell with Pump, Motor & Pump House at San Guillermo Elem. School, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 128 | GF | 1608631.33 |  | 1608631.33 | 1592613.35 |  | 1592613.35 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 16) Construction of Ynares Stage at Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 96 | GF | 1098454.37 |  | 1098454.37 | 1087223.3 |  | 1087223.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 17) Concreting of Natividad St. Extension (Daang Bangka) with Side Protection at Sitio Ibaba, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 120 | GF | 3012554.69 |  | 3012554.69 | 2981574.17 |  | 2981574.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 18) Installation of Solar Streetlights at Calasiao Feeder Road (Martinez St.) at Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 52 | GF | 912811.21 |  | 912811.21 | 902928.34 |  | 902928.34 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 19) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court & Construction of Fence of Ynares Multi-Purpose Building at Brgy. Bagumbayan & Brgy. Takungan, Pililla, Rizal; a) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Bagumbayan, b) Construction of Fence of Ynares Multi-Purpose Building at Brgy. Takungan | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 52 | GF | 605503.85 |  | 605503.85 | 599354.49 |  | 599354.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 20) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Imatong, Pililla, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 64 | GF | 878846.03 |  | 878846.03 | 870758.57 |  | 870758.57 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 21) Improvement / Construction of Drainage Canal at Brgy. Bagumbayan & Brgy. Malaya, Pililla, Rizal; a) Constuction of Drainage Canal at Sitio Matilos to Sitio Calasiao, Brgy. Bagumbayan, b) Construction of Drainage Canal at Estrella St., Brgy. Malaya | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 72 | GF | 768129.21 |  | 768129.21 | 760042.52 |  | 760042.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 22) Concreting of Roads at Avila Compound, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 120 | GF | 2154675.4 |  | 2154675.4 | 2132675.2 |  | 2132675.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 23) Concreting of Road at Sitio Masikap, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 100 | GF | 2018292.75 |  | 2018292.75 | 1998104.83 |  | 1998104.83 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 24) Construction of Stone Masonry for Slope Protection (portion) at Mascap River Mascap Proper, Brgy. Mascap, Rodriguez, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 180 | GF | 6022269.9 |  | 6022269.9 | 5958658.67 |  | 5958658.67 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 25) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at King David Subd., Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | PDRRMF | 807397.8 |  | 807397.8 | 799356.87 |  | 799356.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 26) Construction / Provision of Wash Facilities (Water, Sanitation & Hygiene) for Evacuation Center at Montavilla Subd., Phase 2, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | PDRRMF | 807397.8 |  | 807397.8 | 799448.74 |  | 799448.74 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 27) Repainting/Repair of Ynares Multi-Purpose Covered Court & Movable Bench at Justice Vicente Santiago Elem. School, Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 40 | GF | 515044.41 |  | 515044.41 | 508621.8 |  | 508621.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 28) Rehabilitation / Concreting of Road Lot 4 & Road Lot 5 at Graceland Subd., Brgy. Ampid 2, San Mateo, Rizal; a) Rehabilitation / Concreting of Road Lot 4 at Graceland Subd., Brgy. Ampid 2, b) Rehabilitation / Concreting of Road Lot 5 at Graceland Subd., Brgy. Ampid 2 | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 1262495.3 |  | 1262495.3 | 1249668.51 |  | 1249668.51 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 29) Improvement / Repainting of Fence & Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. Wawa & Brgy. San Isidro, Tanay, Rizal; a) Improvement / Repainting of Fence at Tanay West National High School, Brgy. Wawa, b) Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Brgy. San Isidro | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | SEF | 844789.77 |  | 844789.77 | 835211.27 |  | 835211.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 30) Installation of Electronic Scoreboard & Construction of Movable Bleacher of Ynares Multi-Purpose Covered Court at Brgy. May-Iba & Brgy. Prinza, Teresa, Rizal; a) Installation of Electronic Scoreboard of Ynares Multi-Purpose Covered Court at Brgy. May-Iba, b) Construction of Movable Bleacher of Ynares Multi-Purpose Covered Court at Prinza Elem. School, Brgy. Prinza | PEO |  | Public Bidding |  | 22 - 28 Nov 2019 | 2019-11-28 |  | 2019-12-12 | 2019-12-16 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 40 | GF | 625644.5 |  | 625644.5 | 619211.68 |  | 619211.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-22 |  | 2019-11-22
| 1) Installation of Solar Streetlights at Southville 9, Antipolo City | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 4946237.64 |  | 4946237.64 | 0 |  |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 2) Rehabilitation/Concreting of Carnation St., Nieves Hills Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 1740872.04 |  | 1740872.04 | 1722856.3 |  | 1722856.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 3) Improvement/Construction of Drainage Canal at Ilang-Ilang St., Nieves Hills Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 108 | GF | 3925014.85 |  | 3925014.85 | 3885200.68 |  | 3885200.68 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 4) Improvement of Ynares Multi-Purpose Covered Court at Tanay North National High School, Sitio Dalawang Kawayan, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 56 | SEF | 945016.26 |  | 945016.26 | 934619.71 |  | 934619.71 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 5) Improvement of Streetlights at Rizal St. & Ynares St., Sampaguita St. & Bonifacio St., Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 70 | GF | 3179553.16 |  | 3179553.16 | 3149037.07 |  | 3149037.07 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 6) Construction of Concrete Bleacher & Improvement / Repair of Ynares Multi-Purpose Covered Court at Brgy. Tayuman, Binangonan, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 92 | GF | 2071847.59 |  | 2071847.59 | 2055694.23 |  | 2055694.23 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 7) Elevated Parking Area at Bayanihan Subdivision, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 120 | GF | 2799891.71 |  | 2799891.71 | 2771501.97 |  | 2771501.97 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 8) Improvement/Concreting of Road 3, San Lorenzo Ruiz, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 120 | GF | 5135123.04 |  | 5135123.04 | 5090171.89 |  | 5090171.89 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 9) Improvement/Concreting of Road 4, San Lorenzo Ruiz, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 180 | GF | 7468047.76 |  | 7468047.76 | 7403764.82 |  | 7403764.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 10) Improvement/Concreting of Road 6, San Lorenzo Ruiz, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 160 | GF | 6740404.1 |  | 6740404.1 | 6680958.18 |  | 6680958.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 11) Repair of Roofdeck & Steel Tower of Rizal Provincial Jail, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 2433555.69 |  | 2433555.69 | 2412803.71 |  | 2412803.71 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 12) Concrete Reblocking of Bernardino St., Sitio Tabing-Ilog, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 100 | GF | 2713570.89 |  | 2713570.89 | 2686474.57 |  | 2686474.57 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 13) Rehabilitation/Concreting & Asphalt Overlaying of Road at Sitio Bulacan 1, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 2953674.38 |  | 2953674.38 | 2924551.27 |  | 2924551.27 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 14) Asphalt Overlaying/Concrete Reblocking of Road at Sitio Bulacan II, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 80 | GF | 4132078.62 |  | 4132078.62 | 4091380.34 |  | 4091380.34 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 15) Asphalt Overlay & Concrete Reblocking of G. Dikit Ext., Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 60 | GF | 2199070.64 |  | 2199070.64 | 2177063.02 |  | 2177063.02 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 16) Construction of Bridge traversing Bautista Creekside Brgy. San Isidro to Sub-Urban Village Phase I, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 220 | TF | 13092808.65 |  | 13092808.65 | 12979443.52 |  | 12979443.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 17) Repair / Repainting / Improvement of 3-storey, 40-rooms School Building at Kasiglahan Village National High School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 140 | GF | 11134321 |  | 11134321 | 11023215.82 |  | 11023215.82 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 18) Construction of Stone Masonry Slope Protection at Mascap River Sitio Kislatan, Brgy. Mascap, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 240 | GF | 10688304.86 |  | 10688304.86 | 10583442.14 |  | 10583442.14 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 19) Construction of Stone Masonry for Slope Protection at Bulubok River and Mango River (Daang Tubo (portion) Brgy. Burgos and Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 240 | GF | 13983681.75 |  | 13983681.75 | 13862920.1 |  | 13862920.1 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 20) Construction of Stone Masonry for Slope Protection at Banay River, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26 Nov - 2 Dec 2019 | 2019-12-02 |  | 2019-12-13 | 2019-12-17 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 208 | GF | 8383169.15 |  | 8383169.15 | 8300056.65 |  | 8300056.65 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-26 |  | 2019-11-26
| 1. Construction of Jail Building for Bureau of Jail Management & Penology (Teresa Disrict Jail) at Sitio Pantay, Brgy. Dalig, Teresa, Rizaly | PEO |  | Public Bidding |  | 27 Nov - 3 Dec 2019 | 2019-12-03 |  | 2019-12-16 | 2019-12-18 | 2019-12-23 |  | 2019-12-27 | 2020-01-02 | 2020-01-09 | 320 | GF | 35915081.78 |  | 35915081.78 | 35615001.8 |  | 35615001.8 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2019-11-27 |  | 2019-11-27
Total Alloted Budget of On-going Procurement Activities | [17 empty] | 370994129.21 |  | 370994129.21 | 360916037.97 |  | 360916037.97
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | MA. TERESA E. LASQUETY | [12 empty] | Engr. LUISITO G. MUNSOD | [8 empty] | Dr. REYNALDO H. SAN JUAN, Jr., M.D.
|  | (Sgd) Head - BAC Secretariat | [12 empty] | (Sgd) BAC Chairperson | [8 empty] | (Sgd) Acting Governor