## PMR 2021
PROCUREMENT MONITORING REPORT (FIRST SEMESTER 2021)
RIZAL PROVINCIAL GOVERNMENT
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [12 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
3000-000-1-2-11-399-006-001 | 1) Repair/Repainting of Ynares School Buildings and Ynares Multi-Purpose Covered Court at Regional Lead School for the Arts of Angono, Brgy. San Isidro, Angono, Rizal a) Repair/Repainting of Ynares School Buildings at Regional Lead School for the Arts of Angono, Brgy. San Isidro | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 90 |  | SEF | 1996309.67 | 1635430.34 |  | 1984031.79 | 1628777.2 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-11-399-006-002 | b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Regional Lead School for the Arts of Angono,Brgy. San Isidro | [18 empty] | 360879.33 |  |  | 355254.59
3000-300-1-2-11-311-004-021 | 2) Construction of 2-Storey Ynares Multi-Purpose Building (Senior Citizen’s Building) at Medalva Hills Village, Phase II, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 136 |  | GF | 3710698.03 | 3710698.03 |  | 3691979.2 | 3691979.2 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-31-392-004-006 | 3) Repair/Rehabilitation of Ynares Multi-Purpose Covered Court at Peace Village Phase 3, Brgy. San Luis, Antipolo City a) Repainting of Ynares Multi-Purpose Covered Court at Peace Village Phase 3, Brgy. San Luis | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 45 |  | GF | 857551.88 | 505950.52 |  | 846561.94 | 503731.38 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-31-392-004-007 | b) Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Peace Village, Phase 3, Brgy. San Luis | [19 empty] | 351601.36 |  |  | 342830.56
3000-000-1-1-31-392-004-008 | 4) Construction of 17x30 m. Ynares Multi-Purpose Covered Court (Rafter Type) at Sitio Tagumpay, Brgy. Bagong Nayon, Antipolo City | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 148 |  | GF | 4345912.93 |  | 4345912.93 | 4326032.47 |  | 4326032.47 | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-400-1-1-11-005-001 | 5) Constriction/Provision of Wash Facilities (Water Sanitation & Hygiene) at Maries II Ph. I, Brgy. Mayamot, Antipolo City | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 64 |  | GF | 938478.09 | 938478.09 |  | 926585.37 | 926585.37 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-014 | 6) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Kaytome, Binangonan, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Cpurt, Brgy. Kaytome | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 64 |  | GF | 1209692.31 | 936877.89 |  | 1196552.34 | 926624.46 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-015 | b) Improvement of Ynares Multi-Purpose Covered Court, Brgy. Kaytome | [19 empty] | 272814.42 |  |  | 269927.88
3000-000-1-2-11-399-006-010 | 7) Repair/Repainting of Ynares School Buildings at Mabuhay Homes 2000 Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 90 |  | SEF | 5509400.17 | 5509400.17 |  | 5484415.96 | 5484415.96 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-51-004-005 | 8) Construction of 3-Seater Comfort Room with Urinal at Ynares Village, Brgy. Pantok, Binangonan, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 40 |  | GF | 819253.13 |  | 819253.13 | 809245.2 |  | 809245.2 | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-0110 | 9) Repair/Repainting of Ynares Multi-Purpose Covered Court, Ynares Multi-Purpose Building and Perimeter Fence at Brgy. Pag-Asa, Binangonan, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court, Brgy. Pag-Asa | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 45 |  | GF | 879243.06 | 413103.3 |  | 866149.21 | 408586.2 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-511-004-060 | b) Repair/Repainting of Ynares Multi-Purpose Building, Brgy. Pag-Asa | [18 empty] | 173688.1 |  |  | 169109.38
3000-300-1-2-11-511-004-061 | c) Repair/Repainting of Perimeter Fence, Brgy. Pag-Asa | [18 empty] | 292451.66 |  |  | 288453.63
3000-000-1-2-11-399-006-006 | 10) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Tatala Elem. School, Brgy. Tatala, Binangonan, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Tatala Elem. School, Brgy. Tatala | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 56 |  | SEF | 997757.13 | 609011.04 |  | 983956.43 | 603037.54 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-11-399-006-007 | b) Improvement of Ynares Multi-Purpose Covered Court at Tatala Elem. School, Brgy. Tatala | [19 empty] | 388746.09 |  |  | 380918.89
3000-000-1-1-31-392-004-017 | 11) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Kinagatan, Binangonan, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court, Brgy. Kinagatan | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 60 |  | GF | 1731947.44 | 1032101.32 |  | 694820.04 |  | 1022214.6 | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-016 | b) Improvement of Ynares Multi-Purpose Covered Court, Brgy. Kinagatan | [19 empty] | 699846.12 |  |  | 694820.04
3000-000-1-2-11-399-006-014 | 12) Construction of 10x24 m. Ynares Multi-Purpose Covered Court and Ynares Stage at Baras Senior High School, Sitio Ibabaw, Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 120 |  | SEF | 3540341.25 |  | 3540341.25 | 3524257.5 |  | 3524257.5 | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-11-399-006-015 | 13) Construction of Perimeter Fence and Covered Pathwalk at Pinugay Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 79 |  | SEF | 2546153.35 |  | 2546153.35 | 2530228.89 |  | 2530228.89 | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-11-511-004-016 | 14) Construction of 2-Storey Ynares Multi-Purpose Building at D.M. Subd., Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 60 |  | GF | 3359657.43 |  | 3359657.43 | 3337217.4 |  | 3337217.4 | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-022 | 15) Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Andres, Cainta, Rizal a) Repainting of Ynares Multi-Purpose Covered Court at Greenwood Exec. Village, Area 8, Brgy. San Andres | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 60 |  | GF | 1275958.21 | 343959.39 |  | 1262868.66 | 339493.25 |  | Engr. NELSON PAJARILLO | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-021 | b) Improvement of Ynares Multi-Purpose Covered Court at Greenwood Exec. Village, Area 8, Brgy. San Andres | [19 empty] | 931998.82 |  |  | 923375.41
3000-000-1-2-11-399-006-027 | 16) Repair/Repainting of School Buildings at Boor Barrio Elem. School, Brgy. Boor, Cardona, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 60 |  | SEF | 2206695.36 | 2206695.36 |  | 2192781.11 | 2192781.11 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
8000-000-1-2-501-001-005-021 | 17) Improvement of Cardona Diversion Road, Cardona, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 120 |  | GF | 9999994.28 |  | 9999994.28 | 9944144.09 |  | 9944144.09 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-1-31-392-040-026 | 18) Construction of Ynares Stage and Improvement of Ynares Multi-Purpose Covered Court at Cardona Government and Economic Center, Brgy. San Roque, Cardona, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 168 |  | GF | 3199946.54 |  | 3199946.54 | 3178842.05 |  | 3178842.05 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-51-001-002-028 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of J. Delos Santos St., Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 120 |  | GF | 14971574.13 | 14971574.13 |  | 14886834.1 | 14886834.1 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
8000-000-1-1-51-001-002-026 | 20) Asphalt Overlaying/Concrete Reblocking of Road at Sitio Bagong Silang, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 68 |  | GF | 2686382.15 | 2686382.15 |  | 2670953.81 | 2670953.81 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
9000-900-1-2-40-940-201-001-005 | 21) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok 3, Brgy. Palaypalay, Jalajala, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 88 |  | GF | 2879968.44 |  | 2879968.44 | 2862181.46 |  | 2862181.46 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
8000-000-1-1-51-001-001-002-002-019 | 22) Asphalt Overlaying (portion) of Garrovillas St., Brgy. San Jose, Morong, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 32 |  | GF | 2408508.28 | 2408508.28 |  | 2393374.98 | 2393374.98 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
2000-000-1-1-51-001-002-018 | 23) Improvement/Concreting of Various Roads at Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 80 |  | GF | 2304199.54 |  | 2304199.54 | 2378091.22 |  | 2378091.22 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-400-1-1-11-005-103 | 24) Construction/Provision of Wash Facilities (Water Sanitation & Hygiene) at Malaya National High School, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 64 |  | SEF | 865112.81 |  | 865112.81 | 855102.18 |  | 855102.18 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-511-004-026 | 25) Construction of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Phase 6, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 137 |  | GF | 399996.54 |  | 399996.54 | 3382009.3 |  | 3382009.3 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-511-004-031 | 26) Construction of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Ph4 Block 25, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 147 |  | GF | 3321506.02 |  | 3321506.02 | 3303058.7 |  | 3303058.7 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-511-004-043 | 27) Construction of Ynares Multi-Purpose Building at New San Mateo Subd., Phase 7, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 89 |  | GF | 3049983.73 |  | 3049983.73 | 3029420.5 |  | 3029420.5 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-511-004-046 | 28) Construction of 2-Storey Ynares Multi-Purpose Building & MRF at Cresda Ville 2, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 160 |  | GF | 3049573.26 |  | 3049573.26 | 3033050.81 |  | 3033050.81 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-300-1-2-11-511-004-050 | 29) Construction of Senior Citizen Office/Tribal Hall, Brgy. Sto. Niño, Tanay, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 136 |  | GF | 3458585.93 |  | 3458585.93 | 3437237.76 |  | 3437237.76 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-1-31-392-004-057 | 30) Construction of 17x30m. Ynares Multi-Purpose Covered Court at Carissa Homes East II Subdivision, Brgy. San Gabriel, Teresa, Rizal | PEO |  | Public Bidding |  | 8-14-Jan - 21 | 2021-01-15 |  | 2021-01-27 | 2021-02-02 | 2021-02-12 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-08 | 140 |  | GF | 4126775 |  | 4126775 | 4101339.2 |  | 4101339.2 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-08 | 2021-01-08 | 2021-01-08
3000-000-1-2-11-399-006-001 | 1) Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Angono, Rizal a) Repairing of Ynares Multi-Purpose Coverd Court at Villa Gloria Subd. Brgy. San Isidro b) Improvement of Ynares Multi-Purpose Covered Court at Constellation Homes Subd. Phase 1, Brgy. San Isidro | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 80 |  | GF GF | 846169.12 | 402137.14 | 444031.98 | 834046.36 | 395198.07 | 438848.29 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 1900-01-03 | 2021-01-15
3000-000-1-1-31=392-004-002 | 2) Improvement of Volleyball Court at Grand Valley Subd., Phase 1, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 60 |  | GF | 997710.63 |  | 997710.63 | 982224.14 |  | 982224.14 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-211-399-016-004 | 3) Construction of 2-Storey Ynares Multi-Purpose Building at Dona Justa Guido Mem. School, Brgy., San Roque, Angono, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 160 |  | SEF | 2798128.69 |  | 2798128.69 | 2778080.21 |  | 2778080.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-511-004-003 | 4) Construction of 2-Storey Ynares Multi-Purpose (Senior Citizen’s Building) at Valley view Executive Village Phase 1, Brgy. Mayamot, Antipolo, City. | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 160 |  | GF | 3528697.34 |  | 3528697.34 | 3506531.55 |  | 3506531.55 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-392-004-009 | 5) Improvement of Ynares Multi-Purpose Covered Court at Singcalan, Brgay. San Roque, Antipolo, City | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 60 |  | GF | 937587.01 |  | 937587.01 | 925721.17 |  | 925721.17 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-392-004-005 | 6) Repair/Repainting of Multi-Purpose Covered Court at Maries Village II, Phase I, Brgy Mayamot, Antipolo, City | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 54 |  | GF | 1260902.83 | 1260902.83 |  | 1246841.2 | 1246841.2 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-300-1-2-11-511-004-006 3000-300-1-2-11-511-004-004 | 7) Repair/Repainting of Multi-Purpose Building and Construction of Fence at Victoriaville Homes, Upper Lucban, Brgy. Sta. Cruz, Antipolo, City. a) Repair/Repainting of 1-Storey Multi-Purpose Building at Victoriaville Homes, Upper Lucban, Brgy. Sta. Cruz b) Construction of Fence at Victoriaville Homes, Upper Lucban, Brgy. Sta. Cruz | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 60 |  | GF GF | 996209.17 | 147776.92 | 848432.25 | 983397.62 | 144233.18 | 839164.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-392-004-011 3000-000-1-1-31-392-004-012 | 8) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Ynares Village II, Brgy. Pantok Binangonan. Rizal. a) Repair/Repainting Ynares Multi-Purpose Covered Court at Ynares Village, Brgy. Pantok b) Improvement of Ynares Multi-Purpose Covered Court at Ynares Village II, Brgy. Pantok | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 70 |  | GF | 1236821.07 | 969602.32 | 267218.75 | 1222954.65 | 956804.07 | 266150.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-392-004-013 | 9) Repair/Repainting of Ynares Multi-Purpose Covered Court, Brgy. Bombong, Binangonan, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 60 |  | GF | 646034.36 | 646034.36 |  | 635980.41 | 635980.41 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2-11-399-006-017 3000-000-1-2-11-399-006-016 | 10) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Repair/Repainting of Stage at at Pinugay Elem. School, Brgy. Pinugay Baras, Rizal a) Repair/Repainting Ynares Multi-Purpose Covered Court and Stage at Brgy. Pinugay Elem. School. Brgy. Pinugay b) Improvement of Ynares Multi-Purpose Covered Court at Pinugay Elem. School. Brgy. Pinugay | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 40 |  | SEF SEF | 970066.07 | 382982.97 | 587083.1 | 956054.74 | 376025.3 | 580029.44 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-392-004-018 3000-000-1-1-31-392-004-019 | 11) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Repair/Repainting of Ynares Stage at Habitat Ynares Village, Brgy.Brgy. Pinugay Baras, Rizal a) Repair/Repainting Ynares Multi-Purpose Covered Court and Ynares Stage at Habitat Village, Brgy. Pinugay b) Improvement of Ynares Multi-Purpose Covered Court at Habitat Ynares Village Brgy. Pinugay | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 70 |  | GF | 1092157.08 | 689952.35 | 402204.73 | 1075064.72 | 677647.81 | 397416.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-31-392-004-023 | 12) Improvement of Ynares Multi-Purpose Covered Court and Construction of Stage at Adelina Homes, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 80 |  | GF | 2751571.06 |  | 2751571.06 | 2734620.56 |  | 2734620.56 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-1-31-399-006-024 | 13) Construction of 8x24m Ynares Multi-Purpose Covered Court and Stage at Francisco P. Felix Mem. National High School, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 120 |  | SEF | 2986039.09 |  | 2986039.09 | 2968021.63 |  | 2968021.63 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-300-1-2-11-511-004-019 | 14) Rehabilitation of Existing Stage, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 84 |  | GF | 2036984.74 |  | 2036984.74 | 2023349.52 |  | 2023349.52 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2-11-399-006-026 | 15) Improvement of Ynares Multi-Purpose Covered Court at Dalig Elem. School. Brgy. Dalig, Cardona. Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 76 |  | SEF | 1221497.3 |  | 1221497.3 | 1209326.24 |  | 1209326.24 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2—11-399-006-066 | 16) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Pagkalinawan Elem. School, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | SEF | 942270.32 |  | 942270.32 | 928288.49 |  | 928288.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2—11-399-006-065 | 17) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Punta Elem. School, Brgy. Punta, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | SEF | 972764.94 |  | 972764.94 | 959734.04 |  | 959734.04 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2—11-399-006-064 | 18) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Lubo Elem. School, Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | SEF | 970927.44 |  | 970927.44 | 958644.66 |  | 958644.66 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2—11-399-006-063 | 19) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Palaypalay, Elem. School, Brgy. Palaypalay, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | SEF | 968302.44 |  | 968302.44 | 954997.87 |  | 954997.87 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2—11-399-006-062 | 20) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bagumbong National High School, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | SEF | 968302.44 |  | 968302.44 | 955279.39 |  | 955279.39 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
9000-900-1-2—40-920-001-001-009 | 21) Construction of Stone Masonry for Slope Protection (portion) of Tambongco Creek, Sitio Tambongco, Brgy. San Guillermo, Morong, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 60 |  | GF | 1196404.25 |  | 1196404.25 | 1181531.91 |  | 1181531.91 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2—11-391-006-032 | 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) Virgilio Melendres Mem. Elem. School, Brgy.Takungan, Pililla, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | SEF | 961826.55 |  | 961826.55 | 949751.49 |  | 949751.49 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-400-1-1—11-005-003 | 23) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Sitio Libis,Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 64 |  | GF | 948370.48 |  | 948370.48 | 934194.88 |  | 934194.88 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2-11-399-006-036 3000-000-1-2-11-399-006-035 | 24) Repair & Improvement of Ynares Multi-Purpose Covered Court at Montalban Heights National High School, Brgy. San Jose, Rodriguez, Rizal a) Repair of Ynares Multi-Purpose Covered Court at Montalban Heights National High School, Brgy. San Jose b) Improvement of Ynares Multi-Purpose Covered Court at Montalban Heights National High School, Brgy. San Jose | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 106 |  | SEF | 2980935.98 | 212423.97 | 2768512.01 | 2962700.28 | 209422.07 | 2753278.21 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-300-1-2-11-511-004-021 | 25) Repair/Repainting Ynares Multi-Purpose Covered Court and Ynares Multi-Purpose Building at Montavilla 2 Subdivision, Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 72 |  | GF | 1686214.65 | 1686214.65 |  | 1672230.58 |  | 1672230.58 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-300-1-2-11-511-004-044 | 26) Repair of 3-Units Multi-Purpose Building, Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 170 |  | GF | 3469822.06 | 3469822.06 |  | 3449628.52 | 3449628.52 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-300-1-2-31-392-004-043 | 27) Repair of Ynares Multi-Purpose Covered Court at Bankers Village V, Phase 1, Brgy. Guitnang Bayan 1, San Mateo, Rizal. | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 192 |  | GF | 1692486.52 | 1692486.52 |  | 1678228.05 | 1678228.05 |  | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
8000-000-1-1-51-003-018 | 28) Improvement/Concreting of Road at Block 11, Purok 7 at Lupang Arenda, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 100 |  | GF | 3547743.4 |  | 3547743.4 | 3525758.28 |  | 3525758.28 | Engr. NELSON A. PAJARILLO & Engr. EDGARDO F. BALAJADIA | 2021-01-15 | 2021-01-15 | 2021-01-15
8000-000-1-1-51-002-016 | 29) Concreting of Maysawa Road, Brgy. Cuyambay, Tanay, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-24 | 2021-03-22 | 120 |  | GF | 4994345.83 |  | 4994345.83 | 4970203.66 |  | 4970203.66 |  | 2021-01-15 | 2021-01-15 | 2021-01-15
8000-000-1-1-31-392-004-048 | 30) Improvement of Ynares Multi-Purpose Covered Court at Haven for Elderly, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 15-21-Jan-21 | 2021-01-22 |  | 2021-02-04 | 2021-02-10 | 2021-02-19 | 2021-02-24 | 2021-02-26 | 2021-03-03 | 2021-03-22 | 128 |  | GF | 2721685.34 |  | 2721685.34 | 2706203.66 |  | 2706203.66 |  | 2021-01-15 | 2021-01-15 | 2021-01-15
3000-000-1-2-11-399-006-018 | 1) Improvement of 2- storey, 6-rooms Ynares School Bldg. at Evangelista Elem. School, Brgy. Evangelista, Baras, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 45 |  | SEF | 469672.04 |  | 469672.04 | 461965.24 |  | 461965.24 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-1-31-392-004-024 3000-000-1-1-31-392-004-025 | 2) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage and Improvement of Ynares Multi-Purpose Covered court and Fence at Brgy. San Isidro, Cainta, Rizal. a) Repair/ Repainting of Ynares Multi-Purpose Covered Court and Stage at Cainta Greenpark Village, Zone 5, Brgy. San Isidro b) Improvement of Ynares Multi-Purpose Covered Court and Fence at Cainta Greenpark Village, Zone 5, Brgy. San Isidro | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 2162969.62 | 1698217.87 | 464751.75 | 2147454.88 | 1685220.94 | 462233.94 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2-11-511-004-018 | 3) Improvement of Ynares Multi-Purpose Building and Repainting/Improvement of Ynares Multi-Purpose Covered Court & Ynares Stage at Brgy San Isidro & Brgy San Juan, Cainta, Rizal a) Improvement of Ynares Multi-Purpose Building at Cainta Greenpark Village, Zone 4, Brgy. San Isidro. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 177981.91 |  | 177981.91 | 1755872.73 |  | 1755872.73 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2-11-511-004-017 | b) Improvement of Ynares Multi-Purpose Building (Senior Citizen’s Office) at Cainta Greenpark Village, Zone 3, Brgy. San Isidro | [16 empty] | GF |  |  | 177981.91 |  |  | 175872.73
3000-000-1-2-11-399-006-022 | c) Repainting of Ynares Multi-Purpose Covered Court and Ynares Stage at Saint Anthony Elem. School, Brgy. San Juan | [16 empty] | SEF |  | 297970.03 |  |  | 293197.95
3000-300-1-2-11-399-006-023 | d) Improvement of Ynares Multi-Purpose Covered Court at Saint Anthony Elem. School, Brgy. San Juan | [16 empty] | SEF |  |  | 123784.83 |  |  | 122197.95
3000-300-1-2-11-511-004-014 3000-000-1-1-31-392-004-020 | 4) Repair of Senior Citizen’s Hall & Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Andres, Cainta, Rizal. a) Repair of Senior Citizen’s Hall at Sitio Felix Subd., Brgy. San Andres. b) Improvement of Ynares Multi-Purpose Covered Court at DM 1 Subd., Brgy. San Andres | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 60 |  | GF GF | 895056.48 | 133434.87 | 761621.61 | 883456.15 | 128102.91 | 755353.24 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-025 | 5) Rehabilitation and Concreting of School Ground & Improvement of Ynares Multi-Purpose Building at Brgay. Dalig & Brgy.San Roque, Cardona, Rizal a) Rehabilitation and Concreting of School Ground at Dalig Elem. School at Brgy. Dalig | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 60 |  | SEF | 1190503.32 |  | 699312.44 | 1176556.42 |  | 694459.1 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-400-1-1-11-005-002 | b) Improvement of 2- Storey Ynares Multi-Purpose Building (CBDEG Diabetic Center) at Brgy.San Roque | [16 empty] | GF |  |  | 491190.88 |  |  | 482097.32
3000-000-1-1-31-392-004-025 3000-000-1-1-31-392-004-027 | 6) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court Brgy. Balibago, Cardona, Rizal. a) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court Brgy. Balibago. b) Improvement of Ynares Multi-Purpose Covered Court Brgy. Balibago. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 1762288.17 | 827476.48 | 934811.69 | 1746049.59 | 822267.78 | 923781.81 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-1-51-001-002-025 | 7) Concreting (portion) of Farm to Market Road going to VJS Farm, Brgy. Pagkalinawan, Jalajala, Rizal. | PEO |  | Public Bidding | 2020-06-02 | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 64 |  | GF | 1049315.59 |  | 1049315.59 | 1037501 |  | 1037501 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-057 | 8) Construction of Storage Room at Bombongan Elem. School, Brgy. Bombongan, Morong, Rizal | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 60 |  | GF | 517896.83 |  | 517896.83 | 509142.33 |  | 509142.33 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2-11-511-004-053 | 9) Repair/Repainting/Improvement of Ynares Multi-Purpose Building, Brgy. Maybancal, Morong, Rizal. a) Repair of 2-storey Ynares Multi-Purpose Building (Health Center) Brgy. Maybancal. | PEO |  | Public Bidding | 2020-06-02 | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 70 |  | GF | 1011930.25 | 589885.41 |  | 998913.8 | 581814.71 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2-11-511-004-054 | b) Repair/Repainting of 1-storey Ynares Multi-Purpose Building, Brgy. Maybancal. | [18 empty] | 159549.16 |  |  | 156629.41
3000-300-1-2-11-511-004-055 | c) Improvement of 2-storey Ynares Multi-Purpose Building, Brgy. Maybancal. | [19 empty] | 262495.68 |  |  | 260469.68
3000-300-1-2-11-511-004-052 | 10) Repair/Repainting of 3-units, 2-storey Ynares Multi-Purpose Bldg. (Health Center, Brgy. Hall, RICC & BHW Office), Brgy. San Pedro, Morong, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 1047180.54 | 1047180.54 |  | 1032172.1 | 1032172.1 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399- 006-030 | 11) Repair/Repainting of Ynares School Building at Quisao National High School, Brgy. Quisao, Pililla, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 86 |  | SEF | 1554057.79 | 1554057.79 |  | 1539017.2 | 1539017.2 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
8000-000-1-1-51-001-003-013 | 12) Construction/Concreting of Portion of Masantol Feeder Road, at Brgy. Quisao, Pililla, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 80 |  | GF | 2858597.5 |  | 2858597.5 | 2839468.04 |  | 2839468.04 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
8000-000-1-1-51-001-003-011 | 13) Construction/Concreting of Portion of Upper Daria Street, at Brgy. Niogan, Pililla, Rizal | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 60 |  | GF | 1159196.72 |  | 1159196.72 | 1146691.27 |  | 1146691.27 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
8000-000-1-1-51-001-003-012 | 14) Concreting of Portion of E-Tibay Street (Pulo), at Brgy. Wawa, Pililla, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 60 |  | GF | 999688.14 |  | 999688.14 | 987712.94 |  | 987712.94 |  | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-1-31-392-004-029 | 15) Construction/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Niogan & Brgy. Malaya, Pililla, Rizal. a) Construction of Concrete Bleacher of Ynares Multi-Purpose Covered Court, Brgy. Niogan. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 1805633.96 |  | 798593.84 | 1786585.7 |  | 792322.71 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-1-31-392-004-031 | b) Repainting of Ynares Multi-Purpose Covered Court Brgy. Malaya. | [18 empty] | 565778.44 |  |  | 560673.69
3000-000-1-1-31-392-004-030 | c) Improvement of Ynares Multi-Purpose Building, Brgy. Malaya. | [19 empty] | 441261.68 |  |  | 433589.3
3000-300-1-2—11-511-004-038 | 16) Repair/Improvement of Ynares Multi-Purpose Bldg. Brgy. San Rafael, Rodriguez, Rizal. a) Repair of 2-storey Ynares Multi-Purpose Building (VAWC/BCPC Office Clinic, & Senior Citizen’s Office), Brgy. San Rafael. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 80 |  | GF | 1080573.63 | 616422.95 |  | 1067057.85 | 610282.85 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2—11-511-004-039 | b) Repair of 2-storey Ynares Multi-Purpose Building (Lupon & SK Office) Brgy. San Rafael. | [18 empty] | 144179.66 |  |  | 141662.55
3000-300-1-2—11-511-004-040 | c) Improvement of 2-storey Ynares Multi-Purpose Building (Lupon & SK Office) Brgy.San Rafael. | [19 empty] | 319971.02 |  |  | 315112.45
3000-300-1-2—11-511-004-032 | 17) Repair of Waiting Shed & Ynares Multi-Purpose Bldg. at Brgy. Puray, Rodriguez, Rizal. a) Repair of 2-units Waiting Shed (Arc Type) at Sitio Malasia, Puray Proper, Brgy. Puray. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 70 |  | GF | 1014252.71 | 519392.52 |  | 998089.71 | 507513.68 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2—11-511-004-029 | b) Repair of 2-storey Ynares Multi-Purpose Building (Brgy. Hall), Brgy. Puray. | [18 empty] | 494860.19 |  |  | 490576.03
3000-300-1-2—11-511-004-023 | 18) Construction of Fence & Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Isidro, Rodriguez, Rizal. a) Construction of Perimeter Fence at Eastwood Residences Phase 1, Block 68, Brgy. San Isidro. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 1922977.18 |  | 1077544.38 | 1902688.85 |  | 1064582.55 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-2—11-511-004-036 | b) Construction of Fence at Eastwood Residence at Eastwood Residences Phase 6, Brgy. San Isidro. | [19 empty] | 349953.03 |  |  | 343803.72
3000-000-1-1—31-392-004-061 | c) Improvement of Ynares Multi-Purpose Covered Court at Eastwood Residences. Phase 6, Brgy. San Isidro. | [19 empty] | 495479.77 |  |  | 494302.58
3000-000-1-2—11-511-004-020 | 19) Construction of Welcome Arc, Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Brgy. San Isidro and Brgy. Burgos, Rodriguez, Rizal. a) Construction of 2-units Welcome Arc at Southville 8, Phase 1, Brgy. San Isidro. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 80 |  | GF | 1876671.93 |  | 396993.68 | 1860617.61 |  | 394589.35 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-1-31-392-004-032 | b) Improvement of Multi-Purpose Covered Court at Greenbreeze Subd., Phase 2A, Brgy. San Isidro. | [16 empty] | GF |  |  | 885048.54 |  |  | 874727.75
3000-000-1-2-11-399-006-034 | c) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Burgos National High School -Sorrento Annex, Brgy. Burgos. | [16 empty] | SEF |  | 594629.71 |  |  | 591300.51
3000-400-1-1-11-005-004 | 20) Construction/Provision (Water, Sanitation & Hygiene) Tierra Monte Subd. Brgy. Silangan, San Mateo, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 80 |  | GF | 1389420.84 |  | 1389420.84 | 1375031.41 |  | 1375031.41 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-039 | 21) Repair/Repainting of Ynares School Buildings at Dulongbayan Elem.School, Brgy. Dulongbayan 1, San Mateo, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 72 |  | SEF | 2798218.24 | 2798218.24 |  | 2780185.41 | 2780185.41 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-004-040 3000-300-1-2-11-511-0064-041 | 22) Repainting/Improvement of Ynares Multi-Purpose Covered Court & Construction of Comfort Room at Brgy. Ampid 1, San Mateo, Rizal. a) Repainting of Ynares Multi-Purpose Covered Court at Moncarlo Village, Brgy. Ampid 1. . b) Construction of 2-seater Comfort Room & Improvement of Ynares Multi-Purpose Covered Court at Sunnyville 4 Subd., Brgy. Ampid 1 | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 60 |  | GF GF | 1018657.51 | 618796.94 | 399860.57 | 1006581.75 | 610118.12 | 396463.63 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-040 | 23) Improvement of DepEd School Buildings at San Mateo Senior High School, Sta. Cecilia Subd., Brgy. Guitnang Bayan I, San Mateo, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 48 |  | SEF | 741835.05 |  | 741835.05 | 731774.95 |  | 731774.95 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-1-31-392-004-047 | 24) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court & Construction of Demountable Stage at Brgy. San Juan & Brgy. Dolores,Taytay, Rizal. a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Meralco Village, Brgy. San Juan. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | GF | 1734433.67 | 690487.42 |  | 1719031.41 | 683411.74 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-300-1-1-31-392-004-046 | b) Improvement of Ynares Multi-Purpose Covered Court at Meralco Village, Brgy. San Juan | [16 empty] | GF |  |  | 899724.6 |  |  | 892732.86
3000-000-1-2-11-399-006-043 | c) Construction of Demountable at Dolores Elem. School Brgy. Dolores. | [16 empty] | SEF |  |  | 144221.65 |  |  | 142886.81
3000-000-1-2-11-399-006-045 | 25) Repair/Repainting of Ynares School Buildings at Alas-Asin Elem. School, Brgy. Alas-Asin, Tanay, Rizal. | CANCELLED
3000-300-1-2-31-399-006-052 | 26) Repair/Repainting of Ynares School Building at Brgy. Plaza Aldea, Tanay, Rizal. a) Repair of School Buildings at Balimbing, Sitio Balimbing, Brgy. Plaza Plaza Aldea. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | SEF | 1882032.85 | 1182774.72 |  | 1862659.68 | 1171543.38 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-048 | b) Repair/Repainting of 2-storey, 6-rooms Ynares School Buildings at Tanay National High School, Brgy. Plaza Aldea. | [18 empty] | 699258.13 |  |  | 691116.3
3000-000-1-2-11-399-006-049 | 27) Construction of Drainage Canal & Soil Embankment at Patricio Jarin Mem. Elem. School, Brgy. San Isidro, Tanay, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 96 |  | GF | 1590215.84 |  | 1590215.84 | 1573102.27 |  | 1573102.27 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-044 | 28) Construction of Perimeter Fence at Balimbing Elem. School, Brgy. Plaza Aldea, Tanay, Rizal. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 132 |  | SEF | 3499145.85 |  | 3499145.85 | 3477105.6 |  | 3477105.6 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-051 3000-000-1-2-11-399-006-050 | 29) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Balimbing Elem. School, Brgy. Plaza Aldea, Tanay, Rizal. a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Balimbing Elem. School, Brgy. Plaza Aldea. b) Improvement of Ynares Multi-Purpose Covered Court at Balimbing Elem. School, Brgy. Plaza Aldea. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 90 |  | SEF | 1549839.13 | 822169.51 | 727669.62 | 1533706.04 | 813401.45 | 720304.59 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-055 | 30) Repair/Repainting/Improvement of Ynares School Building, Ynares Multi-Purpose Covered Court & Stage at Brgy. Bagumbayan, & Brgy. Prinza, Teresa, Rizal a) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Building at Bagumbayan Elem. School, Brgy. Bagumbayan. | PEO |  | Public Bidding |  | 26-Jan-1-Feb | 2021-02-02 |  | 2021-02-17 | 2021-02-23 | 2021-03-05 | 2021-03-10 | 2021-03-12 | 2021-03-22 | 2021-04-08 | 70 |  | SEF | 1251849.15 | 626025.47 |  | 1236614.34 | 619232.31 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-01-26 | 2021-01-26 | 2021-01-26 | 2021-01-26
3000-000-1-2-11-399-006-053 | b) Repainting of Ynares Multi-Purpose Covered Court and Stage at Prinza Elem. School, Brgy. Prinza. | [18 empty] | 351538.16 |  |  | 345774.88
3000-000-1-2-11-399-006-054 | c) Improvement of Ynares Multi-Purpose Covered Court and Stage at Prinza Elem. School, Brgy. Prinza. | [19 empty] | 274285.52 |  |  | 271607.15
3000-000-1-2-11-399-006-083 | 1) Repair /Repainting of 1-storey, 8-rooms Ynares School Building at Carlos “Botong” Francisco Memorial High School, Brgy. Mahabang Parang, Angono, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 60 |  | SEF | 1897458.15 | 1897458.15 |  | 1884321.61 | 1884321.61 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-000-002-002 | 2) Asphalt Overlaying of Various Streets at Victoriaville Subd., Brgy. Sta. Cruz, Antipolo, City. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 64 |  | GF | 2699056.94 | 2699056.94 |  | 2683642.27 | 2683642.27 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-399-006-009 | 3) Repair/Repainting of Ynares School Building at Lunsad Elem. School, Brgy. Lunsad, Binangonan, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 120 |  | SEF | 4498177.91 | 4498177.91 |  | 4476106.88 | 4476106.88 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-511-004-008 | 4) Construction of 1-Storey Ynares Multi-Purpose Building at Meralco Village, Brgy. Palangoy, Binangonan, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 90 |  | GF | 2618190.3 |  | 2618190.3 | 2154611.49 |  | 2154611.49 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-511-004-009 | 5) Construction of 2-Storey Ynares Multi-Purpose Building at Vocalan Compound, Brgy. Pag-Asa, Binangonan, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 136 |  | GF | 3779681.12 |  | 3779681.12 | 3759198.55 |  | 3759198.55 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-511-004-057 | 6) Construction of Ynares Multi-Purpose Building, Jalajala, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 156 |  | GF | 4010233.42 |  | 4010233.42 | 3994129.91 |  | 3994129.91 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
900-900-1-2-40-940-001-001-005 | 7) Construction of Stone Masonry for Side Protection at Dalaga Creek (Boundary of Purok 2 & 3). Brgty. Bayugo, Jalajala, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 120 |  | GF | 8294349.1 |  | 8294349.1 | 8261179.48 |  | 8261179.48 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-002-020 | 8) Asphalt Overlaying/Concrete Reblocking (portion) of J. Villegas St., Brgy. San Jose, Morong, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 60 |  | GF | 4198483.66 | 4198483.66 |  | 4177905.64 |  | 4177905.64 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-399-006-059 | 9) Repair/Repainting of Ynares School Building at Lagundi, CCL National High School, Morong, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 90 |  | SEF | 1837936.91 | 1837936.91 |  | 1823364.74 | 1823364.74 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-002-015 | 10) Improvement of San Lorenzo Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 90 |  | GF | 5396278.08 |  | 5396278.08 | 5371538.04 |  | 5371538.04 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-003-010 | 11) Concreting of Road at Sitio, Ligua, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 60 |  | GF | 1098155.71 |  | 1098155.71 | 1086192.78 |  | 1086192.78 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
9000-900-1-2-40-940-001-001-004 | 12) Construction of Stone Masonry for Slope Protection (portion) of Creek at Sitio Matagbak, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 92 |  | GF | 4198795.84 |  | 4198795.84 | 4177115.84 |  | 4177115.84 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-002-011 | 13) Rehabilitation of Matagbak Feeder Road, Sitio, Paliparan, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 42 |  | GF | 4498272.01 |  | 4498272.01 | 4474617.29 |  | 4474617.29 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-002-007 | 14) Asphalt Overlaying and Concreting (portion) of Sitio, Camale, Feeder Road, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 80 |  | GF | 2438529.06 | 2438529.06 |  | 2422136.52 | 2422136.52 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-002-009 | 15) Asphalt Overlaying of Angel Paz St. Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 32 |  | GF | 1727859.6 | 1727859.6 |  | 1712819.54 | 1712819.54 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-399-006-031 | 16) Repair/Repainting of Ynares School Buildings at Halayhayin Elem. School, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 84 |  | SEF | 2396585.4 | 2396585.4 |  | 2379159.28 | 2379159.28 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-1-31-392-004-034 | 17) Construction of 14x24m Ynares Multi-Purpose Covered Court at Eastwood, Residences Phase 6A, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 96 |  | GF | 3411318 |  | 3411318 | 3392084.51 |  | 3392084.51 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-1-31-392-004-042 | 18) Construction of 17x30m Ynares Multi-Purpose Covered Court at Villa San Mateo 2, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 128 |  | GF | 4258716.29 |  | 4258716.29 | 4236523.57 |  | 4236523.57 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-1-31-392-004-045 | 19) Improvement of Ynares Multi-Purpose Covered Court at Tierra Monte Subd., Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 71 |  | GF | 3306626.01 |  | 3306626.01 | 3288420.94 |  | 3288420.94 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-300-1-2-11-511-004-048 | 20) Construction of Ynares Stage at Haven for the Elderly, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 60 |  | GF | 1398805.04 |  | 1398805.04 | 1386056.33 |  | 1386056.33 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-1-1-31-392-004-049 | 21) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered at Brgy.Tandang Kutyo and Brgy. San Isidro, Tanay, Rizal a) Repair/ Repainting of Ynares Multi-Purpose Covered Court at Sitio Bukal, Brgy. Tandang Kutyo | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 80 |  | GF | 979758.4 | 576035.74 |  | 969675.1 | 571402.21 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-1-2-11-399-006-049 | b) Repair/ Repainting of Ynares Multi-Purpose Covered Court at Patricio Jarin Mem. Elementary School, Brgy. San Isidro | [16 empty] | SEF |  | 403722.66 |  |  | 398272.89
3000-000-1-1-31-392-004-048 | 22) Improvement of Ynares Multi-Purpose covered court and Const. of Comfort Room at Sitio Bukal, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 136 |  | GF | 2668067.22 |  | 2668067.22 | 2652004.57 |  | 2652004.57 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-0001-2-11-399-006-046 | 23) Repair/Repainting of 2-Storey, 8-rooms Ynares Building at Tanay North National High School, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 65 |  | SEF | 1999973.01 | 1999973.01 |  | 1985943.35 | 1985943.35 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-399-006-047 | 24) Repair/Repainting of 2-Storey, 6-rooms Ynares Building at Tanay West National High School, Brgy. Wawa, Tanay, Rizal. | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 72 |  | SEF | 2199839.57 | 2199839.57 |  | 2184841.61 | 2184841.61 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-1-31-392-004-056 | 25) Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Andres, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 60 |  | GF | 2279877.19 |  | 2279877.19 | 2263617.14 |  | 2263617.14 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-511-004-047 | 26) Construction of 2-Storey Ynares Multi-Purpose Building at Golden City Subd. Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 156 |  | GF | 4167324.28 |  | 4167324.28 | 4144170.32 |  | 4144170.32 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
8000-000-1-1-51-001-003-023 | 27) Rehabilitation of Stone Masonry Wall at Rizal Provincial Jail, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 60 |  | GF | 1197020.42 |  | 1197020.42 | 1184790.84 |  | 1184790.84 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-2-11-399-006-042 | 28) Construction/Improvement of Concrete Canal and Perimeter Fence at Bagong Pag-asa Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 95 |  | GF | 1799930.71 |  | 1799930.71 | 1784542.54 |  | 1784542.54 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-000-1-1-31-392-004-051 | 29) Construction of 11x30m Ynares Multi-Purpose Covered Court at Carissa Homes East I, Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding |  | 22-28-Feb-21 | 2021-03-01 |  | 2021-03-15 | 2021-03-22 | 2021-04-05 | 2021-04-08 | 2021-04-12 | 2021-04-16 | 2021-04-21 | 100 |  | GF | 3333119.34 |  | 3333119.34 | 3316107.43 |  | 3316107.43 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22 | 2021-02-22
3000-300-1-2-11-511-004-002 | 1) Construction of Fence of Open Space at Baytown Homes, Brgy. Kalayaan, Angono, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 45 |  | GF | 779068.93 |  | 779068.93 | 769218.07 |  | 769218.07 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-001 | 2) Improvement of Cheerfulness Street, AFP Logcom Village, Brgy. Dela Paz, Antipolo, City. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 399953.86 |  | 399953.86 | 393006.81 |  | 393006.81 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-003 | 3) Improvement/Rehabilitation of Road and Construction of Drainage Canal at JM Basa St. and Alley, Brgy. Libid, Binangonan, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 180 |  | GF | 6794304.43 |  | 6794304.43 | 6766636.3 |  | 6766636.3 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-005 | 4) Improvement/Rehabilitation/Concreting (portion) of Oja Road at Sitio Mambalon, Brgy. Mahabang Parang, Binangonan, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 160 |  | GF | 5198383.71 |  | 5198383.71 | 5174515.17 |  | 5174515.17 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-006 | 5) Concreting (portion) of R. Sison St. Brgy. Mahabang Parang, Binangonan, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 80 |  | GF | 1790069.24 |  | 1790069.24 | 1779109.07 |  | 1779109.07 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-012 | 6) Repair/Repainting of Ynares School Building and Ynares Stage at Brgy. Limbon, Limbon, Binangonan, Rizal. a) Repair/Repainting of Ynares School Buildings at Limbon Limbon Elem. School, Brgy. Limbon Limbon. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 50 |  | SEF | 1610956.48 | 1525528.66 |  | 1599740.4 | 1516922.85 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-013 | b) Repair/Repainting of Ynares Stage at Limbon Limbon Elem. School at Brgy. Limbon Limbon. | [18 empty] | 85427.82 |  |  | 82817.55
3000-000-1-2-11-399-006-020 | 7) Repair/Repainting of Ynares Stage and Barangay Hall, at Brgy. Concepcion and Brgy. San Salvador, Baras, Rizal. a) Repainting of Ynares Stage at Baras Elem. School, Brgy. Concepcion | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | SEF | 539026.74 | 63925.51 |  | 531080.54 | 62004.27 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-511-004-013 | b) Repair of Barangay. Hall, Brgy. San Salvador. | [16 empty] | GF |  | 475101.23 |  |  | 469076.27
3000-000=1-2-399-006-019 | 8) Repair/Repainting of Ynares School Buildings at Baras Elem. School, Brgy. Concepcion, Baras, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 180 |  | SEF | 6798560.5 |  | 6798560.5 | 6769500.49 |  | 6769500.49 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-00-1-1-51-001-002-023 | 9) Construction/Concreting at Purok 2, Brgy. Bayugo, Jalajalaj, Rizal a) Construction of Box Culvert at Purok 2, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 898208.02 |  | 398221.41 | 887442.68 |  | 391240.21 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-00-1-1-51-001-002-022 | b) Concreting of Bukang Liwayway St. Purok 2, Brgy. Bayugo | [19 empty] | 499986.61 |  |  | 496202.47
8000-000-1-1-51-001-002-027 | 10) Improvement of J. Borja St., Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 1099635.72 |  | 1099635.72 | 1086959.53 |  | 1086959.53 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-024 | 11) Concreting (portion) of Lirio St., Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 80 |  | GF | 1599014.32 |  | 1599014.32 | 1577343.43 |  | 1577343.43 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-029 | 12) Concreting of Feeder Road between Purok 1 and 2 at Sitio Kanluran, Brgy. Palaypalay, Jalajala, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 1099482.06 |  | 1099482.06 | 1086126.78 |  | 1086126.78 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
9000-900-1-2-40-940-001-001-006 | 13) Construction of Stone Masonry for Slope Protection of Creek at Sitio Biga, Brgy. 3rd District, Jalajala, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 1292642.09 |  | 1292642.09 | 1278638.98 |  | 1278638.98 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-010 | 14) Rehabilitation of Matagbak Feeder Road, Sitio Matilos, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 100 |  | GF | 3699986.79 |  | 3699986.79 | 3679837.62 |  | 3679837.62 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-1-1-51-001-002-013 | 15) A Rehabilitation of Matagbak Feeder Road, Sitio Calumpang, Brgy. Bagumbayan, Pililla, Rizal. | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 80 |  | GF | 1994940.85 |  | 1994940.85 | 1975441.31 |  | 1975441.31 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-51-004-063 | 16) Concreting of Ground infront of Barangay Hall, Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 649423.81 |  | 649423.81 | 640446.39 |  | 640446.39 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-1-31-392-004-062 | 17) Repair/ Repainting of Ynares Multi-Purpose Covered Court, Ynares Multi-Purpose building and Perimeter Fence at Brgy. San Jose, Rodriguez, Rizal a) Repair/ Repainting of Ynares Multi-Purpose Covered Court at Montalban Heights Phase II, Brgy. San Jose | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 90 |  | GF | 1116178.93 | 755560.22 |  | 1107145.69 | 747813.26 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-511-004-035 | b) S Repair/ Repainting of Ynares Multi-Purpose Building at Montalban Heights Phase II, Brgy. San Jose | [18 empty] | 175918.85 |  |  | 173255.59
3000-300-1-2-11-511-004-034 | c) Repair/Repainting of Perimeter Fence at Montalban Heights Phase II, Brgy. San Jose | [18 empty] | 184699.86 |  |  | 186076.84
3000-300-1-2-11-511-004-033 | 18) Improvement of Ground & Ynares Multi-Purpose Covered Court at Brgy. San Jose, Rodriguez, Rizal a) Improvement of Gound at Montalban Heights Phase II, Brgy. San Jose | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 48 |  | GF | 876832.81 |  | 445294.25 | 864652.11 |  | 436936.48 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-1-31-392-004-036 | b) Improvement of Ynares Multi-Purpose Covered Court at St. Peter Ville, Suburban Village, Brgy. San Jose | [19 empty] | 431538.56 |  |  | 427715.63
3000-000-1-1-31-392-004-035 | 19) Repair/ Repainting of Ynares Multi-Purpose Covered Court at St. Peter Ville, Suburban Village, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 40 |  | GF | 1298617.66 | 1298617.66 |  | 1284396.13 | 1284396.13 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-1-31-392-004-037 | 20) Repair of 17x30m Ynares Multi-Purpose Covered Court, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 169 |  | GF | 1177879.76 | 1177879.76 |  | 1166879.55 | 1166879.55 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-038 3000-000-1-2-11-399-006-037 | 21) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Ynares Stage at Brgy. San Jose, Rodriguez, Rizal a) Repair/ Repainting of Ynares Multi-Purpose Covered Court and Ynares Stage at Tagumpay National High School, Brgy. San Jose . b) Improvement of Ynares Multi-Purpose Covered Court at Tagumpay National High School, Brgy. San Jose | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 80 |  | SEF | 1197688.99 | 754633.85 | 443055.14 | 1184379.98 | 746685.92 | 437694.06 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-1-31-392-004-041 | 22) Repainting/Repair of Ynares Multi-Purpose Covered Court and Ynares Multi- Purpose Building at Brgy. Ampid I and Brgy. Sta Ana, San Mateo, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court, at Rafaela 2 Subd., Brgy. Ampid I | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 65 |  | GF | 997451.28 | 654747.37 |  | 987217.46 | 650208.81 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-511-004-045 | b) Repair/Repainting of 2-storey Ynares Multi-Purpose Building, Brgy. Sta Ana | [18 empty] | 342703.91 |  |  | 337008.65
3000-000-1-1-31-392-004-044 | 23) Repair/ Repainting of Ynares Multi-Purpose Covered Court at Brgy. Silangan and Brgy. Guitnang Bayan I, San Mateo, Rizal a) Repair/ Repainting of Ynares Multi-Purpose Covered Court at Tierra Monte Subd., Brgy. Silangan | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 133 |  | GF | 1257043.17 | 837642.81 |  | 1242005.24 | 830916.73 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-1-31-392-004-038 | b) Repainting of Ynares Multi-Purpose Covered Court at Easterview Park Subd. Brgy. Guitnang Bayan I | [18 empty] | 419400.36 |  |  | 411088.51
3000-000-1-1-31-392-004-039 | 24) Repair/Repainting of Ynares Multi-Purpose Covered Court at Divine Mercy Village, Brgy. Guitnag Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 56 |  | GF | 933798.44 | 933798.44 |  | 921545.5 | 921545.5 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-041 | 25) Repair/Repainting of Ynares Multi-Purpose Covered Court at Bagong Pag-Asa Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 38 |  | SEF | 499787.95 | 499787.95 |  | 491348 | 491348 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
1000-000-1-1-31-012-008-001 | 26) Repair/Rewiring of Feeder Wire of Rizal Provincial Jail at Cabrera Road, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 60 |  | GF | 1104999.65 | 1104999.65 |  | 1092639.93 | 1092639.93 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
9000-900-1-2-40-940-001-012 | 27) Construction of Stone Masonry for Slope Protection (portion) of Teresa River, Brgy. May-Iba, Teresa, Rizal | PEO |  | Public Bidding | 2021-03-01 | 5-11-Mar-21 | 2021-03-12 |  | 2021-03-24 | 2021-03-30 | 2021-04-08 | 2021-04-14 | 2021-04-15 | 2021-04-19 | 2021-04-28 | 252 |  | GF | 19914863.99 |  | 19914863.99 | 19873298.39 |  | 19873298.39 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-068 | 1) Concreting of School Ground at Dona Justa Guido Mem. School, Brgy. San Roque, Angono, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 40 |  | SEF | 632372.44 |  | 632372.44 | 623610.06 |  | 623610.06 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-511-004-006 | 2) Improvement of Multi-Purpose Building & Concreting of Ground at Victoriaville Homes, Upper Lucban, Brgy. Sta. Cruz, Antipolo, City. a) Improvement of 1-Storey Multi-Purpose Building at Victoriaville Homes, Upper Lucban, Brgy. Sta. Cruz | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 45 |  | GF | 765419.6 |  | 108287.99 | 755288.52 |  | 105471.44 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-511-004-005 | b) Concreting of Ground at Victoriaville Homes, Upper Lucban, Brgy. Sta. Cruz. | [19 empty] | 657131.61 |  |  | 649817.08
3000-300-1-2-11-511-004-012 | 3) Extension of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall), Brgy. San Jose, Baras, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 132 |  | GF | 2797321.75 |  | 2797321.75 | 2779300.89 |  | 2779300.89 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-021 | 4) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Evangelista Elem. School, Baras, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 72 |  | SEF | 1298812.63 |  | 1298812.63 | 1284769.92 |  | 1284769.92 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-011 | 5) Improvement of School Ground and Construction of Demountable Stage, at Brgy.Bilibiran and Brgt. Libis, Binangonan, Rizal. a) Improvement of School Ground at Guronasyon Foundation Inc., National High School, Brgy. Bilibiran | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 90 |  | SEF | 667620.3 |  | 488259.09 | 618727.18 |  | 443241.26 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-300-1-2-11-511-004-011 | b) Construction of Demountable Stage, Brgy. Libis | [16 empty] | GF |  |  | 179361.21 |  |  | 175485.92
3000-000-1-2-11-399-006-074 | 6) Construction of 2-Storey, 6-Rooms Ynares School Building at Talim Elem. School, Brgy. Rayap, Binangonan, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 235 |  | SEF | 13480748.26 |  | 13480748.26 | 13405576.36 |  | 13405576.36 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-074 | 7) Construction of 2-Storey, 6-Rooms Ynares School Building at Malakaban Elem. School, Brgy. Malakaban, Binangonan, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 235 |  | SEF | 13340354.7 |  | 13340354.7 | 13262345.71 |  | 13262345.71 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
8000-000-11-51-001-003-025 | 8) Improvement of Mahabang Parang Lunsad Road, Binangonan, Rizal. | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 164 |  | GF | 9999835.58 |  | 9999835.58 | 9949520.46 |  | 9949520.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-070 | 9) Construction of 2-Storey, 4-Rooms Ynares School Building at Elem. School, Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 176 |  | SEF | 10777992.21 |  | 10777992.21 | 10722590.26 |  | 10722590.26 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-071 | 10) Construction of 2-Storey, 6-Rooms Ynares School Building at Buhangin Elem. School, Brgy. Buhangin, Binangonan, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 235 |  | SEF | 15350539.88 |  | 15350539.88 | 15274439.57 |  | 15274439.57 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-072 | 11) Construction of 2-Storey, 6-Rooms Ynares School Building at Bombong Elem. School, Brgy. Bombong, Binangonan, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 235 |  | SEF | 15308039.3 |  | 15308039.3 | 15228475.16 |  | 15228475.16 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05
3000-000-1-2-11-399-006-076 | 12) Construction of 2-Storey, 3-Rooms with Multi-Purpose Area (Second Floor) at Catalino D. Salazar National High School, Brgy. Subay, Cardona, Rizal. | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 40 |  | SEF | 6965020.17 |  | 6965020.17 | 6929962.17 |  | 6929962.17 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
0-300-1-2-11-511-004-056 | 13) Improvement of 1-Storey Multi-Purpose Bldg., Brgy. 3rd District, Jalajala, Rizal Construction of Stone Masonry for Slope Protection of Creek at Sitio Biga, Brgy. 3rd District, Jalajala, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 120 |  | GF | 1558830.4 |  | 1558830.4 | 1541652.55 |  | 1541652.55 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-044 | 14) Asphalt Overlaying/Concrete Reblocking (portion) of Borja St. and P.Torres St. Brgy. Special District, Jalajala, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 60 |  | GF | 1150482.24 | 1150482.24 |  | 1137844.55 | 1137844.55 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
9000-900-1-2-40-940-001-001-006 | 15) Costruction of Stone masonry for Side Protection (beside J. Luna Street) at Sitio Lumang Nayon, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 60 |  | DDRRMF | 998888.97 |  | 998888.97 | 987792.5 |  | 987792.5 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-000-1-2-11-399-006-081 | 16) Construction of 2-Storey, 2-Rooms Ynares School Building at Bayugo National High School, Brgy. Bayugo, Jalajala, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 108 |  | SEF | 4842983.37 |  | 4842983.37 | 4816546.09 |  | 4816546.09 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-021 | 17) Improvement/Rehabilitation of Drainage Canal (portion) of J.Pascual St. Sitio Hulo (Pamboy’s Club) Brgy. San Pedro, Morong, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 60 |  | 20% | 530205.72 |  | 530205.72 | 522057.87 |  | 522057.87 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-000-1-2-399-006-058 | 18) Construction/Replacement of Perimeter Fence at Bombongan Elem. School, Brgy. Bombongan, Morong, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 77 |  | SEF | 2199841.46 |  | 2199841.46 | 2182841.43 |  | 2182841.43 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-035 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of Bagumbayan-Wawa Market Road (Snakeroad), Brgy. Bagumbayan-Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 90 |  | GF | 5799428.2 | 5799428.2 |  | 5764732.13 | 5764732.13 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-033 | 20) Asphalt Overlaying/Concrete Reblocking (portion) of San Lorenzo Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 80 |  | GF | 3597182.15 | 3597182.15 |  | 3574213.72 | 3574213.72 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-037 | 21) Asphalt Overlaying/Concrete Reblocking (portion) of E. Tibay St. Brgy. Wawa, Pililla, Rizal. | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 120 |  | GF | 8699804.1 | 8699804.1 |  | 8659733.75 | 8659733.75 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-038 | 22) Asphalt Overlaying/Concrete Reblocking (portion) of Matagbak Feeder Road (Corner Manila East Road), Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 120 |  | GF | 7499935.69 | 7499935.69 |  | 7463854.77 | 7463854.77 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-300-1-2-11-511-004-030 | 23) Construction of Ynares Multi-Purpose Building (Tribal Hall) at Sitio Mabolo, Brgy. Puray, Rodriguez, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 168 |  | GF | 3784298.09 |  | 3784298.09 | 3754107.58 |  | 3754107.58 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-300-1-2-11-511-004-025 | 24) Construction of 2-Storey, 2-Rooms Ynares School Building (Health Center/Brgy. Annex Office) at N.V. Dela Costa Homes V. Brgy. Burgos, Rodriguez, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 136 |  | GF | 3680835.99 |  | 3680835.99 | 3655871.46 |  | 3655871.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-000-1-1-31-392-004-032 | 25) Improvement of Ynares Multi-Purpose Covered Court at Greenbreeze Subd. Phase 2, Brgy. San Isidro, Rodriguez, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 86 |  | GF | 2382202.71 |  | 2382202.71 | 2367221.46 |  | 2367221.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-300-1-2-11-511-004-037 3000-300-1-2-11-511-004-027 | 26) Construction of 2-Seater Comfort Room and Repair of Ynares Multi-Purpose Building at Brgy. Isidro and Brgy. Balite, Rodriguez, Rizal. a) Construction of 2-Seater Comfort Room at Eastwood Residences Phase 6, Brgy.San Isidro. b) Repair of Ynares Multi-Purpose Building (Lupon Building), Brgy. Balite, Rodriguez, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 130 |  | GF | 1157246.43 | 808719.02 | 348527.41 | 1143067.64 | 796875.44 | 346192.2 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-300-1-2-11-511-004-028 | 27) Repair/Repainting of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall), Brgy. Balite, Rodriguez, Rizal. | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 163 |  | GF | 1242874.23 | 1242874.23 |  | 1231652.05 | 1231652.05 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-000-1-2-11-399-006-079 | 28) Construction of 4-Storey, 8-Rooms Ynares School Building at Muzon Elem. School, Brgy. Muzon, Taytay, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 260 C. D. |  | SEF | 23801392.78 |  | 23801392.78 | 23711184.03 |  | 23711184.03 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
3000-000-1-2-11-399-006-057 | 29) Construction/Improvement of Perimeter Fence at Abuyod Elem. School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 122 C. D. |  | SEF | 2814692.7 |  | 2814692.7 | 2793765.52 |  | 2793765.52 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
8000-000-1-1-51-001-002-017 | 30) Concrete Reblocking (portion) of Filipinas Ave., Brgy. Dulumbayan, Teresa, Rizal | PEO |  | Public Bidding | 2021-04-05 | 8-14-April-21 | 2021-04-15 |  | 2021-04-27 | 2021-05-03 | 2021-05-14 | 2021-05-19 | 2021-05-20 | 2021-05-24 | 2021-05-31 | 120 C. D. |  |  | 6605956.06 |  | 6605956.06 | 6576094.13 |  | 6576094.13 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08
516926603.71
Total Contract Price of Procurement Activities Conducted | [21 empty] | 516711929.57
Total Savings (Total Alloted Budget - Total Contract Price) | [18 empty] | 516926603.71
PROCUREMENT OF GOODS
| RENTAL OF COPYING MACHINE | PGSO | NO | Competitive Bidding | N/A | 2020-12-03 | 2020-12-10 | 2020-12-22 | 2020-12-22 | 2020-12-29 | 2021-01-04 | 2021-01-05 | 2021-01-08 | 2021-01-15 | 2021-01-20 | N/A |  | GoP | 1008260 |  |  | 1008260 |  |  | NGO | 2020-12-10 | 2020-12-22 | 2020-12-22 | 2020-12-29 | 2021-01-04 | N/A
| TREATMENT & TRANSPORT OF HAZARDOUS WASTE | RPHS | NO | Competitive Bidding | 2020-12-02 | 2020-12-03 | 2020-12-10 | 2020-12-22 | 2020-12-22 | 2020-12-29 | 2021-01-05 | 2021-01-07 | 2021-01-12 | 2021-01-27 | 2021-01-29 | N/A |  | GoP | 4550000 |  |  | 4550000 |  |  | NGO | 2020-12-10 | 2020-12-22 | 2020-12-22 | 2020-12-29 | 2021-01-05 | N/A
| PROVISION OF HOSPITAL LINENS & LAUNDRY SERVICES | RPHS | NO | Competitive Bidding | 2020-12-02 | 2020-12-03 | 2020-12-10 | 2020-12-22 | 2020-12-22 | 2020-12-29 | 2021-01-07 | 2021-01-08 | 2021-01-12 | 2021-01-27 | 2021-01-29 | N/A |  | GoP | 4355000 |  |  | 4355000 |  |  | NGO | 2020-12-10 | 2020-12-22 | 2020-12-22 | 2020-12-29 | 2021-01-07 | N/A
| HIRING OF JANITORIAL SERVICES | RPHS/PGSO | NO | Competitive Bidding | 2020-12-02 | 2020-12-04 | 2020-12-11 | 2020-12-23 | 2020-12-23 | 2020-12-29 | 2021-01-06 | 2021-01-08 | 2021-01-12 | 2021-01-20 | 2021-01-25 | N/A |  | GoP | 25107300 |  |  | 23802904.07 |  |  | NGO | 2020-12-11 | 2020-12-23 | 2020-12-23 | 2020-12-29 | 2021-01-06 | N/A
| PROCUREMENT OF MOBILE SHOWER | PDRRMO | NO | Competitive Bidding | 2020-12-02 | 2020-12-04 | 2020-12-11 | 2020-12-23 | 2020-12-29 | 2020-12-29 | 2021-01-06 | 2021-01-08 | 2021-01-11 | 2021-01-13 | 2021-01-20 | 2021-02-24 |  | GoP | 4800000 |  |  | 4790000 |  |  | NGO | 2020-12-11 | 2020-12-23 | 2020-12-29 | 2020-12-29 | 2021-01-06 | 2021-02-24
| PROCUREMENT OF UTILITY VEHICLE | GOVS | NO | Competitive Bidding | 2020-12-09 | 2020-12-11 | 2020-12-17 | 2020-12-29 | 2020-12-29 | 2021-01-04 | 2021-01-07 | 2021-01-11 | 2021-01-13 | 2021-04-26 | 2021-04-27 | 2021-06-25 |  | GoP | 2300000 |  |  | 2295000 |  |  | NGO | 2020-12-17 | 2020-12-29 | 2020-12-29 | 2021-01-04 | 2021-01-07 | 2021-06-25
| PROCUREMENT OF MEDICAL OXYGEN (REFILL) | RPHS | NO | Competitive Bidding | 2020-12-22 | 2020-12-29 | 2021-01-05 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-25 | 2021-01-26 | staggered basis |  | GoP | 10977250 |  |  | 9475100 |  |  | NGO | 2021-01-05 | 2021-01-19 | 2021-01-19 | 2021-01-19 | 2021-01-20 | staggered basis
| PROVISION OF FOOD | RPHS | NO | NP-53.9 - Small Value Procurement | N/A | 2020-12-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-04 | N/A | staggered basis |  | GoP | 585900 |  |  | 544000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | staggered basis
| PROCUREMENT OF LPG | RPHS | NO | Shopping | N/A | 2020-12-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-07 | N/A | staggered basis |  | GoP | 184500 |  |  | 176300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | staggered basis
| PROVISION OF FOOD | ADMIN | NO | Competitive Bidding | 2020-12-28 | 2021-12-29 | 2021-01-05 | 2021-01-19 | 2021-01-19 | 2021-01-20 | 2021-01-21 | 2021-01-22 | 2021-01-25 | 2021-01-27 | 2021-01-28 | staggered basis |  |  | 4860000 |  |  | 4860000 |  |  | NGO | 2021-01-05 | 2021-01-19 | 2021-01-19 | 2021-01-20 | 2021-01-21 | staggered basis
| PROCUREMENT OF LATEX EXAM GLOVES | PHO | NO | Shopping | N/A | 2021-01-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-20 | N/A | 2021-01-25 |  | GoP | 498000 |  |  | 488040 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-25
| PROCUREMENT OF MEDICAL SUPPLIES | RPHS | NO | Shopping | N/A | 2021-01-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-29 | N/A | 2021-02-05 |  | GoP | 710000 |  |  | 699000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-05
| PROCUREMENT OF TABLET ARMCHAIR | DEPED | NO | Competitive Bidding | 2021-01-15 | 2021-01-19 | 2021-01-26 | 2021-02-09 | 2021-02-09 | 2021-02-10 | 2021-02-11 | 2021-02-15 | 2021-02-16 | 2021-02-18 | 2021-03-05 | staggered basis |  | GoP | 4000000 |  |  | 3590000 |  |  | NGO | 2021-01-26 | 2021-02-09 | 2021-02-09 | 2021-02-10 | 2021-02-11 | staggered basis
| CONSIGNMENT OF DRUGS & MEDICINES | RPHS | NO | Competitive Bidding | 2021-01-20 | 2021-01-22 | 2021-01-29 | 2021-02-11 | 2021-02-11 | 2021-02-15 | 2021-02-18 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-26 | staggered basis |  | GoP | 64597163.05 |  |  | 64597163.05 |  |  | NGO | 2021-01-29 | 2021-02-11 | 2021-02-11 | 2021-02-15 | 2021-02-18 | staggered basis
| CONSIGNMENT OF IV FLUIDS | RPHS | NO | Competitive Bidding | 2021-01-20 | 2021-01-22 | 2021-01-29 | 2021-02-11 | 2021-02-11 | 2021-02-15 | 2021-02-16 | 2021-02-18 | 2021-02-22 | 2021-02-24 | 2021-02-26 | staggered basis |  | GoP | 25118790 | [5 empty] | NGO | 2021-01-29 | 2021-02-11 | 2021-02-11 | 2021-02-15 | 2021-02-16 | staggered basis
| PROCUREMENT OF CADAVER BAG | RPHS | NO | Shopping | N/A | 2021-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-01 | N/A | 2021-02-11 |  | GoP | 280000 |  |  | 224000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-11
| PROCUREMENT OF OFFICE SUPPLIES | PAC | NO | Shopping | N/A | 2021-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-19 | N/A | 2021-02-26 |  | GoP | 57320 |  |  | 54874 |  |  | N/A | [5 empty] | 2021-02-26
| CALIBRATION OF XRAY MACHINE | RPHS | NO | NP-53.9 - Small Value Procurement | N/A | 2021-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-08 | N/A | 2021-04-19 |  | GoP | 215000 |  |  | 195030 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-19
| PROVISION OF FOOD | GOVERNOR'S OFFICE | NO | NP-53.9 - Small Value Procurement | N/A | 2021-01-22 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-25 | N/A | 2021-01-26 |  | GoP | 68400 |  |  | 61200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-01-28
| PROVISION OF FOOD | RPHS | NO | Competitive Bidding | 2021-01-26 | 2021-01-28 | 2021-02-04 | 2021-02-17 | 2021-02-17 | 2021-02-18 | 2021-02-19 | 2021-02-22 | 2021-02-23 | 2021-02-24 | 2021-02-26 | staggered basis |  | GoP | 8300000 |  |  | 8300000 |  |  | NGO | 2021-02-04 | 2021-02-17 | 2021-02-17 | 2021-02-18 | 2021-02-19 | staggered basis
| PROCUREMENT OF BITUMINOUS CONCRETE SURFACE | PEO | NO | Competitive Bidding | N/A | 2021-01-28 | 2021-02-07 | 2021-02-17 | 2021-02-17 | 2021-02-18 | 2021-02-24 | 2021-02-25 | 2021-02-26 | 2021-03-04 | 2021-03-10 | staggered basis |  | GoP | 1500600 |  |  | 1482300 |  |  | NGO | 2021-02-07 | 2021-02-17 | 2021-02-17 | 2021-02-18 | 2021-02-24 | staggered basis
| PROCUREMENT OF SUPPLIES FOR PMS | PEO | NO | Shopping | N/A | 2021-01-29 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-10 | N/A | 2021-05-28 |  | GoP | 326590 |  |  | 315500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-28
| PROCUREMENT OF DESKTOP COMPUTER | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-26 | N/A | 2021-03-02 |  | GoP | 111800 |  |  | 109950 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-02
| PROCUREMENT OF INTENSIFYING SCREEN | RPHS | NO | Shopping | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-11 | N/A | 2021-02-26 |  | GoP | 193600 |  |  | 189961 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-26
| PROCUREMENT OF GLUCOSE STRIPS | RPHS | NO | Shopping | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-01 | N/A | 2021-03-11 |  | GoP | 744000 |  |  | 347820 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-11
| PROCUREMENT OF DESKTOP & PRINTER | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-19 | N/A | 2021-03-29 |  | GoP | 98400 |  |  | 93530 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-29
| PROCUREMENT OF TIRES | PEO | NO | Shopping | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-10 | N/A | 2021-05-18 |  | GoP | 194000 |  |  | 167000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-18
| REPAIR OF BIO REFRIGERATOR | RPHS | NO | NP-53.9 - Small Value Procurement | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-01 | N/A | 2021-03-11 |  | GoP | 68400 |  |  | 61200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-11
| JANITORIAL SERVICES | RPG | NO | NP-53.9 - Small Value Procurement | N/A | 2021-02-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-22 | N/A | ON GOING |  | GoP | 900000 |  |  | 806873.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF COVID-19 ANTIGEN RAPID TEST DEVICE | RPHS | NO | Competitive Bidding | 2021-02-08 | 2021-02-10 | 2021-02-18 | 2021-03-03 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-08 | 2021-03-09 | 2021-03-12 | 2021-03-18 | 2021-04-06 |  | GoP | 3600000 |  |  | 2970000 |  |  | NGO | 2021-02-18 | 2021-03-03 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-04-06
| REPAIR OF ANESTHESIA MACHINE | RPHS | NO | NP-53.9 - Small Value Procurement | N/A | 2021-02-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-01 | N/A | 2021-03-11 |  | GoP | 265000 |  |  | 259000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-11
| REPAIR OF ISUZU CLOSED VAN | PGSO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-02-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-22 | N/A | 2021-03-26 |  | GoP | 62310 |  |  | 60610 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-26
| PROCUREMENT OF ELECTRICAL SUPPLIES | RPHS | NO | Shopping | N/A | 2021-02-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-26 | N/A | 2021-03-05 |  | GoP | 57745 |  |  | 54545 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-05
| PROCUREMENT OF HARDWARE MATERIALS | PGSO | NO | Shopping | N/A | 2021-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-12 | N/A | 2021-05-20 |  | GoP | 135714.5 |  |  | 126131 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-20
| PROCUREMENT OF ELECTRICAL SUPPLIES | PGSO | NO | Shopping | N/A | 2021-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-04 | N/A | 2021-03-08 |  | GoP | 55635 |  |  | 53040 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-08
| PROCUREMENT OF HARDWARE MATERIALS | PGSO | NO | Shopping | N/A | 2021-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-04 | N/A | 2021-03-08 |  | GoP | 54058 |  |  | 48283 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-08
| PROCUREMENT OF HARDWARE MATERIALS | RPHS | NO | Shopping | N/A | 2021-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-26 | N/A | 2021-03-02 |  | GoP | 218685.58 |  |  | 205747.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-02
| PROCUREMENT OF HARDWARE MATERIALS | RPHS | NO | Shopping | N/A | 2021-02-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-26 | N/A | 2021-03-02 |  | GoP | 216821.58 |  |  | 206940 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-02
| PROCUREMENT OF PASSENGER ELEVATOR | PGSO | NO | Competitive Bidding | 2021-02-12 | 2021-02-16 | 2021-02-23 | 2021-03-09 | 2021-03-09 | 2021-03-10 | 2021-03-12 | 2021-03-15 | 2021-03-16 | 3/19/ | N/A | ON GOING |  | GoP | 7200000 |  |  | 7150000 |  |  | NGO | 2021-02-23 | 2021-03-09 | 2021-03-09 | 2021-03-10 | 2021-03-12 | ON GOING
| PROCUREMENT OF DESKTOP COMPUTER | DEPED | NO | Competitive Bidding | 2021-02-17 | 2021-02-23 | 2021-03-02 | 2021-03-16 | 2021-03-16 | 2021-03-17 | 2021-03-19 | 2021-03-22 | 2021-03-24 | 2021-05-17 | 2021-05-18 | 2021-06-14 |  | GoP | 5915000 |  |  | 5872750 |  |  | NGO | 2021-03-02 | 2021-03-16 | 2021-03-16 | 2021-03-17 | 2021-03-19 | 2021-06-14
| PROCUREMENT OF IT EQUIPMENT | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-02-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-15 | N/A | 2021-03-22 |  | GoP | 95155 |  |  | 89350 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-22
| PROCUREMENT OF DRUGS | RPHS | NO | Shopping | N/A | 2021-02-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-03 | N/A | 2021-05-08 |  | GoP | 916050 |  |  | 891130 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-08
| PROCUREMENT OF CUSTOMIZED NO. 56 | PTO | NO | NP-53.5 Agency-to-Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-02-26 | N/A | N/A | N/A | N/A |  | GoP | 427275 |  |  | 331793.28 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF FUEL | RPG | NO | Competitive Bidding | 2021-02-26 | 2021-03-01 | 2021-03-08 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-24 | 2021-03-29 | 2021-04-05 | 2021-05-03 | 5/10//2021 | staggered basis |  | GoP | 13318879.94 |  |  | 13318879.94 |  |  | NGO | 2021-03-08 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-24 | staggered basis
| PROCUREMENT OF LABORATORY REAGENTS | RPHS | NO | Competitive Bidding | 2021-02-26 | 2021-03-02 | 2021-03-09 | 2021-03-23 | 2021-03-23 | 2021-03-24 | 2021-03-26 | 2021-03-29 | 2021-03-30 | 2021-03-31 | 2021-04-02 | staggered basis |  | GoP | 39593100 |  |  | 39593100 |  |  | NGO | N/A | N/A | N/A | N/A | N/A | staggered basis
| REPAIR AND MAINTENANCE OF BASKETBALL COURT | YSA | NO | Competitive Bidding | N/A | 2021-03-05 | 2021-03-12 | 2021-03-25 | 2021-03-25 | 2021-03-26 | 2021-03-30 | 2021-04-05 | 2021-04-06 | 2021-04-12 | 2021-04-14 | 2021-05-10 |  | GoP | 1300000 |  |  | 1173000 |  |  | NGO | 2021-03-12 | 2021-03-25 | 2021-03-25 | 2021-03-26 | 2021-03-30 | 2021-05-10
| PROCUREMENT OF AIRCON PARTS | PGSO | NO | Shopping | N/A | 2021-03-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-15 | N/A | 2021-03-22 |  | GoP | 133400 |  |  | 126200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-22
| PROCUREMENT OF OFFICE SUPPLIES | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-03-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-05 | N/A | 2021-04-12 |  | GoP | 242125 |  |  | 230470 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-12
| PROCUREMENT OF TIRES | PEO | NO | Shopping | N/A | 2021-03-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-22 | N/A | 2021-03-25 |  | GoP | 156000 |  |  | 151200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-26
| PROCUREMENT OF VEHICLE PARTS | PGSO | NO | Shopping | N/A | 2021-03-09 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-22 | N/A | 2021-03-26 |  | GoP | 84880 |  |  | 82300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-26
| PROCUREMENT OF MEDICAL SUPPLIES | RPHS | NO | Shopping | N/A | 2021-03-12 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-22 | N/A | 2021-03-25 |  | GoP | 452800 |  |  | 443480 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-25
| PROCUREMENT OF PATROL VEHICLE | GOVERNOR'S OFFICE | NO | Competitive Bidding | 2021-03-08 | 2021-03-10 | 2021-03-17 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-04-07 | 2021-04-08 | 2021-04-14 | 2021-05-28 | 2021-05-24 | 2021-05-31 |  | GoP | 4200000 |  |  | 4113000 |  |  | NGO | 2021-03-17 | 2021-03-30 | 2021-03-30 | 2021-03-31 | 2021-04-07 | 2021-05-31
| PROCUREMENT OF CUSTOMIZED A.F. NO. 51 | PTO | NO | NP-53.5 Agency-to-Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-11 | N | N/A | N | N/A |  | GoP | 1721940 |  |  | 1691884.32 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF MEDICAL SUPPLIES | RPHS | NO | Competitive Bidding | 2021-03-12 | 2021-03-16 | 2021-03-24 | 2021-04-06 | 2021-04-06 | 2021-04-12 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-05-05 | 2021-05-17 | staggered basis |  | GoP | 18760381 |  |  | 18378649.45 |  |  | NGO | 2021-03-24 | 2021-04-06 | 2021-04-06 | 2021-04-12 | 2021-04-21 | staggered basis
| PROCUREMENT OF DESKTOP CLONE & PRINTER | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-20 | N/A | 2021-05-03 |  | GoP | 79700 |  |  | 77400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-03
| PROCUREMENT OF ECG MACHINE | RPHS | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-08 | N/A | 2021-04-16 |  | GoP | 275000 |  |  | 145000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-16
| PROCUREMENT OF TRASHBAG | RPHS | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-16 | N/A | 2021-04-22 |  | GoP | 339300 |  |  | 160950 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-22
| PROCUREMENT OF PRINTER | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-13 | N/A | 2021-04-19 |  | GoP | 192000 |  |  | 185000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-19
| PROCUREMENT OF AIRCON PARTS | RPG | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-16 | N/A | 2021-04-21 |  | GoP | 118250 |  |  | 113440 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-21
| PROCUREMENT OF MEDICAL SUPPLIES | RPHS | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-26 | N/A | 2021-03-30 |  | GoP | 895395 |  |  | 844450.75 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-03-30
| PROCUREMENT OF OFFICE SUPPLIES | PGSO | NO | Shopping | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-10 | N/A | 2021-05-20 |  | GoP | 981393 |  |  | 922596.75 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-20
| GEOTECHNICAL INVESTIGATION | PEO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-06 | N/A | 2021-04-30 |  | GoP | 600000 |  |  | 540000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-30
| HYDRAULIC SECONDARY PUMP | PEO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-03-19 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-10 | N/A | 2021-05-17 |  | GoP | 155000 |  |  | 149000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-17
| PROCUREMENT OF DENTAL SUPPLIES | RPHS | NO | Shopping | N/A | 2021-03-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-04 | N/A | 2021-06-09 |  | GoP | 112006 |  |  | 109315 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-09
| PROCUREMENT OF MEDICAL SUPPLIES | RPHS | NO | Shopping | N/A | 2021-03-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-16 | N/A | 2021-04-21 |  | GoP | 158400 |  |  | 142200 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-21
| PROCUREMENT OF MEDICAL, DENTAL & LABORATORY SUPPLIES | RPHS | NO | Shopping | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-14 | N/A | 2021-05-28 |  | GoP | 329325 |  |  | 320984 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-28
| PROCUREMENT OF RADIOLOGY SUPPLIES | RPHS | NO | Competitive Bidding | N/A | 2021-04-08 | 2021-04-15 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-07 | 2021-05-31 | 2021-06-10 |  | GoP | 1945690 |  |  | 1899290 |  |  | NGO | 2021-04-15 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-05-03 | 2021-06-10
| PROCUREMENT OF DRUGS AND MEDICINES | PHO | NO | Competitive Bidding | 2021-04-06 | 2021-04-08 | 2021-04-15 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-05-04 | 2021-05-05 | 2021-05-07 | 2021-05-13 | 2021-05-26 | staggered basis |  | GoP | 2986926.2 |  |  | 2905909.2 |  |  | NGO | 2021-04-15 | 2021-04-28 | 2021-04-28 | 2021-04-29 | 2021-05-04 | staggered basis
| PROCUREMENT OF 6 WHEELER MINI DUMP TRUCK | PDRRMO | NO | Competitive Bidding | 2021-04-05 | 2021-04-08 | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | 2021-05-06 | 2021-05-07 | 2021-06-25 | 2021-06-28 | ON GOING |  | GoP | 6000000 |  |  | 5900000 |  |  | NGO | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | ON GOING
| PROCUREMENT OF WHEEL LOADER | PDRRMO | NO | Competitive Bidding | 2021-04-05 | 2021-04-08 | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | 2021-05-06 | 2021-05-07 | 2021-06-25 | 2021-06-28 | ON GOING |  | GoP | 6230000 |  |  | 6150000 |  |  | NGO | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | ON GOING
| PROCUREMENT OF 10 WHEELER WATER TANKER | PDRRMO | NO | Competitive Bidding | 2021-04-05 | 2021-04-08 | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | 2021-05-06 | 2021-05-07 | 2021-06-25 | 2021-06-28 | ON GOING |  | GoP | 16280000 |  |  | 16180000 |  |  | NGO | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | ON GOING
| PROCUREMENT OF SKID LOADER | PDRRMO | NO | Competitive Bidding | 2021-04-05 | 2021-04-08 | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | 2021-05-06 | 2021-05-07 | 2021-06-25 | 2021-06-28 | ON GOING |  | GoP | 4400000 |  |  | 4350000 |  |  | NGO | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-04 | ON GOING
| PROCUREMENT OF 6 WHEELER ALUMINUM VAN | PDRRMO | NO | Competitive Bidding | 2021-04-05 | 2021-04-08 | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-06-25 | 2021-06-28 | ON GOING |  | GoP | 6380000 |  |  | 6280000 |  |  | NGO | 2021-04-16 | 2021-04-29 | 2021-04-29 | 2021-04-30 | 2021-05-05 | ON GOING
| PROCUREMENT OF DIPLOMA HOLDER | GOVERNOR'S OFFICE | NO | Competitive Bidding | 2021-04-05 | 2021-04-08 | 2021-04-16 | 2021-04-30 | 2021-04-30 | 2021-05-03 | 2021-05-05 | 2021-05-07 | 2021-05-10 | 2021-06-15 | 2021-06-17 | 2021-07-05 |  | GoP | 24074680 |  |  | 23988699 |  |  | NGO | 2021-04-16 | 2021-04-30 | 2021-04-30 | 2021-05-03 | 2021-05-05 | 2021-07-05
| REPAIR OF SERVICE VEHICLE | PGSO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-23 | N/A | 2021-04-27 |  | GoP | 62760 |  |  | 60790 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-27
| PROCUREMENT OF CERTIFICATE/DIPLOMA | GOVERNOR'S OFFICE | NO | NP-53.9 - Small Value Procurement | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-02 | N/A | 2021-06-16 |  | GoP | 988781.5 |  |  | 404134.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-16
| PROCUREMENT OF FLATBED SCANNER | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-26 | N/A | 2021-05-03 |  | GoP | 90000 |  |  | 88500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-03
| PROCUREMENT OF RABIES VACCINE | PVET | NO | Shopping | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-10 | N/A | 2021-05-18 |  | GoP | 137500 |  |  | 135000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-18
| PROCUREMENT OF AIRCON PARTS | RPHS | NO | Shopping | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-27 | N/A | 2021-05-03 |  | GoP | 53990 |  |  | 51936 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-03
| PROCUREMENT OF REMDESIVIR | PHO | NO | Shopping | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-16 | N/A | 2021-04-21 |  | GoP | 800000 |  |  | 736000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-04-21
| REPAIR OF AIR CONDITIONING SYSTEM | YC | NO | Competitive Bidding | 2021-04-14 | 2021-04-16 | 2021-04-23 | 2021-05-06 | 2021-05-06 | 2021-05-07 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-06-07 | 2021-06-10 | ON GOING |  | GoP | 1920000 |  |  | 1918375 |  |  | NGO | 2021-04-23 | 2021-05-06 | 2021-05-06 | 2021-05-07 | 2021-05-11 | ON GOING
| PROCUREMENT OF LABORATORY SUPPLIES | RPHS | NO | Competitive Bidding | 2021-04-15 | 2021-04-19 | 2021-04-23 | 2021-05-06 | 2021-05-06 | 2021-05-07 | 2021-05-11 | 2021-05-19 | 2021-05-21 | 2021-06-15 | 2021-06-17 | ON GOING |  | GoP | 3551850 |  |  | 2821920 |  |  | NGO | 2021-04-23 | 2021-05-06 | 2021-05-06 | 2021-05-07 | 2021-05-11 | ON GOING
| PROCUREMENT OF JANITORIAL SUPPLIES | PSWD | NO | Shopping | N/A | 2021-04-30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-28 | N/A | 2021-06-02 |  | GoP | 225795 |  |  | 213735 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-02
| REPAIR OF SERVICE VEHICLE | PGSO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-04-08 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-07 | N/A | 2021-05-12 |  | GoP | 55040 |  |  | 53780 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-12
| GEOTECHNICAL INVESTIGATION | PEO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-05-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-13 | N/A | 2021-06-07 |  | GoP | 150000 |  |  | 130480 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-07
| PROCUREMENT OF RISO INK & MASTER ROLL | RPG | NO | Direct Contracting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-05 | N/A | 2021-05-11 | N/A | 2021-05-17 |  | GoP | 684000 |  |  | 631440 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-17
| PROCUREMENT OF OFFICE SUPPLIES | PGSO | NO | Shopping | N/A | 2021-05-06 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-17 | N/A | 2021-05-21 |  | GoP | 943960 |  |  | 924603.5 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-21
| PROCUREMENT OF OFFICE SUPPLIES | GOVERNOR'S OFFICE | NO | Competitive Bidding | 2021-05-03 | 2021-05-06 | 2021-05-13 | 2021-05-26 | 2021-05-26 | 2021-05-27 | 2021-05-31 | 2021-06-02 | 2021-06-03 | 2021-06-22 | 2021-06-24 | ON GOING |  | GoP | 5196339 |  |  | 5055666 |  |  | NGO | 2021-05-13 | 2021-05-26 | 2021-05-26 | 2021-05-27 | 2021-05-31 | ON GOING
| PROCUREMENT OF NFA RICE | PDRRMO | NO | NP-53.5 Agency-to-Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-12 | N/A | N/A | N/A | N/A |  | GoP | 375000 |  |  | 375000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| PROCUREMENT OF TRASH BIN | RPHS | NO | Competitive Bidding | N/A | 2021-05-07 | 2021-05-14 | 2021-05-27 | 2021-05-27 | 2021-06-02 | 2021-06-04 | 2021-06-07 | 2021-06-08 | 2021-06-18 | 2021-06-21 | ON GOING |  | GoP | 1178575 |  |  | 1037440 |  |  | NGO | 2021-05-14 | 2021-05-27 | 2021-05-27 | 2021-06-02 | 2021-06-04 | ON GOING
| PROCUREMENT OF CADAVER BAG | RPHS | NO | Shopping | N/A | 2021-05-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-25 | N/A | 2021-06-03 |  | GoP | 150000 |  |  | 136000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-03
| PROCUREMENT OF CURL CATHETER | RPHS | NO | Shopping | N/A | 2021-05-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-04 | N/A | 2021-06-08 |  | GoP | 225000 |  |  | 213750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-08
| PROCUREMENT OF OXYGEN REGULATOR | RPHS | NO | Shopping | N/A | 2021-05-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-10 | N/A | 2021-06-15 |  | GoP | 350000 |  |  | 300000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-15
| PROCUREMENT OF WOUND DRESSING PACK | RPHS | NO | Shopping | N/A | 2021-05-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-10 | N/A | 2021-06-21 |  | GoP | 100000 |  |  | 76000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-21
| PROCUREMENT OF INDUSTRIAL FAN | PGSO | NO | Shopping | N/A | 2021-05-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-05-28 | N/A | 2021-06-04 |  | GoP | 240000 |  |  | 230400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-04
| PROCUREMENT OF HARDWARE MATERIALS | PGSO | NO | Shopping | N/A | 2021-05-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-14 | N/A | 2021-06-17 |  | GoP | 54790 |  |  | 53300 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-17
| PROCUREMENT OF MILK | PDRRMO | NO | Shopping | N/A | 2021-05-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-09 | N/A | 2021-06-14 |  | GoP | 127200 |  |  | 123000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-14
| PROCUREMENT OF DOCUMENT STORAGE BOX | PGSO | NO | Shopping | N/A | 2021-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-25 | N/A | 2021-06-28 |  | GoP | 140000 |  |  | 139500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-28
[5 empty] | 2021-05-10: Total ABC |  |  | 356226874.35
Total Contract Price | [21 empty] | 322536473.81
| ON-GOING PROCUREMENT ACTIVITIES (CIVIL WORKS) | [20 empty] | 0
3000-000-1-1-31-392-004-052 | 1) Improvement of Multi-Purpose Covered Court at Purok 29 Zone 5, Pag-Asa, Brgy. Mahabang Parang, Angono, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 60 |  | GF | 611430.55 |  | 611430.55 | 0 |  |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-000-1-2-399-006-005 | 2) Repair/Repainting of Multi-PurposeCovered Court (DPWH) at Margarito A. Duavit Memorial High School, Brgy. Pilapila, Binangonan, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 70 |  | SEF | 649629.31 | 649629.31 |  | 642091.66 | 642091.66 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-2-51-001-002-004 | 3) Improvement/Concreting and Construction of Drainage Canal at M.H. Del Pilar St., Sitio Tibagan, Brgy. Libid, Binangonan, Rizal | CANCELLED | [22 empty] | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-003-003 | 4) Improvement of Road at Brgy. Ithan, Binangonan, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 80 |  | GF | 3999729.37 |  | 3999729.37 | 3975128.46 |  | 3975128.46 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-300-1-2-11-51-004-015 | 5) Construction of 2-Storey, Ynares Multi-Purpose Building at Vista Verde Executive Village Phase 4, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 136 |  | GF | 3459499.55 |  | 3459499.55 | 3435901.65 |  | 3435901.65 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-002-042 | 6) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Purok 7, Brgy. Palay-Palay, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 120 |  | GF | 11499257.28 | 11499257.28 |  | 11433273.89 | 11433273.89 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-002-043 | 7) Asphalt Overlaying/Concrete Reblocking (portion) of Borja St., Brgy. 2nd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 60 |  | GF | 1629334.6 | 1629334.6 |  | 1612992.19 | 1612992.19 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-11-51-001-002-045 | 8) Construction of Stone Masonry for Slope Protection (portion) of Felipe Braza Creek at Sitio Naglabas, Brgy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 240 |  | GF | 25049145.19 |  | 25049145.19 | 24950218.6 |  | 24950218.6 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-11-51-001-002-046 | 9) Construction of Stone Masonry for Slope Protection (portion) of Turnina River, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 90 |  | GF | 4599675.56 |  | 4599675.56 | 44573270.39 |  | 44573270.39 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-11-51-001-002-047 | 10) Construction of Stone Masonry for Side Protection (portion) of Creek at Purok 5, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 140 |  | GF | 6989064.74 |  | 6989064.74 | 6956308.31 |  | 6956308.31 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-11-51-001-002-048 | 11) Construction of Stone Masonry for Side Protection (portion) of Creek at Purok 6, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 160 |  | GF | 8999080.72 |  | 8999080.72 | 8960238.56 |  | 8960238.56 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-000-1-2-11-399-006-061 | 12) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Bayugo Elem. School, Jalajala, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 64 |  | SEF | 968433.67 |  | 968433.67 | 953525.92 |  | 953525.92 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-003-025 | 13) Construction of Box Culvert/Drainage Canal at Brgy. San Guillermo & Brgy.Malaya, Morong and Pililla, Rizal a) Construction of Box Culvert at Sitio Labac (R. Mata St.), Brgy. San Guillermo | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 80 |  | GF | 1099836.37 |  | 599872.33 | 1083088.25 |  | 590576.18 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
9000-900-1-2-40-940-001-001-003 | b) Construction of Drainage Canal at Alejandro Street,Brgy. Malaya | [19 empty] | 499964.04 |  |  | 492512.07
8000-000-1-1-51-001-003-009 | 14) Asphalt Overlaying/Concrete Reblocking (portion) of E. Dela Paz Road, Brgy..Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 100 |  | GF | 17997013.11 | 17997013.11 |  | 17916807.3 | 17916807.3 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-003-008 | 15) Asphalt Overlaying at San Geronimo St., Brgy. San Jose, Morong, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 32 |  | GF | 2332341.38 | 2332341.38 |  | 2315223.1 | 2315223.1 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-000-1-2-11-399-006-078 | 16) Construction of 3-Storey, 12-rooms Ynares School Building at Lagundi Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 318 |  | SEF | 36859034.14 |  | 36859034.14 | 36719861.14 |  | 36719861.14 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-002-034 | 17) Asphalt Overlaying/Concrete Reblocking (portion) of M. Bautista St. to J.Paz St., Brgy. Wawa, Pililla, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 100 |  | GF | 6534437.78 | 6534437.78 |  | 6506012.05 | 6506012.05 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-002-032 | 18) Asphalt Overlaying/Concrete Reblocking (portion) of E. Tibay St., Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 60 |  | GF | 8877313.41 | 8877313.41 |  | 866475.89 | 866475.89 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-002-035 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of Bagumbayan-Wawa Market Road (Snakeroad), Brgy. Bagumbayan-Brgy. Wawa, Pililla, Rizal. | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 60 |  | GF | 2579479.5 | 2579479.5 |  | 2563408.84 | 2563408.84 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-002-030 | 20) Construction of Box Culvert at Kinahulugan Creek, Matagbak Feeder Road, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 70 |  | GF | 1499370.6 |  | 1499370.6 | 1485362.2 |  | 1485362.2 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-020-1-2-11-399-006-028 | 21) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court & Stage at Quisao National High School, Brgfy. Quisao, Pililla, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage at Quisao National High School, Brgy. Quisao | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 90 |  | SEF | 1309294.34 | 494510.42 |  | 1294103.08 | 490266.95 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-020-1-2-11-399-006-029 | b) Improvement of Ynares Multi-Purpose Covered Court & Stage at Quisao National High School, Brgy. Quisao | [18 empty] | 814783.92 |  |  | 803836.13
3000-000-1-2-11-51-004-042 | 22) Improvement of 2- Storey Ynares Multi-Purpose Building (Daycare) at Divine Mercy Subd., Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 45 |  | GF | 401839.3 |  | 401839.3 | 391103.08 |  | 391103.08 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-300-1-2-11-399-006-078 | 23) Construction of 4-Storey, 12-Rooms Ynares School Building at Justice Vicente Santiago Elem. School, Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 358 |  | SEF | 38190568.92 |  | 38190568.92 | 38048594.36 |  | 38048594.36 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-300-1-2-11-399-006-045 | 24) Repair/Repainting Ynares School Building at Alas-Asin Elem. School, Sitio, Alas-Asin, Brgy. Daraitan, Tanay, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 80 |  | SEF | 1936883.46 | 1936883.46 |  | 1920557.75 | 1920557.75 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-300-1-2-11-399-006-079 | 25) Construction of 3-Storey, 9-Rooms Ynares School Building at Ilaya Elem. School, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 300 |  | SEF | 26499351.13 |  | 26499351.13 | 26408114.16 |  | 26408114.16 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
8000-000-1-1-51-001-003-022 | 26) Improvement of Taytay-Angono Coastal Road, Taytay, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 90 |  | GF | 6546778.78 |  | 6546778.78 | 6513302.79 |  | 6513302.79 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-300-1-2-11-51-004-051 | 27) Construction of Multi-Purpose Bldg., Brgy. San Gabriel, Teresa, Rizal | PEO |  | Public Bidding |  | 17-23-May-21 | 2021-05-24 |  | 2021-06-07 | 2021-06-10 | 2021-06-21 | 2021-06-24 | 2021-06-25 | 2021-06-29 | 2021-07-06 | 302 |  | GF | 18917343.34 |  | 18917343.34 | 18836184.37 |  | 18836184.37 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17 | 2021-05-17
3000-000-1-1-31-392-004-059 | 1) Rehabilitation/Improvement of Baras Municipal Gymnasium, Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding | 2021-05-28 |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 120 |  | GF | 7200451.05 |  | 7200451.05 | 7165319.64 |  | 7165319.64 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-085 | 2) Repair/Repainting of 1-Storey, 5-rooms, Ynares School Building at Baras-Pinugay Integrated High School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 44 |  | SEF | 801612.57 | 801612.57 |  | 791398.97 | 791398.97 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-086 | 3) Repair/Repainting of 3-Storey, 15-rooms NHA School Building at Painaan Elem. School, Heroes Ville Annex, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 60 |  | SEF | 1242303.17 | 1242303.17 |  | 1228047.64 | 1228047.64 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-088 | 4) Repair/Repainting of 1-Storey, 5-rooms Ynares School Building at Bombong Elem.School, Brgy. Bombong, Binangonan, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 30 |  | SEF | 1152576.52 | 1152576.52 |  | 1137421.67 | 1137421.67 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-089 | 5) Repair/Repainting of Ynares School Building at SapangElem. School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 133 |  | SEF | 1252738.21 | 1252738.21 |  | 1235154.83 | 1235154.83 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-093 | 6) Improvement of Perimeter Fence and Covered Pathwalk at Subay Elem. School, Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 40 |  | SEF | 857316.57 |  | 857316.57 | 846217.64 |  | 846217.64 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-095 | 7) Repair/Repainting of 1-Storey, 3-Rooms Ynares School Building at Subay Elem. School Building at Subay, Cardona, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 38 |  | SEF | 1197299.3 | 1197299.3 |  | 1181105.38 | 1181105.38 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-097 | 8) Extension of 12x24m Ynares Multi-Purpose Covered Court at Bayugo Elem. School, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 88 |  | SEF | 1523481.9 |  | 1523481.9 | 1500216.54 |  | 1500216.54 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-102 | 9) Repair/Repainting of Ynares School Building at Bugarin Elem. School, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 72 |  | SEF | 1699285.78 | 1699285.78 |  | 1684390.76 | 1684390.76 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-108 | 10) Improvement of Ynares Multi-Purpose Covered Court at Silangan National High School, Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 60 |  | SEF | 2280854.87 |  | 2280854.87 | 2265585.83 |  | 2265585.83 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-114 | 11) Construction of Perimeter Fence at Ilaya Elem. School, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 55 |  | SEF | 2154301.79 |  | 2154301.79 | 2138109.69 |  | 2138109.69 | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-115 | 12) Repair/Repainting of Ynares School Building and Ynares Multi-Purpose Covered Court at Brgy. Dalig, Teresa, Rizal a) Repair/Repainting of Ynares School Building at Pantay Elem. School, Brgy. Dalig | PEO |  | Public Bidding |  |  | 31-May-6-Jun-21 |  | 2021-06-21 | 2021-07-28 | 2021-07-08 | 2021-07-13 | 2021-07-14 | 2021-07-16 | 2021-07-23 | 90 |  | SEF | 2275350.4 | 1826825.91 |  | 2256272.04 | 1809492.57 |  | Engr. NELSON A. PAJARILLO & Mr. Warren Simon King | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31
3000-000-1-2-11-399-006-116 | b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Pantay Elem. School, Brgy. Dalig | [18 empty] | 448524.49 |  |  | 446779.47
Total Alloted Budget of On-going Civil Works | [18 empty] | 263672738.23 |  |  | 293790388.62
ON-GOING (GOODS)
| REPAIR OF STATIONARY XRAY MACHINE | RPHS | NO | NP-53.9 - Small Value Procurement | N/A | 2021-05-21 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 90105 |  |  | 81905.6 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF MEDICAL SUPPLIES | RPHS | NO | Competitive Bidding | N/A | 2021-05-27 | 2021-06-03 | 2021-06-16 | 2021-06-16 | 2021-06-17 | 2021-06-21 | 2021-06-23 | 2021-06-24 | ON GOING | ON GOING | ON GOING |  | GoP | 1896500 |  |  | 1874650 |  |  | NGO | 2021-06-03 | 2021-06-16 | 2021-06-16 | 2021-06-17 | 2021-06-21 | ON GOING
| PROCUREMENT OF OFFICE SUPPLIES | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-05-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 159776 |  |  | 132500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF ALCOHOL | PHO | NO | Shopping | N/A | 2021-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-28 | N/A | ON GOING |  | GoP | 80000 |  |  | 78400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF AIRCON PARTS | PGSO | NO | Shopping | N/A | 2021-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 63115 |  |  | 60400 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| TERMITE TREATMENT AND CONTROL SERVICES | RPHS | NO | NP-53.9 - Small Value Procurement | N/A | 2021-06-10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 599168.82 |  |  | 370000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF SHIPPING PERMIT | PVET | NO | NP-53.9 - Small Value Procurement | N/A | 2021-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 192500 |  |  | 187250 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| GEOTECHNICAL INVESTIGATION | PEO | NO | NP-53.9 - Small Value Procurement | N/A | 2021-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 630000 |  |  | 540750 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF KETAMINE | RPHS | NO | Shopping | N/A | 2021-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 156480 |  |  | 144000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF BABY BASSINET | RPHS | NO | Shopping | N/A | 2021-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 200000 |  |  | 18000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF DESKTOP CLONE | GOVERNOR'S OFFICE | NO | Shopping | N/A | 2021-06-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 130000 |  |  | 124000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF MEDICAL EQUIPMENT | RPHS | NO | Shopping | N/A | 2021-06-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 540000 |  |  | 526000 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF PANEL SCREEN | RPHS | NO | Shopping | N/A | 2021-06-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 136000 |  |  | 127500 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF AIRCON PARTS | PGSO | NO | Shopping | N/A | 2021-06-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 60980 |  |  | 57270 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF DRUGS AND MEDICINES | RPHS | NO | Shopping | N/A | 2021-06-27 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 263250 |  |  | 262430 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF HARDWARE MATERIALS | PGSO | NO | Shopping | N/A | 2021-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 81510 |  |  | 78480 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
| PROCUREMENT OF SEEDS | AGRI | NO | Shopping | N/A | 2021-06-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING | N/A | ON GOING |  | GoP | 239233 |  |  | 236900 |  |  | N/A | N/A | N/A | N/A | N/A | N/A | ON GOING
[5 empty] | 2021-06-17: Total ABC |  |  | 5518617.82
[5 empty] | 2021-06-17: TOTAL ON-GOING CONTRACT (GOODS) | [5 empty] | 4900435.6
[20 empty] | Prepared by: |  |  |  | Recommended for Approval by: |  |  |  |  | Approved:
[20 empty] | MA. TERESA E. LASQUETY |  |  |  | Engr. LUISITO G. MUNSOD | [5 empty] | HON. REBECCA A. YNARES
[20 empty] | Head - BAC Secretariat |  |  |  | BAC Chairperson | [5 empty] | Governor