## PMR 2021 AS OF DEC 2021
PROVINCE OF RIZAL PROCUREMENT MONITORING REPORT as of DECEMBER 2021
Code | Procurement | PMO/ | Is this | Mode of | Actual Procurement Activity | [11 empty] | Source | ABC (Php) |  |  | Contract Cost (Php) |  |  | List of | Date of Receipt of Invitation | [5 empty] | Remarks
(UACS/PAP) | Program/Project | End-User | Early Procurement? | Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | BAC Res Date Recom Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | of Funds | Total | MOOE | CO | Total | MOOE | CO | Invited Observers | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (if applicable) | (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
| 1) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Isidro & Brgy. Lunsad, Angono and Binangonan, Rizal a) Improvement of Ynares Multi-Purpose Covered Court at Venus Compound, Brgy. San Isidro b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Lunsad Elem. School, Brgy. Lunsad | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 90 90 | GF SEF | 821,314.86 370,581.23 | 370581.23 | 821314.86 | 811367.55 366,370.47 | 366370.47 | 811367.55 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-063
3000-000-1-2-11-511-004-066
3000-000-1-2-11-511-004-066 | 2) Construction of 2-Storey Multi-Purpose Building at the Village Subd., Brgy. San isidro, Angono, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 18-24-Jun-22 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 139 | GF | 3758123.83 |  | 3758123.83 | 3733108.25 |  | 3733108.25 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-064 3000-000-1-1-31-392-004-065 | 3) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Dalig, Antipolo, City a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Phase 1 Sta. Maria Subd., Brgy. Dalig b) Improvement of Ynares Multi-Purpose Covered Court at Phase 1 Sta. Maria Subd., Brgy. Dalig | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-26 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 60 60 | GF GF | 731,699.21 595,250.15 | 731699.21 | 595250.15 | 720,298.95 590,446.29 |  | 590446.29 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-2-11-399-006-084 3000-000-1-1-31-392-004-066 | 4) Repair/Repainting of Ynares School Building and Ynares Multi-Purpose Covered Court Brgy. Mayamot and Brgy. San Jose, Antipolo, City a) Repair/Repainting of Ynares School Building at Mayamot Elem. Schoo, Brgy. Mayamot b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Sumilang, PCUP-RPG Ville Brgy. San Jose | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 100 100 | GF GF | 2,634,984.73 288,942.16 | 2,634,984.73 288,942.17 |  | 2,360,753.99 274,878.04 | 2,360,753.99 274,878.05 |  | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-21-392-004-067 | 5) Improvement of Ynares Multi-Purpose Covered Court at Carolina Village, Brgy. Sta. Cruz, Antipolo, City. | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 80 | GF | 3564122.85 |  | 3564122.85 | 3541088.95 |  | 3541088.95 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-2-11-399-006-075 | 6) Construction of 4-Storey, 8-Rooms Ynares School Buildings at Binangonan Elem. School, Brgy. Layunan, Binangonan, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 258 | SEF | 23931785.32 |  | 23931785.32 | 23834579.9 |  | 23834579.9 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-068 3000-000-1-1-31-392-004-070 | 7) Repair/Repainting/Rehabilitation of Ynares Multi-Purpose Covered court at Brgy. Janosa and Brgy. Gulod, Binangonan, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered court at Brgy. Janosa b) Repair/Rehabilitation of Electrical System of Ynares Multi-Purpose Covered Court at Brgy. Gulod | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 100 100 | GF GF | 2,569,084.44 318,822.23 | 2,569,084.44 318,822.24 |  | 2,556,209.46 315,161.54 |  | 2,556,209.46 315,161.54 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-069 | 8) Repair of Ynares Multi-Purpose Covered Court and Comfort Room at Mambog, Binangonan, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 61 | GF | 1391196.87 | 1391196.87 |  | 1377347.24 | 1377347.24 |  | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-054 | 9) Concreting of Road at Sapang Malalim, Brgy. Tatala, Binangonan, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 80 | GF | 2070610.91 |  | 2070610.91 | 2053129.81 |  | 2053129.81 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-300-1-2-11-511-004-068 | 10) Construction of 2-Storey Multi-Purpose Building at Golden Mile Subdivision, Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 136 | GF | 3699753.06 |  | 3699753.06 | 3674541.69 |  | 3674541.69 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-073 | 11) Repair/Repainting of Ynares Multi-Purpose Covered Court and Perimeter Fence at Katarungan Village, Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 80 | GF | 1448804.84 |  | 1423749.04 | 1423749.04 |  |  | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392004-074 | 12) Improvement of Ynares Multi-Purpose Covered Court at Katarungan Village, Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 96 | GF | 2.199,745.49 |  | 2.199,745.49 | 2.184,060.15 |  | 2.184,060.15 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-064 | 13) Improvement of Camden St., at Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 180 | GF | 7758543.54 |  | 7758543.54 | 7720735.63 |  | 7720735.63 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-065 | 14) Improvement/Concreting of Bluffton Ave., at Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 100 | GF | 2964306.59 |  | 2964306.59 | 2945119.86 |  | 2945119.86 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-066 | 15) Improvement/Concreting of Los Angeles St., at Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 80 | GF | 1944720.5 |  | 1944720.5 | 1927527.42 |  | 1927527.42 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-067 | 16) Improvement/Concreting of New York St., at Brookside Hills Subd., Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 72 | GF | 1271038.4 |  | 1271038.4 | 1255801.72 |  | 1255801.72 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-071 | 17) Improvement of Ynares Multi-Purpose Covered Court at Vista Verde Exec. Village Phase 3, Brgy. San Isidro, Cainta, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 32 | GF | 1474965.09 |  | 1474965.09 | 1456437.3 |  | 1456437.3 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-073 | 18) Concrete Relocking of M. Bellin St., Brgy. Special District, Jalajala, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 126 | GF | 4599272.96 |  | 4599272.96 | 4569242.12 |  | 4569242.12 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-076 3000-000-1-1-31-392-004-077 | 19) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Maybancal, Morong, Rizal a) Repair/Repainting of Ynares Multi-Purpose Covered Court str Sitio Talaga, Brgy. Maybancal b) Improvement of Ynares Multi-Purpose Covered Court, Sitio Talaga, Brgy. Maybancal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 60 60 | GF GF | 414,841.74 1,611,843.80 | 414841.74 | 1611843.8 | 410,359.89 1,599,857.05 | 410359.89 | 1599857.05 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-082 | 20) Construction of Drainage Canal at MateoSt., Rumagat, Sitio Namay, Brgy. San Juan, Morong, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 72 | GF | 1538061.23 |  | 1538061.23 | 1578053.94 |  | 1578053.94 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-300-1-2-11-511-004-073 | 21) Construction of Fence of Lot (Barangay Property) at Sitio Namay, Brgy. San Juan, Morong, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 64 | GF | 981602.5 |  | 981602.5 | 966704.8 |  | 966704.8 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-2-11-399-006-098 3000-000-1-2-11-399-006-117 | 22) Improvement of Feeding Center and Concreting of School Walkway at Morong, Rizal a) Improvement of Feeding Center at Lagundi CCL National High School b) Concreting of of School Walkway at Lagundi CCL National High School | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 60 60 | GF GF | 675,329.54 323,453.76 |  | 675,329.54 323,453.76 | 668,058.16 309,094.54 |  | 668,058.16 309,094.54 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-2-11-399-006-101 3000-000-1-2-11-399-006-100 | 23) Construction of Garden House, Raincatcher & Flagpole and Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Halayhayin, Pililla, Rizal a) Construction of Garden House, Raincatcher & Flagpole at Bugarin Elem. School, Brgy. Halayhayin b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Halayhayin Elem. School Brgy. Halayhayin | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 90 90 | GF SEF | 377,521.60 619,563.95 | 619563.96 | 377521.6 | 368.856.96 605,187.31 | 605187.32 | 368.856.96 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-51-001-002-084 3000-000-1-1-51-001-002-085 | 24) Construction of Roadway Lightings at Brgy. Bagumbayan, Pililla, Rizal a) Construction of Roadway Lightings at Sitio Paliparan, Brgy. Bagumbayan b) Construction of Roadway Lightings at Daang Mulawin Brgy. Bagumbayan | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 40 40 | GF GF | 2,799,579.93 1,734,694.58 |  | 2,799,579.93 1,734,694.58 | 2,786,911.08 1,721,163.01 |  | 2786911.08 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-300-1-2-11-511-004-074 | 25) Construction of 2-Storey Ynares Multi-Purpose Building at Centella Homes, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 109 | GF | 2530261.44 |  | 2530261.44 | 2513198.76 |  | 2513198.76 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-1-31-392-004-081 | 26) Improvement of Ynares Multi-Purpose Covered Court at Eastwood Residences Phase 4, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 60 | GF | 2152940.19 |  | 2152940.19 | 2136137.5 |  | 2136137.5 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-300-1-2-11-511-004-077 | 27) Construction of 2-Storey Ynares Multi-Purpose Building at Rafaella 2 Subd. Brgy. Ampid 1, San Mateo, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 136 | GF | 3226009.32 |  | 3226009.32 | 3205543.75 |  | 3205543.75 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-300-1-2-11-511-004-081 | 28) Construction of Perimeter Fence of Open Space at Tierra Monte Subd. Brgy. Silangan, San Mateo, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 165 | GF | 2210122.14 |  | 2210122.14 | 2194010.28 |  | 2194010.28 | Engr. Nelson Pajarillo Simon King | 2021-06-18
3000-000-1-2-11-399-006-110 | 29) Repair/Repainting of Ynares School Building at Patricio Jarin Memorial Elem. School, Brgy. San Isidro, Tanay, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 74 | GF | 2983286.32 | 2983286.32 |  | 2963151.28 |  | 2963151.28 | Engr. Nelson Pajarillo Simon King | 2021-06-18
8000-000-1-1-51-001-002-086 | 30) Concreting (portion) of Kay-Taijan Road Sitio Waray, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | PUBLIC BIDDING |  | 18-24-Jun-21 | 2021-06-25 |  | 2021-07-07 | 2021-07-13 | 2021-07-23 | 2021-07-27 | 2021-07-28 | 2021-08-06 | 2021-08-16 | 100 | GF | 2917497.01 |  | 2917497.01 | 2898192.87 |  | 2898192.87 | Engr. Nelson Pajarillo Simon King | 2021-06-18
Engr. Nelson Pajarillo Simon King
3000-000-1-1-31-392-004-065 | 1) Repair/Repainting of Ynares Multi-Purpose Covered Court, Multi-Purpose Bldg. & Perimeter Fence and Upgrading of Electrical System at Brgy. Mahabang Parang, Angono, Rizal. a) Repair/Repainting of Ynares Multi-Purpose Covered Court, Multi-Purpose Bldg. & Perimeter Fence at Grandvalley Subd., Phase 1, Brgy. Mahabang Parang b) Upgrading of Electrical System at Carlos Botong Francisco Mem. National High School Brgy. Mahabang Parang | [22 empty] | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-004-067 |  | PEO |  | Public Bidding |  | 28-June - 4-July-21 |  |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 688360 | 688360 |  | 678837.72 |  | 678837.72 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-083 |  | PEO |  | Public Bidding |  | 28-June - 4-July-21 |  |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 151951.24 | 151951.24 |  | 147724.42 |  | 147724.42 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-00-002-049 | 2) Asphalt Overlaying/Concrete Reblocking (portion) of Dalandan St., Phase III, Brgy. San Roque, Angono. Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 76 | GF | 1648119.7 | 1648119.7 |  | 1633093.37 | 1633093.37 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-00-002-050 | 3) Construction of Roadway Lightings at Sitio Paopawan, Brgy. San Salvador, Baras, Rizal | PEO |  | Public Bidding | 2021-06-28 | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 120 | GF | 11440851.02 |  | 11440851.02 | 11380616.87 |  | 11380616.87 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-0001-2-11-399-006-091 | 4) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene at Sapang Elem. School, Brgy. Sapang, Binangonan, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 72 | SEF | 1258742.42 |  | 1258742.42 | 1240357.73 |  | 1240357.73 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-00-002-055 | 5) Improvement of Roads at Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 60 | GF | 1846106.94 |  | 1846106.94 | 1831009.19 |  | 1831009.19 | Engr. Nelson Pajarillo Simon King | 2021-06-28
6) Construction of Roadway Lightings at Brgy. Janosa, Brgy. Pag-asa, Brgy. Kinagatan, Brgy. Pantok and Brgy. Mambog, Binangonan, Rizal
8000-000-1-1-51-001-002-061 | a) Construction of Roadway Lightings at Brgy. Janosa |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 2122994.17 |  | 2122994.17 | 2109951.41 |  | 2109951.41 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-063 | b) Construction of Roadway Lightings at Sitio Pedro Cruz, Brgy. Pag-asa |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 1768081.96 |  | 1768081.96 | 1758768.32 |  | 1758768.32 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-060 | c) Construction of Roadway Lightings at Brgy. Kinagatan |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 1470227.64 |  | 1470227.64 | 1461225.94 |  | 1461225.94 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-062 | d) Construction of Roadway Lightings at Sitio San Roque, Brgy. Pantok |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 1335256.85 |  | 1335256.85 | 1327057.21 |  | 1327057.21 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-056 | e) Construction of Roadway Lightings at M, Cenidoza St. Brgy. Mambog |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 2347772.14 |  | 2347772.14 | 2334621.55 |  | 2334621.55 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-057 | f) Construction of Roadway Lightings at D. Anore St., Brgy. Mambog |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 1190334.2 |  | 1190334.2 | 1183613.64 |  | 1183613.64 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-058 | g) Construction of Roadway Lightings at I. Certeza St. , Brgy. Mambog | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 872472.53 |  | 872472.53 | 867171.52 |  | 867171.52 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-059 | h) Construction of Roadway Lightings at Teacher’s Village St. Brgy. mambog | PEO |  | Public Bidding | 2021-06-28 | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 150 | GF | 7683760.69 |  | 7683760.69 | 763107.6 |  | 763107.6 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-2-61-100-003-008 | 7) Installation of Lift Structure at the Ynares Event Center, Brgy. San Roque, Antipolo, City | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 60 | GF | 3911652.93 |  | 3911652.93 | 3855551.94 | 3855551.94 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
8) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Ynares Multi-Purpose Building at Brgy. Sto. Domingo and Brgy. Sta. Rosa, Cainta, Rizal
3000-000-1-2-11-399-006-092 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Marick Elem. School, Brgy. Sto. Domingo | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | SEF | 464796.68 | 464796.68 |  | 456667 | 456667 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-511-004-069 | b) Improvement of 2-Storey Ynares Multi-Purpose Bldg. (Brgy. Hall) at Brgy. Sta.Rosa | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 354411.32 |  | 354411.32 | 347540.3 |  | 347540.3 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-072 | 9) Construction of Perimeter Fence for Ynares Multi-Purpose Covered Court at Vista Verde Exec. Village Phase 3, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 50 | GF | 1758466.02 |  | 1758466.02 | 1737358.68 |  | 1737358.68 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-511-004-070 | 10) Construction of Perimeter Fence for Ynares Multi-Purpose Covered Court at DM 2 Subd., Brgy. San Roque, Cainta, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 43 | GF | 678783.89 |  | 678783.89 | 664516.81 |  | 664516.81 | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 11) Construction of Roadway Lightings at Brgy. Boor, & Brgy. Ticulio, Cardona, Rizal | [22 empty] | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-070 | a) Construction of Roadway Lightings at Boor Proper, Brgy. Boor |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 80 | GF | 1232596.7 |  | 1232596.7 | 1220113.99 |  | 1220113.99 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-071 | b) Construction of Roadway Lightings at Boor - Pinagkitran Road, Brgy. Boor |  |  |  |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 80 | GF | 1027009.17 |  | 1027009.17 | 1022232.8 |  | 1022232.8 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-072 | c) Construction of Roadway Lightings at Sitio Pinagkitran, Brgy. Boor | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 80 | GF | 585806.63 |  | 585806.63 | 581026.56 |  | 581026.56 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-069 | d) Construction of Roadway Lightings at Brgy. Ticulio | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 80 | GF | 292058.57 |  | 292058.57 | 289960.67 |  | 289960.67 | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 12) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court and Improvement of Principal’s Office at Brgy. Dalig, Brgy. Ticulio and Brgy. Subay, Cardona, Rizal | [22 empty] | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-075 | a) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court, Brgy. Dalig | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 290414.76 |  | 290414.76 | 280738.29 |  | 280738.29 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-096 | b) Installation of Electrical Lighting System of Ynares Multi-Purpose Covered Court at Ticullo Elem. School, Brgy. Tidullo | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 176527.39 |  | 176527.39 | 175113.88 |  | 175113.88 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-094 | c) Improvement of Principal’s Office at SubayElem. School, Brgy. Subay | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 433313.59 |  | 433313.59 | 427254.52 |  | 427254.52 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-511-004-071 | 13) Repair/Repainting of Various Ynares Waiting Sheds, Jalajala, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 478797.34 | 478797.34 |  | 465645.24 | 465645.24 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-51-004-062 | 14) Construction of Livelihood Training Center, Brgy. 1st District, Jalajala, Rizal | PEO |  | Public Bidding | 2021-06-28 | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 200 | GF | 9994297.44 |  | 9994297.44 | 9939170.54 |  | 9939170.54 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-51-004-072 | 15) Construction of 2-Seater Comfort Room at Sitio Namay, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 60 | GF | 673361.34 |  | 673361.34 | 657115.37 |  | 657115.37 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-002-065 | 16) Construction of Roadway Lighting at Balajadia Extension (Bypas Road), San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 60 | GF | 2347772.14 |  | 2347772.14 | 2331189.19 |  | 2331189.19 | Engr. Nelson Pajarillo Simon King | 2021-06-28
17) Improvement of Ynares Multi-Purpose Covered Court and Construction of Gate & Arc at Brgy. Bagumbayan and Brgy. Halayhayin, Pililla, Rizal
3000-000-1-2-11-399-006-099 | a) Improvement of 17x42m Ynares Multi-Purpose Covered Court at Pililla Elem. School Central, Brgy. Bagumbayan, | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | GF | 572018.67 |  | 572018.67 | 562743.98 |  | 562743.98 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-107 | b) Construction of Gate & Arc at Halayhayin Elem School. Brgy. Halayhayin | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 45 | SEF | 471889.48 |  | 471889.48 | 461912.34 |  | 461912.34 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-106 | 18) Improvement of School Drainage Canal and Perimeter Fence (Portion) at Bugarin Elem. School, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 84 | GF | 873568.61 |  | 873568.61 | 855582.43 |  | 855582.43 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-105 | 19) Repair/Repainting of Ynares School Buildings at Bugarin Elem. School, Brgy. Halayhayin, Pililla, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 56 | SEF | 2083037.94 | 2083037.94 |  | 2060146.78 | 2060146.78 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
20) Repair/Repainting of Ynares School Buildings, Ynares Multi-Purpose Covered Court and Stage at Brgy. Malaya, Pililla. Rizal
3000-000-1-2-11-399-006-104 | a) Repair/Repainting of Ynares School Building at Malaya Integrated National High, Brgy. Malaya | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | SEF | 1762797.24 | 1762797.24 |  | 1743721.96 | 1762797.24 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-399-006-103 | b) Repair/Repainting of Ynares Multi-Purpose B Covered Court and Stage at Malaya Integrated National High School, Brgy. Malaya | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | SEF | 446049.24 | 446049.24 |  | 440061.84 | 440061.84 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
21) Repainting/Repair of Ynares Multi-Purpose Covered Court and Ynares Multi- Purpose Building at Brgy. Balite and Brgy. San Rafael, Rodriguez, Rizal
3000-000-1-1-31-392-004-083 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Balite | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | GF | 1274525.83 | 1274525.83 |  | 1257912.01 | 1257912.01 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-075 | b) Repair/Repainting of 2-Storey Ynares Multi-Purpose Building (Brgy. Annex) at Sitio Wawa, Brgy. San Rafael | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | GF | 385068.18 | 385068.18 |  | 381506.73 | 381506.73 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-082 | 22) Improvement of Ynares Multi-Purpose Covered Court at Greenrose 1 Subd.,Brgy. Geronimo, Rodriguez, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 40 | GF | 782756.48 |  | 782756.48 | 768611.21 | 768611.21 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 23) Repainting/Repair of Ynares Multi-Purpose Covered Court and Construction of Comfort Room at Brgy. San Jose and Brgy. Ampid 1, Rodriguez and San Mateo, | [22 empty] | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-079 | a) Repainting/Repair of Ynares Multi-Purpose Covered Court at Montalban Heights, Brgy. San Jose | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 175 | GF | 1040520.17 | 1040520.17 |  | 1031336.23 | 1031336.23 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-078 | b) Construction of 2-Seater Comfort Room at Rafaela 2 Subd.,Brgy. Ampid 1 | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 175 | GF | 364254.94 |  | 364254.94 | 354334.46 |  | 354334.46 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-511-004-075 | 24) Construction of 2-Storey Ynares Multi-Purpose Building (Health Center), Brgy. Balite, Rodriguez, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 160 | GF | 3731325.06 |  | 3731325.06 | 3705199.57 |  | 3705199.57 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-080 | 25) Repainting/Repair of Ynares Multi-Purpose Covered Court at Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | GF | 1732566.1 | 1732566.1 |  | 1711382.06 | 1711382.06 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-078 | 26) Repair/Repainting of Ynares Multi-Purpose Covered Court/Barangay Hall at Brgy. Puray, Rodriguez, Rizal | [16 empty] | CANCELLED
3000-000-1-1-31-392-004-084 | 27) Repair/Repainting of Ynares Multi-Purpose Covered Court at Graceland Exec. Subd., Brgy. Ampid II, San Mateo, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 48 | GF | 980285.62 | 980285.62 |  | 964058.07 | 964058.07 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-300-1-2-11-511-004-079 | 28) Construction of Ynares Stage at Tierra Monte 2 Subd., Brgy. Silangan, San Mateo, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 78 | GF | 1184750.99 |  | 1184750.99 | 1165782.59 |  | 1184750.99 | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 29) Repair/Repainting of Ynares School Building at Jose F. Diaz Mem. National High School, Brgy. Gulod, Malaya, San Mateo, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 40 | SEF | 1403957.7 | 1403957.7 |  | 1394659.87 | 1394659.87 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 30) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Stage at Brgy. Wawa and Brgy. Plaza Aldea, Tanay, Rizal | [22 empty] | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-392-006-112 | a) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court and Stage at Tanay West National High School, Brgy. Wawa | PEO |  | Public Bidding |  | 28-June - 4-July-22 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | SEF | 340250.66 | 340250.66 |  | 329768.93 | 329768.93 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-392-006-113 | b) Improvement of Ynares Multi-Purpose Covered Court at Tanay West National High School, Brgy. Wawa | PEO |  | Public Bidding |  | 28-June - 4-July-23 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | SEF | 998492.18 | 998492.18 | 994048.45 |  | 994048.45 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-2-11-392-006-111 | c) Repair/Repainting of Ynares School Building at Tanay East National High School, Brgy. Plaza, Aldea | PEO |  | Public Bidding |  | 28-June - 4-July-24 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 100 | SEF | 468292.79 | 468292.79 |  | 994048.45 |  | 994048.45 | Engr. Nelson Pajarillo Simon King | 2021-06-28
3000-000-1-1-31-392-004-085 | 31) Repair/Repainting of Ynares Multi-Purpose Covered Court, Bleachers and Perimeter Fence at Palmera Subd., Phase 6, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 50 | GF | 953962.67 | 953962.67 |  | 936723.43 | 936723.43 |  | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 32) Improvement of Ynares Multi-Purpose Building and Construction of Storage Facility at Brgy. Dolores, Taytay, Rizal | [23 empty] | 2021-06-28
3000-300-1-2-11-511-004-082 | a) Improvement of Ynares Multi-Purpose Building at Palmera Subd., Phase 6, Brgy. Dolores | PEO |  | Public Bidding |  | 28-June - 4-July-22 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 50 | GF | 528181.93 |  | 528181.93 | 515749.08 |  | 515749.08 | Engr. Nelson Pajarillo Simon King | 2021-06-28
8000-000-1-1-51-001-001-003 | b) Construction of Storage Facility for the Office of the Provincial Election Supervisor at the Rizal Provincial Jail Compound, Brgy. Dolores | PEO |  | Public Bidding |  | 28-June - 4-July-23 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 50 | GF | 209138.26 |  | 209138.26 | 206435.05 |  | 206435.05 | Engr. Nelson Pajarillo Simon King | 2021-06-28
| 33} Construction of Municipal Jail Management and Penology Center, Morong, Rizal | PEO |  | Public Bidding | 2021-06-28 | 28-June - 4-July-21 | 2021-07-06 |  | 2021-07-19 | 2021-07-23 | 2021-08-03 | 2021-08-06 | 2021-08-07 | 2021-08-13 | 2021-08-23 | 278 | GF | 14684189.29 |  | 14684189.29 | 14609022.95 |  | 14609022.95 | Engr. Nelson Pajarillo Simon King | 2021-06-28
1000-000-1-1-11-004-005-003 | 1) Construction of Municipal Trial Court at Existing Municipal Compound, Brgy. San Isidro, Angono, Rizal | Principal Engr. |  | Public Bidding |  | 23-29-July-17 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 205 | GF | 9119351.97 |  | 9119351.97 | 9068290.7 |  | 9068290.7 | Engr. Nelson Pajarillo Simon King | 2021-07-24
1000-000-1-1-11-004-005-002 | 2) Construction of PNP Building at the Existing Municipal Compound, Brgy. San Isidro, Angono, Rizal | Principal Engr. |  | Public Bidding |  | 23-29-July-18 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 232 | GF | 15463635.43 |  | 15463635.43 | 15386516.48 |  | 15386516.48 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-101-004 | 3) Construction of Dining Area at Ynares Center Complex, Brgfy. San Roque, Antipolo, City | Principal Engr. |  | Public Bidding |  | 23-29-July-19 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 41 | GF | 2165305.17 |  | 2165305.17 | 2146180.31 |  | 2146180.31 | Engr. Nelson Pajarillo Simon King | 2021-07-24
| 4) Construction of Roadway Lightings at San Salvador, Baras, Rizal | [16 empty] | 2523401.41
8000-000-1-1-51-001--002-051 | a) Construction of Roadway Lightings at Sitio Maynipay, San Salvador | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 80 | GF | 872472.53 |  | 872472.53 | 865546.3 |  | 865546.3 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001--002-052 | b) Construction of Roadway Lightings at Sitio Laguarda, San Salvador | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 80 | GF | 825464.44 |  | 825464.44 | 818917 |  | 818917 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001--002-053 | c) Construction of Roadway Lightings at Sitio Tingting, San Salvador | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 80 | GF | 825464.44 |  | 825464.44 | 818917 |  | 818917 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-003-004 | 5) Improvement (Concreting) of Interconnecting Road at Kasinay St., Brgy. Kalawaan to Quarry Road, Brgy. Pantok, Binangonan, Rizal | Principal Engr. |  | Public Bidding | 2021-07-19 | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 200 | GF | 17199866.32 |  | 17199866.32 | 17166652.21 |  | 17166652.21 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-003-005 | 6) Improvement/Concreting of By-Pass Road at Brgy. Ithan, Binangonan, Rizal | Principal Engr. |  | Public Bidding | 2021-07-19 | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 220 | GF | 23999991.22 |  | 23999991.22 | 23901961.29 |  | 23901961.29 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-004 | 7) Improvement/Concreting of and Const. of Drainage Canal of Road at Sitio Tibagan, Binangonan, Rizal | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 80 | GF | 2799760.18 |  | 2799760.18 | 2777539.99 |  | 2777539.99 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-068 | 8) Construction of Roadway Lightings at Brgy. Navotas, Cardona, Rizal | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 30 | GF | 2854704.93 |  | 2854704.93 | 2829651,68 |  | 2829651,70 | Engr. Nelson Pajarillo Simon King | 2021-07-24
| 9) Construction of Roadway Lightings at Lagundi, Morong, Rizal | [16 empty] | 6921074.59
8000-000-1-1-51-001-002-075 | a) Construction of Roadway Lightings at Javier St., Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 2098994.78 |  | 2098994.78 | 2086150.58 |  | 2086150.58 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-076 | b) Construction of Roadway Lightings at Labangan Dam Road, Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 980415.42 |  | 980415.42 | 975464.24 |  | 975464.24 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-077 | c) Construction of Roadway Lightings at Bitong St., Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 980415.42 |  | 980415.42 | 975464.24 |  | 975464.24 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-078 | d) Construction of Roadway Lightings at Feliciano St., Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 1190334.2 |  | 1190334.2 | 1185784.11 |  | 1185784.11 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-079 | e) Construction of Roadway Lightings at Pugala Road, Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 662093.06 |  | 662093.06 | 658943.52 |  | 658943.52 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-080 | f) Construction of Roadway Lightings at Lanang (Kaytago St.) Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 450840.08 |  | 450840.08 | 444046.37 |  | 444046.37 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-081 | g) Construction of Roadway Lightings at Pinugay Road, Brgy. Lagundi | Principal Engr. |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 90 | GF | 557981.63 |  | 557981.63 | 556292.37 |  | 556292.37 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-039 | 10) Construction of Stone Masonry for Side Protection (portion) of Quisao River, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2021-07-19 | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 160 | GF | 12649509.67 |  | 12649509.67 | 12574246.11 |  | 12574246.11 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-040 | 11) Construction of Stone Masonry for Side Protection (portion) of Barak Crekk, Sitio Barak, Brgy. Quisao, Pililla, Rizal | PEO |  | Public Bidding | 2021-07-19 | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 180 | GF | 15449792.66 |  | 15449792.66 | 15372927.69 |  | 15372927.69 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-041 | 12) Construction of Stone Masonry for Side Protection (portion) of Pililla River, Brgy. Hulo, Pililla, Rizal Construction of Perimeter Fence for Ynares Multi-Purpose | PEO |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 100 | GF | 4999676.54 |  | 4999676.54 | 4972614.72 |  | 4972614.72 | Engr. Nelson Pajarillo Simon King | 2021-07-24
8000-000-1-1-51-001-002-031 | 13) Construction of Stone Masonry for Slope Protection at Manggo River (portion) Rodriguez, Rizal | PEO |  | Public Bidding | 2021-07-19 | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 260 | GF | 29999933.31 |  | 29999933.31 | 29879259.4 |  | 29879259.4 | Engr. Nelson Pajarillo Simon King | 2021-07-24
3000-300-1-2-11-511-004-080 | 14) Construction of 2-Storey Ynares Multi-Purpose Building (Sangguniang Office/Brgy. Library) at Brgy. Sto. Nino, San Mateo, Rizal | PEO |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 175 | GF | 3649543.79 |  | 3649543.79 | 3619071.96 |  | 3619071.96 | Engr. Nelson Pajarillo Simon King | 2021-07-24
3000-300-1-2-11-511-004-049 | 15) Construction of 1-Storey Ynares Multi-Purpose Building at Sitio Manggahan, Brgy. Laiban, Tanay, Rizal | PEO |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 86 | GF | 2288375.12 |  | 2288375.12 | 2270165.86 |  | 2270165.86 | Engr. Nelson Pajarillo Simon King | 2021-07-24
3000-000-1-1-31-392-040-086 | 16) Construction of 17x30m Ynares Multi-Purpose Covered Court at Palmera Phase 3 & 4, Taytay, Rizal | PEO |  | Public Bidding |  | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 128 | GF | 4893133.73 |  | 4893133.73 | 4866092.19 |  | 4866092.19 | Engr. Nelson Pajarillo Simon King | 2021-07-24
3000-300-1-2-11-511-004-065 | 17) Site Development (Phase II) at the Antipolo City Government Center, Sitio Cabading, Brgy. San Jose, Antipolo, City | PEO |  | Public Bidding | 2021-07-19 | 23-29-July-21 | 2021-07-30 |  | 2021-08-11 | 2021-08-17 | 2021-08-27 | 2021-09-02 | 2021-09-03 | 2021-09-10 | 2021-09-20 | 280 | GF | 39999139.46 |  | 39999139.46 | 39819061.21 |  | 39819061.21 | Engr. Nelson Pajarillo Simon King | 2021-07-24
1000-000-1-1-11-004-007-002 | 1) Concreting of Farm to Market Road, Barangay Puray, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 180 | TF | 19999154.23 |  | 19999154.23 | 19904.64 |  | 19904.64 | Engr. Nelson Pajarillo Simon King | 2021-07-30
1000-000-1-1-11-004-007-001 | 2) Imp/Concreting of Farm to Market Road, Barangay Macabud, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 200 | TF | 19999999.62 |  | 19999999.62 | 19899991.11 |  | 19899991.11 | Engr. Nelson Pajarillo Simon King | 2021-07-30
1000-000-1-1-11-004-007-003 | 3) Reconstruction of Stone Masonry for Side Protection at Lanatin River (Damage by Typhoon Ulysses last Nov. 12, 2020), Barangay Sta. Ines, Tanay, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 120 | TF | 9999470.37 |  | 9999470.37 | 9944190.64 |  | 9944190.64 | Engr. Nelson Pajarillo Simon King | 2021-07-30
1000-000-1-1-11-004-007-004 | 4) Concreting of Farm to Market Road, (Tinucan Boundary-Sta. Ines Road), Barangay Sta. Ines, Tanay, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 120 | TF | 6999183.88 |  | 6999183.88 | 6964719.38 |  | 6964719.38 | Engr. Nelson Pajarillo Simon King | 2021-07-30
1000-000-1-1-11-004-007-005 | 5) Construction of One StoreyMulti-Purpose Building (Health Center), Barangay Sta. Ines, Tanay, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 86 | TF | 2999659.56 |  | 2999659.56 | 2973128.87 |  | 2973128.87 | Engr. Nelson Pajarillo Simon King | 2021-07-30
9000-900-1-2-40-940-001-001 | 6) Rehabilitation of Pahati St. near Philsin Bridge (Along Teresa River) Teresa, Rizal, Barangay Dalig, Teresa, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 160 | TF | 5705926.59 |  | 5705926.59 | 5674060.77 |  | 5674060.77 | Engr. Nelson Pajarillo Simon King | 2021-07-30
9000-900-1-2-40-940-001-014 | 7) Rehabilitation of Stone Masonry for Side Protection of Lanatin River and Maysawa River, Barangay Laiban, Tanay, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 120 | TF | 8062925.41 |  | 8062925.41 | 7973355.27 |  | 7973355.27 | Engr. Nelson Pajarillo Simon King | 2021-07-30
9000-900-1-2-40-940-001-015 | 8) Rehabilitation of Stone Masonry for Side Protection (portion) of Mascap River, Barangay Mascap, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-07-30 |  | 2021-08-10 |  | 2021-08-23 | 2021-08-27 | 2021-09-07 | 2021-09-10 | 2021-09-14 | 2021-09-20 | 2021-09-29 | 88 | TF | 5999742 |  | 5999742 | 5968175.47 |  | 5968175.47 | Engr. Nelson Pajarillo Simon King | 2021-07-30
[18 empty] | 79766061.66 |  |  | 79302243.61
3000-000-1-2-11-399-006-120 | 1) Repair/Repainting of Ynares School Building at URS Angono Campus, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 103 | GF | 4211955.7 | 4211955.7 |  | 4182910.67 | 4182910.67 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-001-005 | 2) Construction of Perimeter Fence at GSO Warehouse, Ynares Compound, Antipolo City | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 31 | GF | 799920.36 |  | 799920.36 | 784915.85 |  | 784915.85 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-088 | 3) Construction of 17x30m Ynares Multi-Purpose Covered Court at Brgy. Calumpang, Binangonan, Rizal | PEO |  | Public Bidding | 2021-08-20 | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 138 | GF | 6454659.82 |  | 6454659.82 | 6409016.24 |  | 6409016.24 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-300-1-2-11-511-004-084 | 4) Construction 2-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Antolines Street, Brgy. Calumpang, Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 156 | GF | 4254051.21 |  | 4254051.21 | 4212785.66 |  | 4212785.66 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-089 | 5) Repair/Repainting of Ynares Multi-Purpose Covered Court at Sitio Tolentino, Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 40 | GF | 1527588.82 | 1527588.82 |  | 1506338.73 | 1506338.73 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-094 | 6) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 50 | GF | 1743933.27 | 1743933.27 |  | 1724655.61 | 1724655.61 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-088 | 7) Concreting of Road (portion) at San Clemente Village 1, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 120 | GF | 2452413.98 |  | 2452413.98 | 2429695.17 |  | 2429695.17 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-087 | 8) Improvement of Ynares Multi-Purpose Covered Court at Grandview Homes I, Sitio San Jose, Brgy. Bilibiran, Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 80 | GF | 2126495.57 |  | 2126495.57 | 2100941.72 |  | 2100941.72 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-091 | 9) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Gulod, Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 56 | GF | 1031555.92 |  | 1031555.92 | 1011028.08 |  | 1011028.08 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-092 | 10) Improvement of Ynares Multi-Purpose Covered Court at Brgy. Tatala. Binangonan, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 88 | GF | 1303944.52 |  | 1303944.52 | 1280351.06 |  | 1280351.06 | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-003-006 | 11) Asphalt Overlaying/Concrete Reblocking (portion) of Various Roads at Mercedes Executive Village, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding | 2021-08-20 | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 120 | GF | 29892487.04 | 29892487.04 |  | 29892487.04 | 29892487.04 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-095 | 12) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage at Greenpark Zone 6, Brgy. San Isidro, Cainta, Rizal 13) Construction of perimeter Fence at Cainta Greenpark Village Zone, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 21 | GF | 1021153.77 | 1021153.77 |  | 1003031.38 | 1021153.77 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-11-511-004-085 | 13) Construction of perimeter Fence at Cainta Greenpark Village Zone, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 25 | GF | 1182120.08 |  | 1182120.08 | 1160417.61 |  | 1160417.61 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-096 | 14) Improvement of Ynares Multi-Purpose Covered Court and Fence at Mercedes Executive Village, Brgy.San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 56 | GF | 1361081.56 |  | 1361081.56 | 1376006.51 |  | 1376006.51 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-053 | 15) Construction of Ynares Multi-Purpose Covered Court at Mercedes Executive Village Phase 2, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 110 | GF | 4499106.93 |  | 4499106.93 | 4474085.65 |  | 4474085.65 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-167 | 16) Construction of 15x24m Ynares Multi-Purpose Covered Court (Rafter Type) at Eusebio C. Ocampo Memorial School, Brgy. Lambac, Cardona, Rizal 17) Construction of 12x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Tuna Balibago National High School, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 140 | GF | 4449403.38 |  | 4449403.38 | 4419191.02 |  | 4419191.02 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-166 | 17) Construction of 12x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Tuna Balibago National High School, Brgy. Balibago, Cardona, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 112 | GF | 3449175.7 |  | 3449175.7 | 3422015.53 |  | 3422015.53 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-11-511-004-087 | 18) Construction of Stage at Sitio Pulong Ligaya, Brgy.Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 68 | GF | 11110007.69 |  | 11110007.69 | 1088383.49 |  | 1088383.49 | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-089 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of MabiniSt., Brgy. Lubo, Jalajala, Rizal 20) Improvement of J. Luna St., Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 60 | GF | 4014134.1 | 4014134.1 |  | 3988415.53 | 3988415.53 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-090 | 20) Improvement of J. Luna St., Brgy. Lubo, Jalajala, Rizal | PEO |  | Public Bidding | 2021-08-20 | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 100 | GF | 7510497.98 |  | 7510497.98 | 7460869.44 |  | 7460869.44 | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-091 | 21) Asphalt Overlayingat Pag-Asa Street, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 40 | GF | 1575268.81 | 1575268.81 |  | 1552938.67 | 1552938.67 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-110 | 22) Construction of Open Basketball Court at Sitio Swampalukan, Brgfy. Pagkalinawan, Jalajala, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 52 | GF | 3099656.33 |  | 3099656.33 | 3075215.3 |  | 3075215.3 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-100 | 23) Construction of Ynares Multi-Purpose Covered Court at Sitio Wawa, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 120 | GF | 6239079.24 |  | 6239079.24 | 6191199.37 |  | 6191199.37 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-101 | 24) Improvement of ynares Multi-Purpose Covered Court and Fence at Brgy. Imatong, Pililla, Rizal 25) Construction of Perimeter Fence at Brgy. Mabolo, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 47 | GF | 799894.21 |  | 799894.21 | 782221.74 |  | 782221.74 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-300-1-2-11-511-004-093 | 25) Construction of Perimeter Fence at Brgy. Mabolo, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 88 | GF | 2638604.54 |  | 2638604.54 | 2661330.32 |  | 2661330.32 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-106 | 26) Construction of 13x30m Ynares Multi-Purpose Covered Court (Rafter Type) at Banker’s Village V. Phase 9, Brgy. Guitnang Bayan 1, San Mateo, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 100 | GF | 4383678.63 |  | 4383678.63 | 4356165.49 |  | 4356165.49 | Engr. Nelson Pajarillo Simon King | 2021-08-23
9000-900-1-2-40-940-001-001-010 | 27) Rehabilitation/Improvement of Drainage Canal at Daang Bakal Road (GSIS), Brgy. Banaba to Kambal Road, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding | 2021-08-20 | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 180 | GF | 17999915.33 |  | 17999915.33 | 17914322.29 |  | 17914322.29 | Engr. Nelson Pajarillo Simon King | 2021-08-23
28) Repair/Repainting of Ynares Multi-Purpose Covered Court/Ynares Multi-Purpose
3000-000-1-1-31-392-004-109 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Laiban | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 80 | GF | 980407.3 | 980407.3 |  | 963668.85 | 963668.85 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-300-1-2-11-511-004-097 | b) Repair/Repainting of 1-Storey Ynares Multi-Purpose Building (Brgy. Hall) at Brgy. Laiban | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 80 | GF | 346564.73 | 346564.73 |  | 339218.33 | 339218.33 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-092 | 29) Concreting of Block 19 Purok 2, Lupang Arenda, Brgy. Sta Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 100 | GF | 2472477.95 |  | 2472477.95 | 2442396.39 |  | 2442396.39 | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-093 | 30) Concreting of Block 20 Purok 2, Lupang Arenda, Brgy. Sta Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 100 | GF | 2450166.12 |  | 2450166.12 | 2424083.61 |  | 2424083.61 | Engr. Nelson Pajarillo Simon King | 2021-08-23
8000-000-1-1-51-001-002-094 | 31) Rehabilitation of Drainage Canal at F. Gonzales St., Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding | 2021-08-20 | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 180 | GF | 8299594.78 |  | 8299594.78 | 8248752.01 |  | 8248752.01 | Engr. Nelson Pajarillo Simon King | 2021-08-23
9000-300-1-2-11-511-004-099 | 32) Construction of 2-Storey Ynares Multi-Purpose Bldg. (Health Center) at Carissa Homes East II, Brgy. San Gabriel, Teresa, Rizal | PEO |  | Public Bidding |  | 23-29-Aug-21 | 2021-08-31 |  | 2021-09-13 | 2021-09-17 | 2021-09-28 | 2021-10-01 | 2021-10-04 | 2021-10-08 | 2021-10-14 | 157 | GF | 3974502.01 |  | 3974502.01 | 3947831.82 |  | 3947831.82 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-123 | 1) Repair/Repainting of Ynares Multi-Purpose Covered Court at Evangelista Elem. School, Brgy. Evangelista, Baras, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 40 | SEF | 730162.75 | 730162.75 |  | 714097.92 | 714097.92 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-121 | 2) Repair/Repainting of Ynares School Building at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 33 | SEF | 166966.89 | 166966.89 |  | 1647813.54 | 1647813.54 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-126 | 3) Repair/Repainting of 2-Storey, 6-Rooms Ynares School Building (Senior High School) at Baras Elem. School, Brgy. Concepcion, Baras, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 45 | SEF | 1399130.91 | 1399130.91 |  | 1382093.51 | 1382093.51 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-133 | 4) Repair/Repainting of Ynares Multi-Purpose Covered Court, Stage and Covered Pathwalk at Don Jose M. Ynares, Sr. Mem. National High School, Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 100 | SEF | 3160231.2 | 3160231.2 |  | 3135107.48 | 3135107.48 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
5) Repair/Repainting of Ynares Multi-Purpose Covered Court/Ynares Stage and Construction of School Signage at Brgy. Gulod, Brgy. Sapang and Brgy. Tabon, Binangonan, Rizal
3000-000-1-1-31-392-004-091 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Gulod | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 90 | GF | 528761.25 | 528761.25 |  | 516663.36 | 516663.36 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-127 | b) Repair/Repainting of Ynares Stage at Sapang Elem. School, Brgy. Sapang | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 90 | SEF | 324967.73 | 324967.73 |  | 323678.36 | 323678.36 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-128 | c) Construction of School Signage at Tabon Elem. School, Brgy. Tabon | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 90 | GF | 274622.62 |  | 274622.62 | 266773.63 |  | 266773.63 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-130 | 6) Repair/Repainting of Ynares School Buildings at Talim Elem. School, Brgy. Rayap, Binangonan, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 62 | SEF | 2485320.79 | 2485320.79 | 2457071.61 | 2457071.61 |  |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-134 | 7) Repair/Repainting of Ynares School Buildings at Don Jose M. Ynares Sr. Mem. National High School, Brgy. San Carlos, Binangonan, Rizal | PEO |  | Public Bidding | 2021-08-23 | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 163 | SEF | 8815291.61 | 8815291.61 | 8767106.08 | 8767106.08 |  |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-129 | 8) Repair/Repainting of School Buildings at Pinagdilawan Elem. School, Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding | 2021-08-23 | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 166 | SEF | 6277827.09 | 6277827.09 | 6235459.6 | 6235459.6 |  |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-131 | 9) Repair/Repainting of Ynares School Buildings at Darangan Elem. School, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 150 | SEF | 4639614.13 | 4639614.13 | 4610520.1 | 4610520.1 |  |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
10) Repair/Repainting of Ynares Multi-Purpose Covered Court/Ynares Multi-Purpose Building at Brgy. Darangan and brgy. Tayuman, Binangonan, Rizal
3000-000-1-2-11-399-006-132 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Darangan Elem. School, Brgy. Darangan | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 62 | SEF | 549423.67 | 549423.67 |  | 539733.64 | 539733.64 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-300-1-2-11-511-004-083 | b) Repair/Repainting of 2-Storey Ynares Multi-Purpose Bldg. at Brgy. Tayuman | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 62 | GF | 712446.97 | 712446.97 |  | 698881.01 | 698881.01 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
| 11) Repair/Repainting of Ynares Multi-Purpose Covered Court & Construction of Covered Pathwalk at Pag-Asa National High School, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding
3000-000-1-2-11-399-006-118 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Pag-Asa National High School, Brgy. Pag-Asa | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 84 | SEF | 529884.62 | 529884.62 |  | 513710.56 | 513710.56 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-119 | b) Construction of Covered Pathwalk at Pag-Asa National High School, Brgy. Pag-Asa | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 84 | SEF | 669723.84 |  | 669723.84 | 663808.97 |  | 663808.97 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-136 | 12) Repair/Repainting of 2-Storey 4-Rooms Ynares School Bldg. at Balanti Elem. School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 48 | SEF | 949652.17 | 949652.17 |  | 931555.4 | 931555.4 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-137 | 13) Repair/Repainting of Ynares School Bldgs. Balanti Unit-I Elem. School, Brgy. San Isidro, Cainta, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 68 | SEF | 1429234.37 | 1429234.37 |  | 1404110.57 | 1404110.57 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-138 | 14) Repair/Repainting of 3-Storey 9-Rooms Ynares School Building at Francisco P. Felix Elem. School, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 72 | SEF | 776582.19 | 776582.19 |  | 760562.19 | 760562.19 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-135 | 15) Repair/Repainting of School Buildings at Planters Elem. School, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 1122144.6 | 1122144.6 |  | 1105046.72 | 1105046.72 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-139 | 16) Repair/Repainting of Ynares School Bldgs. At Bayugo Elem. School, Brgy. Bayugo, Jalajala, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 64 | SEF | 1150959.4 | 1150959.4 |  | 1131867.76 | 1131867.76 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
17) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage and Provision of Movable Bleachers at Brgy. Lubo and Brgy. Bagumbong, Jalajala, Rizal
3000-000-1-2-11-399-006-141 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Lubo Elem. School, Brgy. Lubo | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 72 | SEF | 547922.41 | 547922.41 |  | 536183.34 | 536183.34 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-140 | b) Provision of Movable Bleachers at Bagumbong Elem. School, Brgy. Bagumbong | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 72 | GF | 509575.7 |  | 509575.7 | 503133.76 |  | 503133.76 | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-142 | 18) Repair/Repainting of Ynares School Buildings at Morong National High School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding | 2021-08-23 | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 240 | SEF | 8194990.16 | 8194990.16 |  | 8141795.57 | 8141795.57 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-143 | 19) Repair/Repainting of Ynares School Buildings at Pulong Kumanoy Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding | 2021-08-23 | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 95 | SEF | 5185930.77 | 5185930.77 |  | 5137731.84 | 5137731.84 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-144 | 20) Repair/Repainting of 1-Storey 6-Rooms Ynares School Buildings at Timoteo A. Reyes Sr. Memorial Elem. School, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 27-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 45 | SEF | 1797657.44 | 1797657.44 |  | 1776415.81 | 1776415.81 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
21) Repair/Repainting of Ynares School Bldg. at Brgy. Halayhayin and Brgy. Takungan, Pililla, Rizal
3000-000-1-2-11-399-006-146 | a) Repair/Repainting of 2-Storey 4-Rooms Ynares School Bldg. at Bugarin Elem. School, Brgy. Halayhayin | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 860498.83 | 860498.83 |  | 838573.5 | 838573.5 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-145 | b) Repair/Repainting of 2-Storey 6-Rooms Ynares School Bldg. at Virgilio B. Melendres Mem. Elem. School, Brgy. Takungan | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 424811.78 | 424811.78 |  | 424811.78 | 424811.78 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
| 22) Repair/Repainting of Ynares Multi-Purpose Covered Court & CHB Fence (portion) at Brgy. San Isidro, Rodriguez, Rizal | [22 empty] | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-1-31-392-004-102 | a) Repainting of Ynares Multi-Purpose Covered Court at Eastwood Residences Phase 2, Brgy. San Isidro | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | GF | 470701.82 | 470701.82 |  | 459618.93 | 459618.93 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-148 | b) Repainting/ Repair of Ynares Multi-Purpose Covered Court & CHB Fence (portion) at San Isidro National High School, Brgy. San Isidro | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 421103.37 | 421103.37 |  | 414243.94 | 414243.94 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-149 | 23) Repair/Repainting of Ynares School Bldgs. at Macaingalan National High School, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 1062706.95 | 1062706.95 |  | 1040507 | 1040507 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
24) Repainting/Repair of Ynares Multi-Purpose Building/Ynares Multi-Purpose Covered Court and Stage at Brgy. San Isidro and Brgy. San Jose, Rodriguez, Rizal
3000-300-1-2-11-511-004-091 | a) Repainting/Repair of 2-Storey Ynares Multi-Purpose Building at Eastwood Residences Phase 7-7A, Brgy. San Isidro | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 64 | GF | 307843.93 | 307843.93 |  | 298635.36 | 298635.36 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-151 | b) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at San Jose National High School, Brgy. San Jose | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 64 | SEF | 586617.77 | 586617.77 |  | 575659.16 | 575659.16 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-147 | 25) Repainting/Repair of Ynares School Bldgs. at San Isidro National High School, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 1447263.34 | 1447263.34 |  | 1425165.87 | 1425165.87 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-150 | 26) Repair/Repainting of Ynares School Bldg. at San Jose National High School, Brgy. San Jose, Rofriguez, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 76 | SEF | 2235242.57 | 2235242.57 |  | 2210113.46 | 2210113.46 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
27) Repair/Repainting of Ynares School Bldgs./Ynares Multi-Purpose Covered Court at Brgy. Banaba, San Mateo, Rizal
3000-000-1-2-11-399-006-153 | a) Repair/Repainting of Ynares School Bldgs. at Banaba Elem. School, Brgy. Banaba | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 856999.44 | 856999.44 |  | 838219.91 | 838219.91 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-154 | b) Repair/Repainting of Ynares Multi-Purpose Covered Court at Banaba Elem. School, Brgy. Banaba | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 60 | SEF | 180546.51 | 180546.51 |  | 176644.3 | 176644.3 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-155 | 28) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at San Mateo National High School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 64 | SEF | 1188413.43 | 1188413.43 |  | 1162317.96 | 1162317.96 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-156 | 29) Repair/Repainting of Ynares Multi-Purpose Covered Court (Rafter Type) at Ilaya Elem. School, Brgy. Tandang-Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 40 | SEF | 1077780.1 | 1077780.1 |  | 1055642.01 | 1055642.01 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-161 | 30) Repair/Repainting of 2-Storey 6-Rooms Ynares School Building at Benjamin B. Esguerra Mem. National High School (Annex), Highway 2000, Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 50 | SEF | 1767835.54 | 1767835.54 |  | 1738711.78 | 1738711.78 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-162 | 31) Repair/Repainting of School Buildings at Benjamin B. Esguerra Mem. National High School (Main Campus), Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding | 2021-08-23 | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 110 | SEF | 5330851.2 | 5330851.2 |  | 5276709.65 | 5276709.65 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-162 | 32) Repair/Repainting of Ynares Multi-Purpose Covered Court at Benjamin B. Esguerra Mem. National High School (Annex) Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 91 | SEF | 1832622.23 | 1832622.23 |  | 1801511.7 | 1801511.7 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-165 | 33) Repair/Repainting of Ynares School Buildings at Teresa Elem. School, Brgy. Dalig | PEO |  | Public Bidding | 2021-08-23 | 26-Aug -2-Sept-21 | 2021-09-03 |  | 2021-09-17 | 2021-09-23 | 2021-10-04 | 2021-10-07 | 2021-10-08 | 2021-10-15 | 2021-10-22 | 130 | SEF | 6437658.81 | 6437658.81 |  | 6386509.61 | 6386509.61 |  | Engr. Nelson Pajarillo Simon King | 2021-08-23
3000-000-1-2-11-399-006-122 | 1) Construction/Improvement of Perimeter Fence, Gate and Concrete Arc at Doña Justa Guido Mem. School, Brgy. San Roque, Angono, Rizal | PEO |  | Public Bidding | 2021-09-03 | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 120 | SEF | 5538730.57 |  | 5538730.57 | 5487730.63 |  | 5487730.63 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-124 | 2) Construction of Perimeter Fence (portion) at Baras-Pinugay National High School (Phase 2), Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | SEF | 919551.06 |  | 919551.06 | 899415 |  | 899415 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-170 | 3) Construction of Covered Pathwalk at Painaan Elem. School, Heroes Ville Annex, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 52 | SEF | 775577.4 |  | 775577.4 | 758719.03 |  | 758719.03 | Engr. Nelson Pajarillo Simon King | 2021-10-22
1000-000-1-1-11-004-002-025 | 4) Improvement of Office/Building of Rizal Provincial Mobile Force Company, Third Maneuver Platoon at Brgy. San Juan, Baras, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 93 | GF | 2842710.68 |  | 2842710.68 | 2813869.67 |  | 2813869.67 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-093 | 5) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Tatala, Binangonan, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 70 | GF | 712511.29 | 712511.29 |  | 696488.39 | 696488.39 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
| 6) Repair/Repainting/Rehabilitation of Ynares Multi-Purpose Covered Court and Ynares Stage at Brgy. San Andres and Brgy. San Roque, Cainta, Rizal | [23 empty] | 2021-10-22
3000-000-1-1-31-392-004-097 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court and Ynares Stage at DM 5 Subd., Brgy. San Andres | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | GF | 1161745.62 | 1161745.62 |  | 1146431.31 | 1146431.31 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-099 | b) Rehabilitation of Electrical Lighting System of Ynares Multi-Purpose Covered Court & Repainting of Ynares Stage at DM 2 Subd., Brgy. San Roque | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | GF | 445696.32 | 445696.32 |  | 438922.52 | 438922.52 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-098 | 7) Repair/Repainting of Ynares Multi-Purpose Covered Court at ESLA, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 43 | GF | 671334.13 | 671334.13 |  | 657138.1 | 657138.1 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
8) Repair/Repainting/Improvement of Multi-Purpose Bldg. at Brgy. Malaya, Pililla, Rizal
3000-300-1-2-11-511-004-088 | a) Repair/Repainting of 2-Storey Multi-Purpose Bldg. (Brgy. Hall), at Brgy. Malaya | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | GF | 369916.09 | 369916.09 |  | 360687.15 | 360687.15 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-089 | b) Improvement of 1-Storey Multi-Purpose Bldg. (Health Center), at Brgy. Malaya | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | GF | 472732.59 |  | 472732.59 | 462842.78 |  | 462842.78 | Engr. Nelson Pajarillo Simon King | 2021-10-22
9) Improvement/Repainting/Repair of Ynares Multi-Purpose Covered Court/Ynares Multi-Purpose Building at Brgy. San Isidro and Brgy. Rosario, Rodriguez, Rizal
3000-000-1-1-31-392-004-102 | a) Improvement of Ynares Multi-Purpose Covered Court at Eastwood Residences Phase 2, Brgy. San Isidro | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 83 | GF | 857667.37 |  | 857667.37 | 835928.65 |  | 835928.65 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-094 | b) Repainting/Repair of 2-Storey Ynares Multi-Purpose Building at Brgy. Rosario | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 83 | GF | 411779.27 | 411779.27 |  | 409482.94 | 409482.94 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-104 | 10) Construction of 10x18m Ynares Multi-Purpose Covered Court (Rafter Type) at Sitio Mabolo, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 112 | GF | 2555037.68 |  | 2555037.68 | 2527183.69 |  | 2527183.69 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-105 | 11) Repair/Repainting of Multi-Purpose Covered Court at Sitio Wawa, Brgy. San Rafael, Rodriguez, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 90 | GF | 1730291.54 | 1730291.54 |  | 1704100.85 | 1704100.85 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-092 | 12) Construction of Stage at Eastwood Residences Phase 2, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 68 | GF | 982031.27 |  | 982031.27 | 958603.39 |  | 958603.39 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-096 | 13) Improvement of 2-Storey Ynares Multi-Purpose Building, BADAC, and Tanod Office at Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 65 | GF | 1649758.6 |  | 1649758.6 | 1634584.3 |  | 1634584.3 | Engr. Nelson Pajarillo Simon King | 2021-10-22
14) Repair/Repainting of Ynares Multi-Purpose Building at Brgy. Rosario and Brgy. Manggahan, Rodriguez, Rizal
3000-300-1-2-11-511-004-095 | a) Repair/Repainting of 1-Storey Ynares Multi-Purpose Building (Health Center) at Brgy. Rosario | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 79 | GF | 895408.28 | 895408.28 |  | 881717.3 | 881717.3 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-090 | b) Repainting/Repair of 1-Storey Ynares Multi-Purpose Building (Day Care Center) at Brgy. Manggahan | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 79 | GF | 134282.35 | 134282.35 |  | 128778.03 | 128778.03 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
15) Improvement/Repair/Repainting of Diaz Multi-Purpose Covered Court at Bancom Life Homes , Brgy. Gulod Malaya, San Mateo, Rizal
3000-000-1-1-31-392-004-107 | a) Improvement of Diaz Multi-Purpose Covered Court at Bancom Life Homes, Brgy. Gulod Malaya | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 118 | GF | 1523718.28 |  | 1523718.28 | 1507575.67 |  | 1507575.67 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-108 | b) Repair/Repainting of Diaz Multi-Purpose Covered Court at Bancom Life Homes, Brgy. Gulod Malaya | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 118 | GF | 2219053.26 | 2219053.26 |  | 2209044.19 | 2209044.19 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-152 | 16) Construction of Covered Pathwalk at san Mateo Sr. High School, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | SEF | 1108999.36 |  | 1108999.36 | 1086558.27 |  | 1086558.27 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-158 | 17) Construction of Ynares Multi-Purpose Covered Court at Rawang Elem. School, Brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 100 | SEF | 4113684.95 |  | 4113684.95 | 4085180.42 |  | 4085180.42 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-157 | 18) Construction of Ynares Stage at Rawang Elem. School, brgy. Tandang Kutyo, Tanay, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 30 | SEF | 1204893.45 |  | 1204893.45 | 1183488.8 |  | 1183488.8 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-11-51-001-001-008 | 19) Improvement of Building formerly occupied by the Rizal Chamber of Commerce & Industry at Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 59 | GF | 956779.57 |  | 956779.57 | 935755.59 |  | 935755.59 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-163 | 20) Construction/Improvement of Perimeter Fence and Steel Arc at Benjamin B. Esguerra Mem. National High School (Main Campus), Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 95 | SEF | 2229238.94 |  | 2229238.94 | 2200198.1 |  | 2200198.1 | Engr. Nelson Pajarillo Simon King | 2021-10-22
21) Improvement/Repair/Repainting of Ynares Multi-Purpose Covered Court/Multi-Purpose Building at Brgy. Dalig and Brgy. Poblacion, Teresa, Rizal
3000-000-1-2-11-399-006-164 | a) Improvement of Ynares Multi-Purpose Covered Court at Pantay Elem. School, Brgy. Dalig | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | SEF | 882559.63 |  | 882559.63 | 866718.5 |  | 866718.5 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-098 | b) Repair/Repainting of 2-Storey Multi-Purpose Building (Brgy. Hall) at Brgy. Poblacion | PEO |  | Public Bidding |  | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 60 | SEF | 419848.92 | 419848.92 |  | 409582.91 | 409582.91 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-003-025 | 22) Construction of Municipal Building Annex/Extension at Municipal Hall Compound, rBrgy. Poblacion, Teresa, Rizal | PEO |  | Public Bidding | 2021-09-03 | 6-12-Sep-21 | 2021-09-13 |  | 2021-09-27 | 2021-10-04 | 2021-10-15 | 2021-10-20 | 2021-10-21 | 2021-10-29 | 2021-11-05 | 320 | GF | 19759820.59 |  | 19759820.59 | 19660709.11 |  | 19660709.11 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-168 | 1) Construction of Covered Pathwalk at San Vicente Elem. School, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 118 | SEF | 2285346.11 |  | 2285346.11 | 2258211 |  | 2258211 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-102 | 2) Construction of 2-Storey Ynares Multi-Purpose Building (Day Care Center) at Antolines St., Brgy. Calumpamg, Binangonan, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 156 | GF | 4246460.08 |  | 4246460.08 | 4215391.59 |  | 4215391.59 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-101 | 3) Concreting of Road with Drainage Canal at Purok 2, Brgy. Tatala, Binangonan, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 150 | GF | 3329564.1 |  | 3329564.1 | 3300261.92 |  | 3300261.92 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-103 | 4) Concreting of Road with Drainage Canal at Tanchongco Compound, Sitio Villamayor Extension, Brgy. Pag-Asa, Binangonan, Rizal | PEO |  | Public Bidding | 2021-09-30 | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 1870861.9 |  | 1870861.9 | 1854697.69 |  | 1854697.69 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-173 | 5) Concreting of School Ground at Baras-Pinugay Phase 2 National High School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 60 | SEF | 1584492.03 |  | 1584492.03 | 1563319.36 |  | 1563319.36 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-099 | 6) Improvement/Concreting of Orchid St., Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 160 | GF | 7237324.98 |  | 7237324.98 | 7185219.13 |  | 7185219.13 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-112 | 7) Repair/Repainting of Ynares Multi-Purpose Covered Court at Cainta Greenland Exec. Village (Phase 4), Brgy. San Juan, Cainta, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 48 | GF | 894191.26 |  | 894191.26 | 876165.64 |  | 876165.64 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-1-31-392-004-113 | 8) Repair/Repainting of Ynares Multi-Purpose Covered Court at Village East Executive Homes, Brgy. Sto. Domingo, Cainta, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 45 | GF | 877127.27 | 877127.27 |  | 857025.36 | 857025.36 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-168 | 9) Concreting (portion) of Del Pilar Street, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding | 2021-09-30 | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 60 | GF | 1198364.82 |  | 1198364.82 | 1173329.78 |  | 1173329.78 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-181 | 10) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Sitio Biga, Brgy. 3rd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 100 | GF | 5534939.39 | 5534939.39 |  | 5484576.45 | 5484576.45 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-169 | 11) Improvement/Construction of Drainage Canal of Road at Sitio Pulong Ligaya, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 60 | GF | 1099782.48 |  | 1099782.48 | 1081368.56 |  | 1081368.56 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-170 | 12) Improvement/Construction of Drainage Canal at Villaran Street, Brgy. Special District, Jalajala, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 72 | GF | 1996971.9 |  | 1996971.9 | 1973057.85 |  | 1973057.85 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-173 | 13) Construction of Drainage Canal in front of Talaga Elem. School, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 80 | GF | 1749705.92 |  | 1749705.92 | 1729906.72 |  | 1729906.72 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-174 | 14) Asphalt Overlaying of P. Pascual St., Brgy. San Jose, Morong, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 32 | GF | 843598.32 | 843598.32 |  | 822300.39 | 822300.39 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-176 | 15) Asphalt Overlaying of R. Palma St., Sitio Hulo, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 32 | GF | 1782091.25 | 1782091.25 |  | 1759129.37 | 1759129.37 |  | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-108 | 16) Construction of 2-Storey Ynares Multi-Purpose Bldg. at URS, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 136 | GF | 4181850.77 |  | 4181850.77 | 4149653.87 |  | 4149653.87 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-151 | 17) Improvement/Concreting at Upper Belleza St., Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 80 | GF | 2132634.62 |  | 2132634.62 | 2107084.53 |  | 2107084.53 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-144 | 18) Construction of Stone Masonry for Slope Protection (portion) of Matagbak Creek (Corner of Elem. GMA School Bldg.) Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2021-09-30 | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 150 | GF | 7200866.18 |  | 7200866.18 | 7145670.76 |  | 7145670.76 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-150 | 19) Improvement/Concreting (portion) of San Lorenzo Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 4774319.74 |  | 4774319.74 | 4729595.47 |  | 4729595.47 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-111 | 20) Construction of 2-Storey Ynares Multi-Purpose Building at Villa San Mateo 2, Brgy. Guitnang Bayan II, San Mateo, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 176 | GF | 3967743.08 |  | 3967743.08 | 3938626.56 |  | 3938626.56 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-183 | 21) Concreting (portion) of School Ground at San Mateo elem. School, Brgy. Sta. Ana, San Mateo, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 60 | SEF | 1063202.69 |  | 1063202.69 | 1046180.62 |  | 1046180.62 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-184 | 22) Concreting of School Ground at San Mateo Senior High School, Brgy. Guitnang Bayan I, San Mateo, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 60 | SEF | 1299296.42 |  | 1299296.42 | 1278012.09 |  | 1278012.09 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-31-001-002-154 | 23) Concreting of Old Laiban Road, Brgy. Laiban, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 2821568.28 |  | 2821568.28 | 2791330.24 |  | 2791330.24 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-31-001-002-156 | 24) Concreting of Rosal St., Brgy. Sto. Niño, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 2465574.18 |  | 2465574.18 | 2439203.48 |  | 2439203.48 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-31-001-002-158 | 25) Concreting of Verallo St., Brgy. Daraitan, tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 2499584.59 |  | 2499584.59 | 3471318.96 |  | 3471318.96 | Engr. Nelson Pajarillo Simon King | 2021-10-22
2000-000-1-1-31-392-004-117 | 26) Construction of 17x30m Ynares Multi-Purpose Covered Court at Camp Mateo Capinpin, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 168 | GF | 4875818.22 |  | 4875818.22 | 4831185.82 |  | 4831185.82 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-000-1-2-11-399-006-187 | 27) Construction of 1-Storey, 2-Rooms Ynares School Building at Rosario Ocampo Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 115 | SEF | 4052951.41 |  | 4052951.41 | 4025764.91 |  | 4025764.91 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-161 | 28) Improvement/Construction of Box Culvert of Creek (along B. Pag-Asa St.), Brgy. Sta. Ana, Taytay, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 2137763.38 |  | 2137763.38 | 2113693.88 |  | 2113693.88 | Engr. Nelson Pajarillo Simon King | 2021-10-22
3000-300-1-2-11-511-004-115 | 29) Construction of 2-Storey Ynares Multi-Purpose Building (Health Center), Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 157 | GF | 4005664.17 |  | 4005664.17 | 3976576.1 |  | 3976576.1 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-162 | 30) Improvement/Concreting of Road with Drainage Canal at Tamarind Street, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 22-28-Sept-21 | 2021-09-29 |  | 2021-10-11 | 2021-10-15 | 2021-10-26 | 2021-10-29 | 2021-11-02 | 2021-11-11 | 2021-11-19 | 120 | GF | 3293410.76 |  | 3293410.76 | 3267202.22 |  | 3267202.22 | Engr. Nelson Pajarillo Simon King | 2021-10-22
8000-000-1-1-51-001-002-098 | 1) Improvement/Upgrading/Concreting of 4th Street with Drainage Canal, Brgy. San Vicente, Angono, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 200 | GF | 10499495.7 |  | 10499495.7 | 10441591.02 |  | 10441591.02 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-300-1-2-11-511-004-100 | 2) Improvement of 2-Storey Ynares Multi-Purpose Building, Brgy. Buhangin, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 80 | GF | 1760618.25 |  | 1760618.25 | 1726456.55 |  | 1726456.55 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-000-1-1-31-392-004-111 | 3) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Mabuhay Homes 2000, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 80 | GF | 1181925.11 | 1181925.11 |  | 1163912.92 | 1163912.92 |  | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-102-104 | 4) Construction of Stone Masonry for Slope Protection and Concreting of Creek Bed at Creek (Zone 4 to Zone 6), Brgy. Malakaban, Binangonan, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 200 | GF | 7395370.89 |  | 7395370.89 | 7395370.89 |  | 7395370.89 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-164 | 5) Construction of Concrete Canal of Road at Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 140 | GF | 4986110.46 |  | 4986110.46 | 4940049.4 |  | 4940049.4 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-165 | 6) Construction of Perimeter Fence of Road at Brgy. Pinagdilawan, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 80 | GF | 1389032.74 |  | 1389032.74 | 1367145.26 |  | 1367145.26 | Engr. Nelson Pajarillo Simon King | 2021-10-01
7) Construction of Roadway Lightings at Brgy. Tatala, Binangonan, Rizal
8000-000-1-1-51-001-002-112 | a) Construction of Roadway Lightings at T. Ceñidoza, Brgy. Tatala | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 2233396.78 |  | 2233396.78 | 2218464.69 |  | 2218464.69 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-113 | b) Construction of Roadway Lightings at F. Aragones St., Brgy. Tatala | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 3340216.35 |  | 3340216.35 | 3320474.44 |  | 3320474.44 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-114 | c) Construction of Roadway Lighting at C. Bolado St., Brgy. Tatala | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 6533788.51 |  | 6533788.51 | 6493511.36 |  | 6493511.36 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8) Construction of Roadway Lightings at Brgy. Darangan, Binangonan, Rizal
8000-000-1-1-51-001-002-115 | a) Construction of Roadway Lightings at Sitio San Juan, Brgy. Darangan to Macamot Elem. School, Brgy. Darangan | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 7199190.35 |  | 7199190.35 | 7164892.91 |  | 7164892.91 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-116 | b) Construction of Roadway Lightings at Kalawaan St. to Darangan Elem. School, Brgy. Darangan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 806741.27 |  | 806741.27 | 796224.75 |  | 796224.75 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-117 | c) Construction of Roadway Lightings at Bagong Bayan to Kasinay Bridge, Brgy. Darangan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 2232740.53 |  | 2232740.53 | 2220488.98 |  | 2220488.98 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-135 | d) Construction of Roadway Lightings at Narcicorn St., Brgy. Darangan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 1573427.82 |  | 1573427.82 | 1564012.91 |  | 1564012.91 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-136 | e) Construction of Roadway Lightings at Hernandez St., Brgy. Darangan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 1136936.75 |  | 1136936.75 | 1130044.37 |  | 1130044.37 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-137 | f) Construction of Roadway Lightings at Balagtas St., Brgy. Darangan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 367076.03 |  | 367076.03 | 362285.97 |  | 362285.97 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-138 | g) Construction of Roadway Lightings at Top 40 St., Brgy. Darangan | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 913257.05 |  | 913257.05 | 907763.49 |  | 907763.49 | Engr. Nelson Pajarillo Simon King | 2021-10-01
9) Construction of Roadway Lightings at Brgy. Lunsad, Binangonan, Rizal
8000-000-1-1-51-001-002-118 | a) Construction of Roadway Lighting at Aguinaldo St. to Bideco Cpd., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 2125122.2 |  | 2125122.2 | 2110627.57 |  | 2110627.57 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-119 | b) Construction of Roadway Lighting at Bonifacio St. (Lower), Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 494853.24 |  | 494853.24 | 494335.83 |  | 494335.83 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-120 | c) Construction of Roadway Lighting at Bonifacio St. (Upper), Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 400605.61 |  | 400605.61 | 400603.44 |  | 400603.44 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-121 | d) Construction of Roadway Lighting at Lunsad Wharf and Coastal Road Extension, Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 795226.92 |  | 795226.92 | 786025.07 |  | 786025.07 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-122 | e) Construction of Roadway Lighting at Venaville Cpd., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 1070286.37 |  | 1070286.37 | 1067903.54 |  | 1067903.54 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-123 | f) Construction of Roadway Lighting Monico St., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 400605.61 |  | 400605.61 | 400603.44 |  | 400603.44 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-124 | g) Construction of Roadway Lighting at M.L. Quezon St., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 974925.32 |  | 974925.32 | 974839.18 |  | 974839.18 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-125 | h) Construction of Roadway Lighting at M.H. Del Pilar St., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 589496.3 |  | 589496.3 | 587567.85 |  | 587567.85 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-126 | i) Construction of Roadway Lighting at J.M. Pacis St., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 692014.91 |  | 692014.91 | 685429.86 |  | 685429.86 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-127 | j) Construction of Roadway Lighting at J. Sumulong St., Brgy. Lunsad | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 120 | GF | 2890145.51 |  | 2890145.51 | 2871435.78 |  | 2871435.78 | Engr. Nelson Pajarillo Simon King | 2021-10-01
10) 6) Construction of Roadway Lightings at Brgy. Batingan, Binangonan, Rizal
8000-000-1-1-51-001-002-128 | a) Construction of Roadway Lightings at Flordeliza St., Brgy. Batingan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 1136936.75 |  | 1136936.75 | 1130496.97 |  | 1130496.97 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-129 | b) Construction of Roadway Lightings at Mechilina St., Brgy. Batingan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 1687538.6 |  | 1687538.6 | 1679009.47 |  | 1679009.47 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-130 | c) Construction of Roadway Lightings at Mejorada/Antazo St., Brgy. Batingan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 1687538.6 |  | 1687538.6 | 1679009.47 |  | 1679009.47 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-131 | d) Construction of Roadway Lightings at Sta. Ursula St., Brgy. Batingan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 2233396.78 |  | 2233396.78 | 2217024.4 |  | 2217024.4 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-132 | e) Construction of Roadway Lightings at Aragoza St., Brgy. Batingan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 1687538.6 |  | 1687538.6 | 1679009.47 |  | 1679009.47 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-133 | f) Construction of Roadway Lightings at Bilog St., Brgy. Batingan | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 2233396.78 |  | 2233396.78 | 2317024.4 |  | 2317024.4 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-134 | g) Construction of Roadway Lightings at Ceñidoza St., Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 1136936.75 |  | 1136936.75 | 1130496.97 |  | 1130496.97 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-140 | h) Construction of Roadway Lightings at Ulang St., Brgy. Batingan, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 150 | GF | 1136936.75 |  | 1136936.75 | 1209281.2 |  | 1209281.2 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-139 | 11) Construction of Roadway Lightings at Ulang St., Brgy. Tatala, Binangonana, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 112 | GF | 8281790.75 |  | 8281790.75 | 8229653.07 |  | 8229653.07 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-102 | 12) Construction of Stone Masonry for Slope Protection (portion) of Gupiing Creek at Sitio Gupiing, Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 140 | GF | 3999999.34 |  | 3999999.34 | 3970180.77 |  | 3970180.77 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-142 | 13) Construction of Roadway Lightings at Sitio Hulo Road, Brgy. Pila Pila, Binangonan, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 80 | GF | 5026185.15 |  | 5026185.15 | 4997398.99 |  | 4997398.99 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-000-1-1-31-392-004-114 | 14) Construction of 15x24m Ynares Multi-Purpose Covered Court, Brgy. Navotas, Cardona, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 140 | GF | 5488413.05 |  | 5488413.05 | 5453690.54 |  | 5453690.54 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-143 | 15) Construction of Roadway Lightings at Brgy. Subay, Cardona, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 60 | GF | 2293968.65 |  | 2293968.65 | 2268325.15 |  | 2268325.15 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-166 | 16) Construction of Drainage Canal at Various Roads, Brgy. Dalig, Cardona, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 200 | GF | 16153167.2 |  | 16153167.2 | 16064302.48 |  | 16064302.48 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-300-1-2-11-511-004-107 | 17) Repair of Puericulture/Health Center Bldg., Brgy. Bombongan, Morong, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 60 | GF | 454030.29 | 454030.29 |  | 440106.62 | 440106.62 |  |  | 2021-10-01
3000-000-1-2-11-399-006-176 | 18) Construction of 15x24m (Rafter Type) Ynares Multi-Purpose Covered Court at Pulong Kumanoy Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 111 | GF | 4805013.81 |  | 4805013.81 | 4774108.43 |  | 4774108.43 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-177 | 19) Construction of Stone Masonry for Side Protection (portion) of Pililla River along G. Dikit Street, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 160 | GF | 6642515.44 |  | 6642515.44 | 6611404.01 |  | 6611404.01 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-149 | 20) Construction of Stone Masonry for Slope Protection of Pililla River (along M.L. Quezon St.), Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 140 | GF | 4199076.65 |  | 4199076.65 | 4170365.95 |  | 4170365.95 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-180 | 21) Construction of Stone Masonry for Slope Protection (portion) of Balite Creek, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 140 | GF | 7299976.93 |  | 7299976.93 | 7261757.86 |  | 7261757.86 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-000-1-1-31-392-004-116 | 22) Improvement of Ynares Multi-Purpose Covered Court and Stage at Southville 8B Phase 4, Brgy. San Isidro, Rodriguez, Rizal | PEO |  | Public Bidding | 2021-09-30 | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 50 | GF | 1563820.7 |  | 1563820.7 | 1545620.03 |  | 1545620.03 | Engr. Nelson Pajarillo Simon King | 2021-10-01
23) Improvement of Generator Rooms and Construction of Generator Flatform at Brgy. Burgos, Rodriguez, Rizal
3000-400-1-2-21-009-002 | a) Improvement of Generator Rooms and Construction of Generator Flatform at Rizal Provincial Hospital System (RPHS) Casimiro A. Ynares, Sr. Memorial Hospital, Brgy. Burgos | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 90 | GF | 1219731.7 |  | 1219731.7 | 1209281.2 |  | 1209281.2 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-400-1-2-21-009-003 | b) Construction of 2-units Generator Flatform at Rizal Provincial Hospital System (RPHS) Casimiro A. Ynares, Sr. Memorial Hospital, Brgy. Burgos | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 90 | GF | 527618.24 |  | 527618.24 | 514769.73 |  | 514769.73 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-000-1-2-11-399-006-182 | 24) Repair/Repainting of Ynares School Buildings at Maly Elem. School, Brgy. Maly, San Mateo, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 142 | SEF | 6576249.87 | 6576249.87 |  | 6545111.86 |  | 6545111.86 | Engr. Nelson Pajarillo Simon King | 2021-10-01
25) Construction of Comfort Room and Improvement of Ynares Multi-Purpose Building at Brgy. Sta. Ines and Brgy. Laiban, Tanay, Rizal
3000-300-1-2-11-511-004-114 | a) Construction of 3-Seater Comforr Room, Brgy. Sta. Ines | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 125 | GF | 911318.2 |  | 911318.2 | 892961.48 |  | 892961.48 | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-300-1-2-11-511-004-113 | b) Improvement of 1-Storey Ynares multi-Purpose Building (Day Care Center), Brgy. Laiban | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 125 | GF | 736960.37 |  | 736960.37 | 730166.96 |  | 730166.96 | Engr. Nelson Pajarillo Simon King | 2021-10-01
| 26) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court at Brgy. Sampaloc, Tanay, Rizal | [23 empty] | 2021-10-01
3000-000-1-1-31-392-004-118 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Jungle Mountaineers Neighborhood Association, Inc., Brgy. Sampaloc | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 90 | GF | 1212357.66 | 1212357.66 |  | 1195483.38 | 1195483.38 |  | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-000-1-1-31-392-004-119 | b) Improvement of Ynares Multi-Purpose Covered Court at Jungle Mountaineers Neighborhood Association, Inc., Brgy. Sampaloc | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 90 | GF | 281134.71 |  | 281134.71 | 276540.96 |  | 276540.96 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-160 | 27) Improvement/Construction of Hanging Bridge at Brgy. Sto. Niño, Tanay, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 200 | GF | 7309530.4 |  | 7309530.4 | 7274220.94 |  | 7274220.94 | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-001-009 | 28) Repair/Replacement of G.I. Roofing of Rizal Police Provincial Office (RPPO Main Bldg.) at Cabrera Road, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 45 | GF | 1099784.3 | 1099784.3 |  | 1081563.76 | 1081563.76 |  | Engr. Nelson Pajarillo Simon King | 2021-10-01
3000-000-1-1-31-392-004-12 | 29) Repair/Repainting of Ynares Multi-Purpose Covered Court at Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 60 | GF | 678885.92 | 678885.92 |  | 661518.86 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-01
8000-000-1-1-51-001-002-163 | 30) Concreting of Road with Drainage Canal at Sitio Guava Hills, Brgy. Bagumbayan, Teresa, Rizal | PEO |  | Public Bidding |  | 1-7 Oct. 21 | 2021-10-08 |  | 2021-10-22 | 2021-10-27 | 2021-11-08 | 2021-11-11 | 2021-11-15 | 2021-11-24 | 2021-11-29 | 140 | GF | 4828563.73 |  | 4828563.73 | 4803720.1 |  | 4803720.1 | Engr. Nelson Pajarillo Simon King | 2021-10-01
2021-10-01
8000-000-1-1-51-001-002-096 | 1) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Venus Compound, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding | 2021-10-04 | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 100 | GF | 6028401.21 | 6028401.21 |  | 5996390.17 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-097 | 2) Asphalt Overlaying (portion) of E. Dela Paz St., Brgy. Bagumbayan, Angono, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 1765734.96 | 1765734.96 |  | 1742378.2 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-141 | 3) Asphalt Overlay of Cableway, Brgy. Calumpang, Binangonan, Rizal | PEO |  | Public Bidding | 2021-10-04 | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 100 | GF | 11914354.82 | 11914354.82 |  | 11852361.76 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-105 | 4) Asphalt Overlaying/Concrete Reblocking (portion) of Ynares St., Brgy. Mahabang Parang, Binangonan, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 100 | GF | 3099954.58 | 3099954.58 |  | 3071181.47 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-106 | 5) Asphalt Overlaying/Concrete Reblocking (portion) of Sison St., Brgy. Mahabang Parang, Binangonan, Rizal 6) Asphalt Overlaying of Lirio St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 3809166.97 | 3809166.97 |  | 3782427.2 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-107 | 6) Asphalt Overlaying of Lirio St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 1944850.66 | 1944850.66 |  | 1027686.93 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-108 | 7) Asphalt Overlaying/Concrete Reblocking (portion) of Apostadero St., Brgy. Macamot, Binangonan, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 2221746.05 | 2221746.05 |  | 2197632.88 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-109 | 8) Asphalt Overlaying of L. Flores St., Brgy. Lunsad, Binangonan, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 1148738.77 | 1148738.77 |  | 1129899.26 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-110 | 9) Improvement/Construction of Drainage Canal at Sampaguita St., Brgy. Mambog, Binangonan, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 120 | GF | 2046525.11 |  | 2046525.11 | 2023634.7 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-170 | 10) Construction of Covered Pathwalk/Covered Area at Painaan Elem. School, Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 48 | SEF | 751133.55 |  | 751133.55 | 733091.65 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
| 11) Improvement of Ynares School Building/Ynares Multi-Purpose Covered Court at Brgy. Santiago, Baras, Rizal |  |  |  |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29
3000-000-1-2-11-399-006-172 | a) Improvement of Ynares School Building at Santiago Elem. School | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 44 | SEF | 360169.91 |  | 360169.91 | 350514.19 | 350514.19 |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-171 | b) Improvement of Ynares Multi-Purpose Covered Court at Santiago Elem. School | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 44 | SEF | 167441.87 |  | 167441.87 | 160998.02 | 160998.02 |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-174 | 12) Repair/Repainting of Ynares School Buildings at Mariano C. San Juan Elem. School, Cardona, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 120 | GF | 4011683.57 | 4011683.57 |  | 3983507.85 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-167 | 13) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Sitio Masikap, Brgy. 3rd District, Jalajala, Rizal 14) Asphalting (portion) of Manggahan St., Brgy. 2nd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 3798128.63 | 3798128.63 |  | 3772206.14 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-171 | 14) Asphalting (portion) of Manggahan St., Brgy. 2nd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 1856305 | 1856305 |  | 1832881.03 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-172 | 15) Asphalt Overlaying/Concrete Reblocking (portion) of Bayanihan St., Brgy. 3rd District, Jalajala, Rizal 16) Construction of Perimeter Fence (portion) at Pulong Kumanoy Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 3799543.28 | 3799543.28 |  | 3769571.07 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-394-006-178 | 16) Construction of Perimeter Fence (portion) at Pulong Kumanoy Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 64 | GF | 2019342.5 |  | 2019342.5 | 1998154.89 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-177 | 17) Construction of Fence at Morong Senior High School, Brgy. San Juan, Morong, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 2318374.88 |  | 2318374.88 | 2298127.82 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-175 | 18) Asphalt Overlaying of Tupas St. and P. Francisco St. (portion) at Sitio Hulo, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 1295198.48 | 1295198.48 |  | 1276688.63 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-178 | 19) Asphalt Overlaying/Concrete Reblocking (portion) of Matagbak Feeder Road (Larry Beth Farm to Matagbak Elementary School), Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 4031249 | 4031249 |  | 4001216.92 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-146 | 20) Asphalt Overlaying/Concrete Reblocking (portion) of Sitio Tipi Road, Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 2917247.2 | 2917247.2 |  | 2892109.25 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-145 | 21) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Sitio Bulacan II, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 4626703.58 | 4626703.58 |  | 4595934.3 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-148 | 22) Asphalt Overlaying/Concrete Reblocking of Libid Ext. Road and A. Mabini St., Brgy. Hulo, Pililla, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 2448671.8 | 2448671.8 |  | 2427562.46 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-179 | 23) Asphalt Overlaying/Concrete Reblocking (portion) of Road at Sitio Bulacan I, Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | GF | 2678464.17 | 2678464.17 |  | 2655277.74 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-147 | 24) Asphalt Overlaying/Concrete Reblocking (portion) of Matagbak Feeder Road (Sitio Matilos Bagumbayan to Sitio Matagbak), Brgy. Bagumbayan, Pililla, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 100 | GF | 3798612.07 | 3798612.07 |  | 3764544.52 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
25) Repair/Relocation of Ynares Waiting Shed and Improvement of Ynares Multi-Purpose Building at Brgy. Puray and Brgy. Manggahan, Rodriguez and San Mateo, Rizal
3000-300-1-2-11-511-004-116 | a) Repair of Various Ynares Waiting Shed, Rodriguez/San Mateo, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 140 | GF | 996728.38 | 996728.38 | 981320.22 | 981320.22 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-300-1-2-11-511-004-110 | b) Relocation of 1-Unit Ynares Waiting Shed (Arc Type) at Puray National High School, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 140 | GF | 253852.98 | 253852.98 | 249446.11 | 249446.11 |  |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-300-1-2-11-511-004-109 | c) Improvement of 2-Storey Ynares Multi-Purpose Building at Congressville, Brgy. Manggahan, Rodriguez, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 140 | GF | 307759.92 | 307759.92 | 304445.67 |  | 304445.67 |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-179 | 26) Construction of 15x18m Ynares Multi-Purpose Covered Court at Puray National High School, Brgy. Puray, Rodriguez, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 80 | SEF | 3008753.56 |  | 3008753.56 | 2981541.86 |  | 2981541.86 | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-181 | 27) Improvement of Multi-Purpose Covered Court and Stage at San Jose Elem. School, Brgy. San Jose, Rodriguez, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 69 | SEF | 1665065.01 |  | 1665065.01 | 1640072.93 |  | 1640072.93 | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-2-11-399-006-180 | 28) Repair/Repainting of Multi-Purpose Covered Court and Stage at San Jose Elem. School, Brgy. San Jose, Rodriguez, Rizal 29) Improvement of Comfort Room & Stage at Ynares Multi-Purpose Covered Court at Bancom Subd., Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 69 | SEF | 899455.23 | 899455.23 |  | 880138 | 880138 |  | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-300-1-2-11-511-004-112 | 29) Improvement of Comfort Room & Stage at Ynares Multi-Purpose Covered Court at Bancom Subd., Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 257 | GF | 2565075.6 |  | 2565075.6 | 2539999.98 |  | 2539999.98 | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-152 | 30) Construction of Stone Masonry for Slope Protection of Creek inside the Jose F. Diaz Memorial National High School, Brgy. Gulod Malaya, San Mateo, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 60 | GF | 832959.23 |  | 832959.23 | 814494.61 |  | 814494.61 | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-1-31-392-004-120 | 31) Construction of 12x24m Ynares Multi-Purpose Covered Court at Signal Village, Brgy. Sampaloc, Tanay, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 104 | GF | 3543969.04 |  | 3543969.04 | 3510716.35 |  | 3510716.35 | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-159 | 32) Concreting of P. Pranada St., Brgy. Daraitan, Tanay, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 180 | GF | 4012682.94 |  | 4012682.94 | 3982620.33 |  | 3982620.33 | Engr. Nelson Pajarillo Simon King | 2021-10-07
3000-000-1-1-31-392-004-188 | 33) Construction of 8x24m Ynares Multi-Purpose Covered Court at Pantay National High School, Brgy. Dalig, Teresa, Rizal | PEO |  | Public Bidding |  | 7-13 Oct. 21 | 2021-10-15 |  | 2021-10-29 | 2021-11-04 | 2021-11-15 | 2021-11-18 | 2021-11-19 | 2021-11-25 | 2021-11-29 | 90 | SEF | 2826249.61 |  | 2826249.61 | 3799425.36 |  | 3799425.36 | Engr. Nelson Pajarillo Simon King | 2021-10-07
8000-000-1-1-51-001-002-182 | 1) Asphalt Overlay/Concrete Reblocking (portion) of Don Justo Guido St., Brgy. Bagumbayan, Angono, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 100 | GF | 4223440.64 | 4223440.64 |  | 4191882.71 | 4191882.71 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-183 | 2) Asphalt Overlaying/Concrete Reblocking (portion) of Road with Drainage Canal at Edenville, Brgy. San Isidro and Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 150 | GF | 16999896.76 | 16999896.76 |  | 16914170.71 | 16914170.71 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-400-1-2-21-009-004 | 3) Repair of Rizal Provincial Hospital System-Angono Annex, Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 90 | GF | 3448877.39 | 3448877.39 |  | 3423538.33 | 3423538.33 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-095 | 4) Improvement/Concreting of Roads with Drainage Canal at Nieves Hills Subd., Brgy. San Isidro, Angono, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 90 | GF | 5698749.66 |  | 5698749.66 | 5668439.53 |  | 5668439.53 | Engr. Nelson Pajarillo Simon King | 2021-10-19
5) Improvement of Ynares Multi-Purpose Building at Brgy. Mahabang Parang and Brgy. Darangan, Binangonan, Rizal
3000-300-1-2-11-511-004-103 | a) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall), Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 70 | GF | 557130 |  | 557130 | 549459.01 |  | 549459.01 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-300-1-2-11-511-004-101 | b) Improvement of 2-Storey Ynares Multi-Purpose Building (Brgy. Hall), Brgy. Darangan 6) Repair/Repainting of Ynares School Buildings at Bangad Elem. School, Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 70 | GF | 300453.33 |  | 300453.33 | 288657.74 |  | 288657.74 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-189 | 6) Repair/Repainting of Ynares School Buildings at Bangad Elem. School, Brgy. Bangad, Binangonan, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 70 | GF | 857583.33 | [5 empty] | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-184 | 7) Construction of Roadway Lightings at Brgy. Pipindan, Binangonan, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 92 | SEF | 1902962.7 | 1902962.7 |  | 1878371.51 | 1878371.51 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
| 8) Construction of Roadway Lightings and Installation of Area Lightings at Brgy. Palangoy, Brgy. Pag-Asa, and Brgy. Lunsad, Binangonan, Rizal |  |  |  | 2021-10-14
8000-000-1-1-51-001-002 | a) Construction of Roadway Lightings at Madrigal Village, Brgy. Palangoy, Binangonan, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 96 | GF | 4837382.74 |  | 4837382.74 | 4803568.37 |  | 4803568.37 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-194 | b) Construction of Roadway Lightings at Diaz 2 Compound St., Brgy. Pag-Asa | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 96 | GF | 709088.35 |  | 709088.35 | 707441.14 |  | 707441.14 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002 | c) Installation of Area Lightings at School Compound of Lunsad Elem. School, Brgy. Lunsad | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 96 | GF | 490320.74 |  | 490320.74 | 490131.19 |  | 490131.19 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002 | 9) Construction of Roadway Lightings at Brgy. Mambog, Binangonan, Rizal
8000-000-1-1-51-001-002-186 | a) Construction of Roadway Lightings at Sampaguita St. Extension, Brgy. Mambog | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 96 | GF | 1636385.44 |  | 1636385.44 | 1634594.03 |  | 1634594.03 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-187 | b) Construction of Roadway Lightings at Catleya 1 St., Brgy. Mambog | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 96 | GF | 2376963.55 |  | 2376963.55 | 2264338.65 |  | 2264338.65 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-188 | c) Construction of Roadway Lightings at Catleya 2 St., Brgy. Mambog | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 96 | GF | 2299318.71 |  | 2299318.71 | 2277411.64 |  | 2277411.64 | Engr. Nelson Pajarillo Simon King | 2021-10-19
| 10) Construction of Roadway Lightings at Brgy. Mahabang Parang, Binangonan, Rizal |  |  |  | 2021-10-14 | [12 empty] | 6,212,667.70/96 cd
8000-000-1-1-51-001-002-189 | a) Construction of Roadway Lightings at Sison St., brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 2900719 |  | 2900719 | 2885844.99 |  | 2885844.99 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-190 | b) Construction of Roadway Lightings at Viernes St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 806799.82 |  | 806799.82 | 801506.82 |  | 801506.82 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-191 | c) Construction of Roadway Lightings at Oja St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 6533788.51 |  | 6533788.51 | 6499400.22 |  | 6499400.22 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-192 | d) Construction of Roadway Lightings at Mesa St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 2900719.03 |  | 2900719.03 | 2885844.99 |  | 2885844.99 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-193 | e) Construction of Roadway Lightings at Oja Mambalon St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 6198565.39 |  | 6198565.39 | 6169686.28 |  | 6169686.28 | Engr. Nelson Pajarillo Simon King | 2021-10-19
| 11) Construction of Roadway Lightings at Brgy. Mahabang Parang, Binangonan, Rizal |  |  |  | 2021-10-14 | [12 empty] | 19,340,591.75/180 cd
8000-000-1-1-51-001-002-195 | a) Construction of Roadway Lightings at Villones St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 140 | GF | 2233455.34 |  | 2233455.34 | 2219774.44 |  | 2219774.44 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-196 | b) Construction of Roadway Lightings at Pitallo St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 140 | GF | 2459458.51 |  | 2459458.51 | 2446997.72 |  | 2446997.72 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-197 | c) Construction of Roadway Lightings at Dugay St., Brgy. Mahabang Parang | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 140 | GF | 5877028.75 |  | 5877028.75 | 5843974.8 |  | 5843974.8 | Engr. Nelson Pajarillo Simon King | 2021-10-19
10,569,942.60/140 cd
3000-000-1-2-11-399-006-151 | 12) Improvement of Ynares Multi-Purpose Covered Court at Baras-Pinugay (Phase 2) National High School at Brgy. Pinugay, Baras, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 86 | SEF | 1801529.59 |  | 1801529.59 | 1775411.86 |  | 1775411.86 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-100 | 13) Concreting (portion) of Dulong Bayan St., Brgy. Santiago, Baras, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | GF | 343648.39 |  | 343648.39 | 329413.26 |  | 329413.26 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-300-1-2-11-511-004-104 | 14) Improvement of 2-Storey Ynares Multi-Purpose Building at Area 8, Greenwoods Executive Village, Brgy. San Andres, Cainta, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 30 | GF | 179463.41 |  | 179463.41 | 167375.02 |  | 167375.02 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-300-1-2-11-399-006-152 | 15) Repair/Repainting of Ynares School Buildings at Navotas Elem. School, Brgy. Navotas, Cardona, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 82 | GF | 2718350.09 | 2718350.09 |  | 2692110.23 | 2692110.23 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-300-1-2-11-511-004-105 | 16) Improvement of Multi-Purpose Day Care Center at Brgy. PalayPalay, Jalajala, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 45 | GF | 515562.64 |  | 515562.64 | 499562.64 |  | 499562.64 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-400-1-2-21-009-005 | 17) Improvement of Ynares Municipal Hospital at Brgy. First District, Jalajala, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 235 | GF | 6278262.16 |  | 6278262.16 | 6240269.29 |  | 6240269.29 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-300-1-2-11-511-004-106 | 18) Construction of Materials Recovery Facilities (MRF), Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 40 | GF | 567417.98 |  | 567417.98 | 553322.2 |  | 553322.2 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-198 | 19) Asphalt Overlaying of R. Palma St., Sitio Ibaba, Brgy. San Pedro, Morong, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | GF | 3523754.26 | 3523754.26 |  | 3498690.28 | 3498690.28 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-199 | 20) Asphalt Overlaying/Concreting of Road with Drainage Canal at Quezon St., Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 8458051.2 | 8458051.2 |  | 8403291.25 | 8403291.25 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-200 | 21) Asphalt Overlaying/Concreting Reblocking (portion) of Road with Drainage Canal at Alejandro St., Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 180 | GF | 6318000.58 | 6318000.58 |  | 6280966.17 | 6280966.17 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-201 | 22) Asphalt Overlaying/Concreting Reblocking (portion) of Road with Drainage Canal at Bellin St., Brgy. Malaya, Pililla, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 160 | GF | 5488984.25 | 5488984.25 |  | 5455750.08 | 5455750.08 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-153 | 23) Improvement/Concreting of Road (Near MMDA Closed Sanitary Landfill), Brgy. Pintong Bukawe, San Mateo, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 160 | GF | 6799935.48 |  | 6799935.48 | 6759286.87 |  | 6759286.87 | Engr. Nelson Pajarillo Simon King | 2021-10-19
| 24) Repair/Repainting/Improvement of Ynares Multi-Purpose Covered Court & Construction of Covered Pathwalk at Brgy. Gulod Malaya and Brgy. Maly, San Mateo, Rizal |  |  |  | 2021-10-14
3000-000-1-2-11-399-006-193 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court at Jose F. Diaz National High School, Brgy. Gulod Malaya | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | SEF | 265012.03 | 265012.03 |  | 261281.27 | 261281.27 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-194 | b) Improvement of Ynares Multi-Purpose Covered Court at Jose F. Diaz National High School, Brgy. Gulod Malaya | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | SEF | 475917.8 |  | 475917.8 | 469421.02 |  | 469421.02 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-195 | c) Construction of Covered Pathwalk at Jose F. Diaz National High School, Brgy. Gulod Malaya | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | SEF | 325557 |  | 325557 | 321084.38 |  | 321084.38 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-196 | d) Repair/Repainting of Ynares Multi-Purpose Covered Court at Maly Elem. School, Brgy. Maly | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | SEF | 473036.34 | 473036.34 |  | 466739.09 | 466739.09 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
[18 empty] | 1,539,523.17/60 cd | [6 empty] | 2021-10-19
8000-000-1-1-51-001-002-202 | 25) Asphalt Overlaying/Concrete Reblocking (portion) of Various Roads, Brgy. Sta. Ana, San Mateo, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 140 | GF | 10377544.94 | 10377544.94 |  | 10316172.45 | 10316172.45 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-197 | 26) Construction of Steel Water Tank, Water Pressure Tank w/ Booster Pump, and Pump House at Dolores Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 40 | GF | 483437.55 |  | 483437.55 | 468381.24 |  | 468381.24 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-198 | 27) Repair/Repainting of Ynares School Building at Hapay na Mangga Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | SEF | 1947635.02 | 1947635.02 |  | 1920318.81 | 1920318.81 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-199 | 28) Repair/Repainting of Ynares School Buildings at Simona Elem. School, Brgy. San Isidro, Taytay, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 115 | SEF | 3569799.36 | 3569799.36 |  | 3541635.37 | 3541635.37 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-157 | 29) Construction of Stone Masonry for Slope Protection at Mamuyao River, Brgy. Sto. Niño, Tanay, Rizal | PEO |  | Public Bidding | 2021-10-14 | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 160 | GF | 5098031.66 |  | 5098031.66 | 5064295.07 |  | 5064295.07 | Engr. Nelson Pajarillo Simon King | 2021-10-19
8000-000-1-1-51-001-002-155 | 30) Construction of Stone Masonry for Slope Protection at Corner of Narra St., Brgy. Sto. Niño, Tanay, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 90 | GF | 2254015.89 |  | 2254015.89 | 2228474.32 |  | 2228474.32 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-200 | 31) Repair/Repainting of 1-Storey, 5-Rooms Ynares School Bldg. at Don Domingo Capistrano Elem. School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 64 | SEF | 1675369.33 | 1675369.33 |  | 1653226.83 | 1653226.83 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-201 | 32) Repair/Repainting of Ynares Multi-Purpose Covered Court at Don Domingo Capistrano elem. School, Brgy. Plaza Aldea, Tanay, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 28 | SEF | 575025.9 | 575025.9 |  | 558189.47 | 558189.47 |  | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-202 | 33) Repair/Repainting of Ynares School Buildings at Prinza Elem. School, Brgy. Prinza, Teresa, Rizal | PEO |  | Public Bidding |  | 18-24 Oct. 21 | 2021-10-25 |  | 2021-11-05 | 2021-11-11 | 2021-11-22 | 2021-11-26 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 60 | SEF | 1152417.24 | 1152417.24 |  | 1134734.38 |  | 1134734.38 | Engr. Nelson Pajarillo Simon King | 2021-10-19
3000-000-1-2-11-399-006-169 | 1) Construction of 4-Storey, 8-Rooms Ynares School Building at Joaquin Guido Elem. School, Brgy. Kalayaan, Angono, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 250 |  | 27725333.96 |  | 27725333.96 | 27605165.84 |  | 27605165.84 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-203 | 2) Repair/Repainting of 3-Storey, 15-Rooms NHA School Bldg. at Baras-Pinugay Integrated High School, Brgy. Pinugay, Baras, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 60 |  | 1786934.8 | 1786934.8 |  | 1761651.76 | 1761651.76 |  | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-204 | 3) Repair/Repainting of Ynares Multi-Purpose Covered Court and Stage at Calumpang Elem. School, Brgy. Calumpang, Binangonan, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 60 |  | 868465.33 | 868465.33 |  | 850710.12 | 850710.12 |  | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-001-001-020 | 4) Construction of Stone Masonry for Side Protection (portion) and Concreting of Creek Bed at Purok II, Brgy. Sapang, Binangonan, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 120 |  | 1796196.74 |  | 1796196.74 | 1768743.3 |  | 1768743.3 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-002-006-001 | 5) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Janosa Elem. School, Brgy. Janosa, Binangonan, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 72 |  | 1199912.1 |  | 1199912.1 | 1183736.39 |  | 1183736.39 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-205 | 6) Repair/Repainting of Ynares School Bldgs. at Saint Anthony Elem. School, Brgy. San Juan, Cainta, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 80 |  | 1499085.47 | 1499085.47 |  | 1479183.29 | 1479183.29 |  | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-002-006-002 | 7) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at M.C. San Juan Elem. School, Brgy. San Roque, Cardona, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 72 |  | 1028117.03 |  | 1028117.03 | 1008530.94 |  | 1008530.94 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-002-006-003 | 8) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Subay Elem. School, Brgy. Subay, Cardona, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 72 |  | 1189815.82 |  | 1189815.82 | 1171918.52 |  | 1171918.52 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-002-006-004 | 9) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Tadlak Elem. School, Brgy. Looc, Cardona, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 76 |  | 1349611.71 |  | 1349611.71 | 1328608.76 |  | 1328608.76 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-300-1-2-11-511-004-086 | 10) Repair/Repainting of 2-Storey Multi-Purpose Building (Brgy. Hall) at Brgy. Calahan, Cardona, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 22 |  | 299893.85 | 299893.85 |  | 285521.2 | 285521.2 |  | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-206 | 11) Repair/Repainting of Ynares School Bldgs. at Sipsipin Elem. School, Brgy. Sipsipin, Jalajala, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 90 |  | 3798328.13 | 3798328.13 |  | 3772211.01 | 3772211.01 |  | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-001-001-018 | 12) Construction of Stone Masonry for Slope Protection of Creek at J. Luna St., Brgy. Lubo, Jalajala, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 140 |  | 5685725.3 |  | 5685725.3 | 5650938.81 |  | 5650938.81 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-001-001-019 | 13) Construction of Stone Masonry for Slope Protection (portion) of Creek at M. Bellin Jr. Street (Upper Mapacla), Brgy. Special District, Jalajala, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 180 |  | 9488323.77 |  | 9488323.77 | 9428585.28 |  | 9428585.28 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-001-001-021 | 14) Construction of Stone Masonry for Slope Protection (portion) of Creek at Purok I, Brgy. Bayugo, Jalajala, Rizal | PEO |  |  |  | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 100 |  | 1678299 |  | 1678299 | 1655136.02 |  | 1655136.02 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-002-006-005 | 15) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Jalajala Elem. School, Brgy. Special District, Jalajala, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 | 2021-11-03 |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 75 |  | 1053427.85 |  | 1053427.85 | 1034333.65 |  | 1034333.65 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-208 | 16) Construction of 3-Storey, 4-Rooms Ynares School Building at Maybancal Elem. School, Brgy. Maybancal, Morong, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 230 |  | 22893239.63 |  | 22893239.63 | 22796106.34 |  | 22796106.34 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-175 | 17) Construction of 4-Storey, 12-Rooms Ynares School Building at Morong National High School, Brgy. San Juan, Morong, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 350 |  | 46755144.76 |  | 46755144.76 | 46570090.46 |  | 46570090.46 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-211 | 18) Repair/Repainting of Ynares School Bldgs. at Niogan Elem. School, Brgy. Niogan, Pililla, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 90 |  | 3651074.06 | 3651074.06 |  | 3623191.07 | 3623191.07 |  | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-212 | 19) Construction of Covered Pathwalk at Malaya Elem. School, Brgy. Malaya, Pililla, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 90 |  | 1699242.33 |  | 1699242.33 | 1676184.08 |  | 1676184.08 | Engr. Nelson Pajarillo Simon King | 2021-10-26
3000-000-1-2-11-399-006-213 | 20) Improvement of Ynares Multi-Purpose Covered Court at Malaya Elem. School, Brgy. Malaya, Pililla, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 95 |  | 3127631.86 |  | 3127631.86 | 3098410.97 |  | 3098410.97 | Engr. Nelson Pajarillo Simon King | 2021-10-26
9000-900-1-2-40-940-002-006-008 | 21) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Macaingalan National High School, Brgy. Puray, Rodriguez, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 72 |  | 1289439.88 |  | 1289439.88 | 1261219.85 |  | 1261219.85 | Engr. Nelson Pajarillo Simon King | 2021-10-26
| 22) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) and Improvement of Ynares Multi-Purpose Covered Court at Brgy. San Rafael and Brgy. San Jose, Rodriguez, Rizal | [16 empty] | 1988825.05 |  | 1988825.05 | 1959721.85 |  | 1959721.85
9000-900-1-2-40-940-002-006-006 | a) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Catmon Elem. School, Brgy. San Rafael | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 80 |  | 1089134.53 |  | 1089134.53 | 1073164.69 |  | 1073164.69 | Engr. Nelson Pajarillo Simon King
| b) Improvement of Ynares Multi-Purpose Covered Court at Villa Ana Maria Subd., Brgy. San Jose | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 80 |  | 899690.52 |  | 899690.52 | 886557.16 |  | 886557.16 | Engr. Nelson Pajarillo Simon King
9000-900-1-2-40-940-001-001-017 | 23) Construction of Stone Masonry for Slope Protection at Laan Creek (portion) Banaiville, Rodriguez, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 120 |  | 4599965.36 |  | 4599965.36 | 4563307.92 |  | 4563307.92 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-214 | 24) Repair/Repainting of Ynares School Bldg. at Pintong Bukawe National High School, Brgy. Pintong Bukawe, San Mateo, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 36 |  | 293898.34 | 293898.34 |  | 281803.75 | 281803.75 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-215 | 25) Construction of School Canteen at Corazon C. Aquino Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 45 |  | 1539509.61 |  | 1539509.61 | 1518442.14 |  | 1518442.14 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-216 | 26) Construction of 2-Storey, 6-Rooms Ynares School Building at Tapayan Elem. School, Brgy. Sta. Ana, Taytay, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 306 |  | 1699999.58 |  | 1699999.58 | 16912859.19 |  | 16912859.19 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-185 | 27) Construction of 4-Storey, 16-Rooms Ynares School Building at Taytay Elem. School, Brgy. Dolores, Taytay, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 411 |  | 64840878.8 |  | 64840878.8 | 64642712.58 |  | 64642712.58 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-186 | 28) Construction of 4-Storey, 8-Rooms Ynares School Building at Bagong Pag-Asa Elem. School, Brgy. San Juan, Taytay, Rizal | PEO |  |  | 2021-10-22 | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 250 |  | 28375819.56 |  | 28375819.56 | 28250722.19 |  | 28250722.19 | Engr. Nelson Pajarillo Simon King
9000-900-1-2-40-940-002-006-007 | 29) Construction/Provision of Wash Facilities (Water, Sanitation & Hygiene) at Daraetan Elem. School, Brgy. Daraitan, Tanay, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 60 |  | 1237878.09 |  | 1237878.09 | 1218642.34 |  | 1218642.34 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-080 | 30) Construction of 2-Storey, 4-Rooms Ynares School Building at Daraetan National High School, Brgy. Daraitan, Tanay, Rizal | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 176 |  | 8998406.04 |  | 8998406.04 | 8942311.85 |  | 8942311.85 | Engr. Nelson Pajarillo Simon King
| 31) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage at Brgy. Dalig, Teresa, Rizal | [16 empty] | 1555300.04 |  | 1555300.04 | 1533841.75 |  | 1533841.75
3000-000-1-2-11-399-006-217 | a) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage at Abuyod National High School, Brgy. Dalig | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 80 |  | 896070.57 | 896070.57 |  | 883426.19 | 883426.19 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-218 | b) Repair/Repainting of Ynares Multi-Purpose Covered Court & Stage at Abuyod Elem. School, Brgy. Dalig | PEO |  |  |  | 25-31 Oct. 21 |  |  | 2021-11-15 | 2021-11-19 | 2021-11-22 | 2021-12-03 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 80 |  | 659229.47 | 659229.47 |  | 650415.56 | 650415.56 |  | Engr. Nelson Pajarillo Simon King
3000-300-1-2-11-511-004-119 | 1) Repainting of Elevated Water Tank and Pumphouse at Rainbow Village I, Brgy. Kalayaan, Angono, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 32 | GF | 149639.47 | 149639.47 |  | 1134354.21 | 1134354.21 |  | Engr. Nelson Pajarillo Simon King
3000-400-1-2-21-005-008-002 | 2) Upgrading of Rizal Provincial Hospital System (RPHS) Margarito A. Duavit Memorial Hospital, Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 96 | GF | 2549596.14 |  | 2549596.14 | 2530494.91 |  | 2530494.91 | Engr. Nelson Pajarillo Simon King
3000-400-1-2-21-009-006 | 3) Construction of Six (6)-Seater Comfort Room for Rizal Provincial Hospital System (RPHS) Margarito A. Duavit Memorial Hospital at Brgy. Darangan, Binangonan, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 100 | GF | 1867055.61 |  | 1867055.61 | 1838013.46 |  | 1838013.46 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-21-009-006 | 4) Repair/Repainting of Ynares School Buildings at Bagumbong Elem. School, Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 96 | SEF | 3198619.01 | 3198619.01 |  | 3163340.67 | 3163340.67 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002-074 | 5) Improvement of Road at Brgy. 2nd District, Jalajala, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 60 | GF | 609511.33 |  | 609511.33 | 592623.18 |  | 592623.18 | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-002 | 6) Installation of Solar Streetlights at Brgy. Bagumbong, Jalajala, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 100 | GF | 400116.22 |  | 400116.22 | 382102.64 |  | 382102.64 | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-209 | 7) Repair/Repainting of Ynares School Buildings at Lagundi Elem. School, Brgy. Lagundi, Morong, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 90 | SEF | 2672587.12 | 2672587.12 |  | 2643385.33 | 2643385.33 |  | Engr. Nelson Pajarillo Simon King
3000-000-1-2-11-399-006-210 | 8) Repair/Repainting of Ynares School Building at Talaga Elem. School, Sitio Talaga, Brgy. Maybancal, Morong, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 45 | SEF | 1521391.26 | 1521391.26 |  | 1499542.05 | 1499542.05 |  | Engr. Nelson Pajarillo Simon King
3000-400-1-2-21-009-007 | 9) Construction of Six (6)-Seater Comfort Room for Rizal Provincial Hospital System (RPHS) Casimiro A. Ynares, Sr. Memorial Hospital at Brgy. Burgos, Rodriguez, Rizal | PEO |  | Public Bidding |  | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 100 | GF | 1932283.69 |  | 1932283.69 | 1901197.84 | 1901197.84 |  | Engr. Nelson Pajarillo Simon King
8000-000-1-1-51-001-013-017 | 10) Improvement of Daang Bakal Road (GSIS), San Mateo, Rizal | PEO |  | Public Bidding | 2021-11-26 | 30 -Nov.-6- Dec-21 |  |  | 2021-12-20 | 2021-12-27 | 2021-01-07 |  | 2021-01-13 | 2021-01-21 | 2021-01-28 | 150 | GF | 50995929.59 |  | 50995929.59 | 50820972.72 | 50820972.72 |  | Engr. Nelson Pajarillo Simon King
Total Alloted Budget of On-going Procurement Activities
| Prepared by: | [8 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  | MA. TERESA E. LASQUETY | [12 empty] | Engr. LUISITO G. MUNSOD | [8 empty] | HON. REBECCA A. YNARES
|  | Head - BAC Secretariat | [12 empty] | BAC Chairperson | [8 empty] | Governor